## R19 RAN4-led non-spectrum W-SI
| AI | UID | UID | Name | WI/SI Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | SR | Revised WID/SID | TU update | Change or comment for RAN4
1 | 9.2.2 |  | 1020085 | Study on solutions for Ambient IoT (Internet of Things) in NR | FS_Ambient_IoT_solutions | Dec. 2024 | 40% | RP-240826 | 60% | RP-241943 |  | No
2 | 9.2.4 |  | 1040100 | Study on spatial channel model for demodulation performance requirements for NR | FS_NR_demod_SCM | Jun. 2025 | 0% | RP-241610 | 15% | RP-241844 | RP-241848 | No | Rev SID: Title changed, TR number added
3 | 9.2.5 |  | 1020084 | Study on AI (Artificial Intelligence)/ML (Machine Learning) for mobility in NR | FS_NR_AIML_Mob | Sep. 2025 | 25% | RP-240082 | 38% | RP-241744 |  | No | Proposals for detailed RAN4 objectives related to checking point: RP-241804, RP-241818, RP-241987, RP-241990, RP-242095, RP-242119,RP-242136
4 | 9.2.8 |  | 1030074 | Study on NR frequency range 2 (FR2) OTA (Over the Air) testing Phase 3 | FS_NR_FR2_OTA_Ph3 | Sep. 2025 | 30% | RP-241158 | 70% | RP-241845 | RP-241846 | No | Rev SID: Add AI/ML test method objective in this SI, which is related to AI/ML air interface discussions. RP-241986 is relevant to this topic.
5 | 9.2.9 |  | 1030075 | Study on IMT parameters for NR for 4400 to 4800 MHz, 7125 to 8400 MHz and 14800 to 15350 MHz | FS_NR_IMT_4400_7125_14800MHz | Dec. 2024 | 25% | RP-241326 | 50% | RP-241840 |  | No | LS from RAN4 to RAN and ITU-WP5D: RP-241716. In RP-242137, it is suggested to focus on 15GHz issues in Q4 2024.
6 | 9.2.10 |  | 1040101 | Study on NR FR1 DL fragmented carriers | FS_NR_FR1_DL_Frag_Carrier | Jun. 2025 | 0% | RP-241669 | 5% | RP-242054 | RP-242055 |  | Rev SID: title changed, UID added, small clarifications on objective, i.e., to clarify the requirements to be investigated are just for study.
7 | 9.3.1.1 |  | 1020089 | NR MIMO Phase 5 | NR_MIMO_Ph5 | Sep. 2025 |  | RP-240087 |  | RP-241775 |  | No | The potential additional objectives may need involve RAN4 efforts: RP-241762, RP-241765, RP-241774, RP-241819, RP-241820, RP-241849, RP-241903, RP-241941, RP-241965
8 | 9.3.1.1 |  | 1021089 | Core part: NR MIMO Phase 5 | NR_MIMO_Ph5-Core | Sep. 2025 | 35% |  | 55%
9 | 9.3.1.1 |  | 1022089 | Perf. part: NR MIMO Phase 5 | NR_MIMO_Ph5 | Mar. 2026 | 0% |  | 0%
10 | 9.3.1.2 |  | 1020090 | Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo | Sep. 2025 |  | RP-241614 |  | RP-242034 |  | No
11 | 9.3.1.2 |  | 1021090 | Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo | Sep. 2025 | 18% |  | 28%
12 | 9.3.1.2 |  | 1022090 | Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo | Mar. 2026 | 0% |  | 0%
13 | 9.3.1.3 |  | 1020093 | Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air | Sep. 2025 |  | RP-240774 |  | RP-241910 |  | No | Many discussions on scope and how to move forward, which may impact RAN4.
14 | 9.3.1.3 |  | 1021093 | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air | Sep. 2025 | 20% |  | 33%
15 | 9.3.1.3 |  | 1022093 | Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air | Mar. 2026 | 0% |  | 0%
16 | 9.3.1.4 |  | 1020094 | Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS | Sep. 2025 |  | RP-240801 |  | RP-241822 | RP-241824 | No | Rev WID & RP-241823: To create an 3GPP internal TR to record RF aspects for LP-WUS/WUR
17 | 9.3.1.4 |  | 1021094 | Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Core | Sep. 2025 | 20% |  | 30%
18 | 9.3.1.4 |  | 1022094 | Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Perf | Mar. 2026 | 0% |  | 0%
19 | 9.3.1.5 |  | 1020095 | Enhancements of network energy savings for NR | Netw_Energy_NR_enh | Sep. 2025 |  | RP-241650 |  | RP-241866 | RP-241868 | No
20 | 9.3.1.5 |  | 1021095 | Core part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Core | Sep. 2025 | 25% |  | 35%
21 | 9.3.1.5 |  | 1022095 | Perf. part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Perf | Mar. 2026 | 0% |  | 0%
22 | 9.3.2.1 |  | 1020091 | NR mobility enhancements Phase 4 | NR_Mob_Ph4 | Sep. 2025 |  | RP-241515 |  | RP-241915 | RP-241916 | No
23 | 9.3.2.1 |  | 1021091 | Core part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Core | Sep. 2025 | 5% |  | 20%
24 | 9.3.2.1 |  | 1022091 | Perf. part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Perf | Mar. 2026 | 0% |  | 0%
25 | 9.3.2.2 |  | 1020097 | Rel-19 Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3 | Sep. 2025 |  |  |  | RP-242333 | RP-241789 | No
26 | 9.3.2.2 |  | 1021097 | Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Core | Sep. 2025 | 25%
27 | 9.3.2.2 |  | 1022097 | Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Perf | Mar. 2026 | 0%
28 | 9.3.2.3 |  | 1020098 | XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3 | Sep. 2025 |  | RP-240791 |  | RP-241770 | RP-241771 | No
29 | 9.3.2.3 |  | 1021098 | Core part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Core | Sep. 2025 | 18% |  | 30%
30 | 9.3.2.3 |  | 1022098 | Perf. part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Perf | Mar. 2026 | 0% |  | 0%
31 | 9.3.4.1 | 941012 | 1030077 | UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4 | Sep. 2025 |  | RP-241656 |  | RP-242084 |  | No
32 | 9.3.4.1 |  | 1031077 | Core part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4 | Sep. 2025 | 20% |  | 35%
33 | 9.3.4.1 |  | 1032077 | Perf. part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4 | Mar. 2026 | 0% |  | 15%
34 | 9.3.4.2 |  | 1030078 | NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo | Sep. 2025 |  | RP-241284 |  | RP-242011 | RP-242010 | No | Rev WID: small update for the impacted spec
35 | 9.3.4.2 |  | 1031078 | Core part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo-Core | Sep. 2025 | 10% |  | 20%
36 | 9.3.4.2 |  | 1032078 | Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo-Perf | Mar. 2026 | 0% |  | 5%
37 | 9.3.4.3 |  | 1030079 | Even Further RRM enhancement for NR and MR-DC | NR_RRM_Ph5 | Sep. 2025 |  | RP-240830 |  | RP-242342 | RP-241973 | No | Rev WID &RP-241972 : to aligne companies view by changing the objective to only consider the CSSF enhancement for the case when UE is not performing multiple-Rx based simultaneous L3 measurement. Revised WID also updates the acronym and UID.
38 | 9.3.4.3 |  | 1031079 | Core part: NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5-Core | Sep. 2025 | 5% |  | 25%
39 | 9.3.4.3 |  | 1032079 | Perf. part: NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5-Perf | Mar. 2026 | 0% |  | 0%
40 | 9.3.4.4 |  | 1030081 | NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2 | Dec. 2024 |  | RP-241622 |  | RP-242031 |  | No | TU can be added for Q4
41 | 9.3.4.4 |  | 1031081 | Core part: NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2-Core | Dec. 2024 | 25% |  | 70%
42 | 9.3.4.4 |  | 1032081 | Perf. part: NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2-Perf | Jun. 2025 | 0% |  | 0%
43 | 9.3.4.5 |  | 1031082 | Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2 | Sep. 2025 |  | RP-240838 |  | RP-242079 | RP-242083 | No | Rev WID: change objective to prioritize the following scenario of the number of CCs for Type 4a/4b
44 | 9.3.4.5 |  | 1031082 | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2-Core | Sep. 2025 | 25% |  | 35%
45 | 9.3.4.5 |  | 1032082 | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2-Perf | Mar. 2026 | 0% |  | 0%
46 | 9.3.4.6 |  | 1030083 | Enhancements for Air-to-ground network for NR | NR_ATG_enh | Sep. 2025 |  | RP-241213 |  | RP-241933 | RP-241934 | No | Rev WID & RP-241935: Acronym updated, add the objective for DL-MIMO
47 | 9.3.4.6 |  | 1031083 | Core part: Enhancements for Air-to-ground network for NR | NR_ATG_enh-Core | Sep. 2025 | 10% |  | 25%
48 | 9.3.4.6 |  | 1032083 | Perf. part: Enhancements for Air-to-ground network for NR | NR_ATG_enh-Perf | Mar. 2026 | 0% |  | 0%
49 | 9.3.4.7 |  | 1030084 | NR Sidelink: Intra-band Carrier Aggregation in ITS band | NR_SL_intraB_CA_ITS-Core | Sep. 2025 | 15% | RP-240840 |  | RP-241843 |  | No
50 | 9.3.4.7 |  | 1031084 | Core part: NR Sidelink: Intra-band Carrier Aggregation in ITS band | NR_SL_intraB_CA_ITS-Core | Sep. 2025 | 15% |  | 25%
51 | 9.3.4.8 |  | 1030085 | WI on TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3 | Sep. 2025 |  | RP-241623 |  | RP-241828 |  | No
52 | 9.3.4.8 |  | 1031085 | Core part: TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3-Core | Sep. 2025 | 10% |  | 20%
53 | 9.3.4.8 |  | 1032085 | Perf. part: TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3-Perf | Mar. 2026 | 0% |  | 5%
54 | 9.3.4.9 |  | 1030086 | Enhanced requirements and test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh | Sep. 2025 |  | RP-241281 |  | RP-241984 | RP-241985 |  | Rev WID: change the second rapporteur.
55 | 9.3.4.9 |  | 1031086 | Core part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh-Core | Sep. 2025 | 0% |  | 16%
56 | 9.3.4.9 |  | 1032086 | Perf. Part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh-Perf | Mar. 2026 | 0% |  | 10%
57 | 9.3.4.10 |  | 1030080 | NR demodulation performance Phase 5 | NR_demod_Ph5 | Mar. 2026 | 0% | RP-241297 |  | RP-241996 |  | No
58 | 9.3.4.10 |  | 1032080 | Perf. part: NR demodulation performance Phase 5 | NR_demod_Ph5-Perf | Mar. 2026 | 0% |  | 14%
59 | 10.3.1 |  | 1020096 | Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 (for LTE) | IoT_NTN_Ph3 | Sep. 2025 |  | RP-241624 |  | RP-242050 | RP-242145
60 | 10.3.1 |  | 1021096 | Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Core | Sep. 2025 | 15% |  | 30%
61 | 10.3.1 |  | 1032087 | Perf. part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Perf | Dec. 2025 | 0% |  | 0%

## R19 RAN4-led spectrum WI
AI | UID | Name | WI/SI Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | SR | Revised WID/SID | TU update | Change or comment for RAN4
9.4.1.1 | 1040127 | Introduction of the NR FDD 1.4 GHz band | NR_FDD_1400MHz | Dec. 2024 |  | RP-241648 |  | RP-242343 | RP-242120 | No | Rev WID: Modify title, acronym, UID and change the completion date of Perf. Part.
9.4.1.1 | 1041127 | Core part: Introduction of the NR FDD 1.4GHz band | NR_FDD_1400MHz-Core | Dec. 2024 | 0% |  | 40%
9.4.1.1 | 1042127 | Perf. part: Introduction of the NR FDD 1.4GHz band | NR_FDD_1400MHz-Perf | Mar. 2025 | 0% |  | 40%
9.4.1.2 | 1040131 | Introduction of NR bands n87 and n88 | NR_bands_n87_n88 | Dec. 2024 |  | RP-241663 |  | RP-241816 | RP-242338 | No
9.4.1.2 | 1041131 | Core part: Introduction of NR bands n87 and n88 | NR_bands_n87_n88-Core | Dec. 2024 | 0% |  | 33%
9.4.1.2 | 1042131 | Perf. part: Introduction of NR bands n87 and n88 | NR_bands_n87_n88-Perf | Mar. 2025 | 0% |  | 33%
9.4.1.3 | 1040132 | Introduction of NR band n68 | NR_band_n68 | Dec. 2024 |  | RP-241664 |  | RP-241861 |  | No
9.4.1.3 | 1041132 | Core part: Introduction of NR band n68 | NR_band_n68-Core | Dec. 2024 | 0% |  | 25%
9.4.1.3 | 1042132 | Perf. part: Introduction of NR band n68 | NR_band_n68-Perf | Dec. 2024 | 0% |  | 25%
9.4.1.4 | 1040129 | Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband | Jun. 2025 |  | RP-241661 |  | RP-241884 | RP-241885 | No | Rev WID: modify title, UID and add parent WIDs.
9.4.1.4 | 1041129 | Core part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband-Core | Jun. 2025 |  |  | 20%
9.4.1.4 | 1042129 | Perf. part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband-Perf | Jun. 2025 |  |  | 0%
9.4.1.5 | 1040134 | Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) | NR_NTN_combinedLband | Mar. 2025 |  | RP-241689 |  | RP-241782 | RP-241856 | No | Rev WID: modify title, UID and add the supporting company.
9.4.1.5 | 1041134 | Core part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) | NR_NTN_combinedLband-Core | Mar. 2025 | 0% |  | 15%
9.4.1.5 | 1042134 | Perf. part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) | NR_NTN_combinedLband-Perf | Jun. 2025 | 0% |  | 0%
9.4.1.6 | 1040135 | Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands | Sep. 2025 |  | RP-241690 |  | RP-242344 |  | No | RP-242138: Clarify the scope to focus on introducing the single band definition for the Ku-band in this release
9.4.1.6 | 1041135 | Core part: Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands-Core | Sep. 2025 | 0% |  | 15%
9.4.1.6 | 1042135 | Perf. part: Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands-Perf | Mar. 2026 | 0% |  | 0%
9.4.1.7 | 1040121 | Core part: Additional NR bands for NR features in Rel-19 | NR_bands_xFeature_R19-Core | Sep. 2025 | 0% | RP-241677 | 15% | RP-241923 | RP-241922 | No | Rev WID: Add UID and related WIDs, update the justification part and the objective parts.
9.4.2.1 | 1040119 | Core part: Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (x<=6) and single or two NR Supplementary Uplink (SUL) bands | DC_R19_xBLTE_yBNR-Core | Sep. 2025 | 0% | RP-241673 | 10% | RP-241785 | RP-241786 | No | Rev WID: update the band combinations excel sheet. Modify the title, add UID and realted WIDs, update the justificaiton and objecives, add the TR number and add the supporting company.
9.4.2.2 | 1040120 | Core part: Rel-19 NR Carrier Aggregation (CA)/Dual Connectivity (DC) for x bands DL with y bands UL (x<7, y<3) and Supplementary Uplink (SUL) band combinations/CA band combinations with a single SUL or two SUL cells | NR_CADC_SUL_R19-Core | Sep. 2025 | 0% | RP-241674 | 20% | RP-241832 | RP-241833 | No | Rev WID: Add UID and related WIDs, update the justification part and the objective parts, add TR number, update the tasks for each rapporteur. Update the band combination excel sheet.
9.4.2.3 | 1040125 | Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 | LTE_NR_R19_Simult_RxTx-Core | Sep. 2025 | 0% | RP-241682 | 10% | RP-242087 | RP-242088 | No | Rev WID: Add UID and relaetd WIDs, update the justification and objectives.
9.4.2.4 | 1040118 | Core part: Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R19-Core | Sep. 2025 | 0% | RP-241672 | 10% | RP-241999 |  | No
9.4.3.1 | 1041122 | Core part: Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) | HPUE_DC_LTE_NR_R19-Core | Sep. 2025 | 0% | RP-241678 | 15% | RP-242340 | RP-242341 | No
9.4.3.2 | 1040123 | Core part: Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR SUL (supplementary uplink) | HPUE_NR_CADC_SUL_R19 | Sep. 2025 | 0% | RP-241679 | 10% | RP-242004 | RP-242003 | No | Rev WID: update the title, add UID, add the related WIDs, update the objectives, clarify the power class combinations, add TR numbers, and update the band combination request excel sheet.
9.4.3.3 | 1040133 | Core part: NR power class 2 RedCap (Reduced Capability) UE in FR1 | NR_PC2_RedCap_UE-Core | Sep. 2025 | 0% | RP-241665 | 20% | RP-241998 | RP-241997 | No | Rev WID: add UID, add the related WIDs, and remove the example band table.
9.4.3.4 | 1040124 | Core part: Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band, and high power UE operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single NR band | HPUE_NR_FR1_bands_R19-Core | Sep. 2025 | 0% | RP-241680 | 15% | RP-241931 | RP-241932 | No | Rev WID: modify the title and acronym, add UID, add the related WID, modify the justification and objectives, add the TR numbers.
9.4.3.5 | 1040128 | Core part: Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 | NR_n28_PC2_40MHz_CBW-Core | Sep. 2025 | 0% | RP-241660 | 20% | RP-241929 | RP-241930 | No | Rev WID: add acronym and UID.
9.4.4.1 | 1041126 | Core part: Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 | NR_bands_CA_ENDC_R19_BWs-Core | Sep. 2025 | 0% | RP-231684 | 5% | RP-241757 | RP-241758 | No | Rev WID: Modify the title and acronym, add the related WIDs, add 3MHz CBW into objective, add the new requested band and bandwidths, and add the TR number.
10.4.1 | 1040117 | Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN | Dec. 2024 | 0% | RP-241649 |  | RP-241738 | RP-241739 | No | Rev WID: UID added, HD-FDD added in the objectives, impacted specs updated.
10.4.1 | 1041117 | Core part: Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN-Core | Dec. 2024 | 0% |  | 25%
10.4.1 | 1042117 | Perf. part: Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN-Perf | Mar. 2025 | 0% |  | 0%
10.4.2 | 1040130 | Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band | Jun. 2025 | 0% | RP-241662 |  | RP-242061 | RP-242062 | No | Rev WID: modify the title, add acronym and UID, add the table to indicate the impact on core and performance part, add the related WIDs, and add the note to clarify the conclusion for the corresponding NR WID will be reused.
10.4.2 | 1041130 | Core part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band-Core | Jun. 2025 | 0% |  | 20%
10.4.2 | 1042130 | Perf. part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band-Perf | Jun. 2025 | 0% |  | 0%
10.4.3 | 1040116 | Core part: Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band | HPUE_LTE_bands_R19-Core | Sep. 2025 | 0% | RP-241681 | 10% | RP-241814 |  | No
10.4.4 | 1040115 | Core part: Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R19_xBDL_yBUL-Core | Sep. 2025 | 0% |  |  | RP-242332 | RP-242086 |  | Rev WID: update the band combination request excel sheet. Modify the title, add UID, add the parent WID and related WID (need check), update the justification and objectives and add the TR number.