## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: ASP: Abstract Service Primitive
SS: System Simulator
TTCN: Testing and Test Control Notation (version 3)
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-16:
    NR-U: endorsed Test Models & ASP updates to support semi-static channel access mode.
  Rel-17:
    NR NTN: endorsed Test Model & ASP updates to support NGSO scenario and new NTN MAC CEs.
    NR MUSIM: endorsed ASP updates to support MUSIM gap configuration.
    NR MBS: endorsed initial Test Model & ASP updates to support MBS Broadcast.
  Prose CRs to TS 38.523-3 submitted at RAN5#104 for the above.
RAN5 TTCN Workshop #66 material:
  https://portal.3gpp.org/Home.aspx#/meeting?MtgId=60698
Test models & system interface design Progress at TTCN Workshop #66 (4th July’24)
Notes: ASP: Abstract Service Primitive

## Slide 4: TTCN development Progress for period: Jun to Aug’24
Completed:
  5G Rel-15:
    IR.92 EVS default config A.2 for EN-DC
  5G Rel-17:
    RedCap HD-FDD
    IMS voice & NW usability no E-UTRA in 5GS
  NB-IoT:
    Rel-17 non-terrestrial networks (NTN) NGSO
  Rel-18 baseline upgrade:
    Upgraded all type definitions to Rel-18 Jun’24 core specs (in iwd-24wk32)
Started:
  5G Rel-15:
    P-CSCF restoration
  5G Rel-17:
    NR non-terrestrial networks (NTN) GSO
  LTE:
    Rel-9 P-CSCF restoration
    Rel-12 ACB per PLMN
    Rel-18 signal level enh. NW selection (SENSE)
Progressed:
  5G Rel-15:
    NE-DC
  5G Rel-16:
    V2X with NR sidelink
    NR unlicensed (NR-U)
    Redirection with MPS ind.
  5G Rel-17:
    NPN enhancements
    NR SDT in INACTIVE state
    MR-DC further enhancements
  LTE:
    Rel-14 network policy
    Rel-17 UAS conn., id., tracking
  Mission Critical:
    Rel-16 MCData over LTE
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 5: TTCN verification Progress for period: 15th May --> 13th Aug’24
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
NR RRC DL segmentation | Rel-16 | 538 | 2 / 2 | +1 | 
5G CP SOR enhancements in connected | Rel-17 | 534 | 6 / 6 | +2 | 
NB-IoT NTN (GSO) | Rel-17 | 333_NB | 8 / 8 | +1 | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 6: TTCN verification Progress for period: 15th May --> 13th Aug’24
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 96 / 102 | = | 
NR/5GC access stratum | Rel-15 | 503 | 155 / 164 | +1 | 
NR/5GC NR-DC | Rel-15 | 503 | 13 / 16 | = | 
NR/5GC NR CA | Rel-15 | 510 | 31 / 33 | = | 
EN-DC NR CA | Rel-15 | 512 | 14 / 18 | = | 
5G private network - SNPN | Rel-16 | 518 | 7 / 9 | = | 
NR mobility enhancements | Rel-16 | 522 | 10 / 13 | = | 
NR UE power saving | Rel-16 | 533 | 3 / 9 | = | 
IMS eCall over NR/5GC (38.523) | Rel-16 | 537 | 2 / 15 | = | 
MR-DC & NR CA enhancements | Rel-16 | none | 3 / 28 | = | +3 under verification
MPS Priority Indication | Rel-16 | none | 2 / 4 | = | +1 under verification
NR reduced capability (RedCap) | Rel-17 | 530 | 7 / 10 | +1 | 
5G NW slicing enhancements - Phase 2 | Rel-17 | none | 7 / 8 | +1 | 
NR UE power saving enhancements | Rel-17 | 540 | 1 / 5 | = | 
NR eDRX | Rel-17 | 541 | 3 / 4 | = | 
NR RAN slicing enhancement | Rel-17 | none | 4 / 8 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 7: TTCN verification Progress for period: 15th May --> 13th Aug’24
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE positioning | Rel-9+ | 166, RTF-115 | 17 / 27 | = | 
MCPTT over LTE (IPCAN test model) | Rel-14 | 288, RFT-153 | 38 / 51 | = | 
IMS eCall over LTE (34.229) | Rel-14 | 298 | 5 / 12 | = | 
MCData over LTE (IPCAN test model) | Rel-14 | 329, RFT-153 | 4 / 28 | = | 
MCPTT enhancements over LTE (IPCAN test model) | Rel-15 | 330, RFT-153 | 5 / 22 | = | 
IMS over NR/5GC | Rel-15 | 505 | 92 / 94 | = | 
NR Positioning | Rel-16 | none | 10 / 29 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 15th May --> 13th Aug’24
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
CA intra-band contiguous | Rel-11 | 162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | 245 | 6 / 9 | = | 
eDRX | Rel-13 | 253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | 254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | 254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | 257 | 72 / 73 | = | Left: TCs 22.1.1.M2
LAA | Rel-13 | 272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | 295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
IMS eCall over LTE (36.523) | Rel-14 | 298 | 4 / 9 | = | 
LTE RACS | Rel-16 | none | 3 / 4 | +2 | +1 under verification
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 15th May --> 13th Aug’24
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
MCPTT over LTE (E-UTRA test model) | Rel-14 | 288, RFT-153 | 0 / 51 |  | +1 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 10
2023 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | TTCN Development Status (as of Aug’24) / Comments
MCX Client enhancements | R15to16 | L | Q3’24 | 79 | Q1’23-Q4’24 | 2.5 | 81% (@iwd-24wk24)
5G V2X with NR sidelink | Rel-16 | N,L | Q4’24 | 73 | Q4’20-Q1’25 | 2 | 54% (@iwd-24wk24)
NR in unlicensed spectrum (NR-U) | Rel-16 | N,L | Q4’24 | 15 | Q1’22-Q4’24 | 2 | 75% (@iwd-24wk24)
NB-IoT in non-terrestrial network (NTN) | Rel-17 | L | Q1’24 | 49 | Q1’23-Q2’24 | 1 | 100% (@iwd-24wk24)
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q4’24 | 1 | 43% (@iwd-23wk49)
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q3’23 | 11 | Q4’22-Q4’24 | 0.5 | 91% (@iwd-23wk49)
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 45 | Q4’22-Q1’25 | 3.5 | 5% ; Test Model work
EN-DC user plane integrity protection | Rel-17 | L,N | Q1’24 | 5 | Q1’23-Q1’24 | 0.5 | 100% (@iwd-24wk12)
NR sidelink enhancements | Rel-17 | N | Q1’25 | 2 | Q4’22-Q1’25 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q1’25 | 40 | Q4’22-Q2’25 | 1 | Not started ; no prose
NR coverage enhancements | Rel-17 | N | Q1’24 | 9 | Q1’23-Q4’24 | 2 | 11% (@iwd-24wk12)
NR SDT in INACTIVE state | Rel-17 | N | Q4’24 | 8 | Q1’23-Q4’24 | 1 | 75% (@iwd-24wk24)
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q4’24 | 22 | Q1’23-Q4’24 | 3 | 37% (@iwd-24wk24)
5G non-public network enhancements | Rel-17 | N | Q3’24 | 19 | Q1’23-Q3’24 | 2 | 95% (@iwd-24wk24)
NR QoE management and optimizations | Rel-17 | N | Q3’24 | 2 | Q1’23-Q3’24 | 0.5 | 5% ; Test Model work
NR MIMO (further) enhancements | R16to17 | N | Q2’24 | 12 | Q1’23-Q1’25 | 1.5 | 18% (@iwd-24wk12)
New/extended bands & band combinations | R16to18 | L,N | Q2’25 | n/a | Q1’21-Q2’25 | 0.5 | 26% (@iwd-24wk24)
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | 405 |  | 76 | person-months
TTCN workplan 2024
Status of 2023 tasks carried over and maintenance
Notes: Note: TTCN of some features initially started in 2023 will only be completed in 2024 due to availability of prose late in CY2023, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 11
2024 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | TTCN Development Status (as of Aug’24) / Comments
MR-DC further enhancement | Rel-17 | N | Q2’24 | 4 | Q1’24-Q3’24 | 1 | 25% (@iwd-24wk24)
UAS connectivity, identification and tracking | Rel-17 | N,L | Q3’24 | 12 | Q1’24-Q4’24 | 2 | 45% (@iwd-24wk24)
IMS voice & NW usability no E-UTRA in 5GS | Rel-17 | N,L | Q2’24 | 2 | Q1’24-Q2’24 | 0.5 | 100% (@iwd-24wk24)
IMS data channel | Rel-17 | N,L | Q3’24 | 6 | Q2’24-Q4’24 | 1 | WI stopped at TSG RP#104!
5G ATSSS – Phases 1 & 2 | R16to17 | N,W | Q3’24 | 15 | Q2’24-Q1’25 | 2 | Not started
Signal level enhanced network selection (SENSE) | Rel-18 | L | Q1’24 | 6 | Q1’24-Q3’24 | 1 | 80% (@iwd-24wk24)
Dual Tx/Rx MUSIM for NR | Rel-18 | N | Q2’25 | 4 | Q3’24-Q3’25 | 1 | Not started ; no prose
IoT NTN with enhancements | Rel-18 | L | Q4’25 | 5 | Q3’24-Q4’25 | 1.5 | Not started ; no prose
Enhanced RedCap NR UE | Rel-18 | N | Q4’25 | 13 | Q3’24-Q4’25 | 2 | Not started ; no prose
NR multi-carrier enhancements | Rel-18 | N | Q4’25 | 24 | Q3’24-Q4’25 | 1.5 | Not started ; no prose
NR coverage further enhancements | Rel-18 | N | Q4’25 | 11 | Q3’24-Q4’25 | 1.5 | Not started ; no prose
NR network energy savings | Rel-18 | N | Q4’25 | 8 | Q3’24-Q4’25 | 1 | Not started ; no prose
XR enhancements for NR | Rel-18 | N | Q4’25 | 18 | Q3’24-Q4’25 | 1.5 | Not started ; no prose
NR mobility further enhancements | Rel-18 | N | Q4’25 | 10 | Q4’24-Q4’25 | 1 | Not started ; no prose
5G non-public networks (NPN) – Phase 2 | Rel-18 | N | Q4’25 | 9 | Q4’24-Q4’25 | 1 | Not started ; no prose
Expanded & improved NR positioning | Rel-18 | N | Q2’26 | 9 | Q4’24-Q4’26 | 0.5 | Not started ; no prose
TEIx_Test (new TC coverage) | Rel-9+ | All | Q4’24 | 20 | Q1’24-Q4’24 | 3 | 2024 total after RAN5#104: 15 new tests
Total: |  |  |  | >170 |  | 22 | person-months
TTCN workplan 2024
Status of new 2024 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2024 workload is estimated at 98 person-months (pm), see previous slides.
PCG#51/OP#50 approved the 3GPP funding of 58 pm for 2024 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2024.
Current commitments for 2024 are as follows:
3GPP companies / 3GPP MRPs committed to provide 19 pm as voluntary contributions for 2024 TTCN development.
Total resources of 97 pm  estimated funding gap of 1 pm.
TTCN funding 2024
Status
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#51/OP#50 approved (decision OP50/14)
GCF | 12 | NR-NTN, NR-SDT, feMR-DC, eRedCap, NR-feMobility
CTIA/PTCRB | 6 | NR-(f)eCoverage, NR-(f)eMIMO, NR-feMobility, SENSE, NwEnergySav
Qualcomm | 2 | NR-(e)NTN, LTE/NR-eUAV
Total: | 78 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | 
Total: | 19 | 

## Slide 13
Course of action to secure funding for TF160 work in 2025:
  Prior to RAN5#104 meeting (August), a request to identify the potential TTCN development tasks in 2025 has been made to 3GPP members.
  At RAN5#104, a provisional ‘TTCN Tasks List’ has been endorsed by RAN5.
  The TTCN Tasks List will be presented at RAN#105 (Sept) for TSG RAN initial endorsement.
  The RAN Chair will then present the List to 3GPP PCG/OP (Nov) in order to support TF160 request for the TTCN funding in 2025.
  The finalized TTCN Tasks List will be reviewed and endorsed at RAN5#105 (Nov) for TSG RAN approval at RAN#106 (Dec).
Based on feedback from several RAN5 member companies and 3GPP MRPs, the list of TTCN tasks presented in the next slides has been produced by the TF160 Leader and endorsed by RAN5 at RAN5#104.
Preparing for 2025 TTCN Work
Overview

## Slide 14
2024 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2025 WkLoad | 3GPP related Work Item
5G V2X with NR sidelink | Rel-16 | N,L | Q4’24 | 73 | Q4’20-Q1’25 | 1.5 | 5G_V2X_NRSL_eV2XARC-UEConTest
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 45 | Q4’22-Q1’25 | 2.5 | NR_MBS_5MBS_5MBUSA-UEConTest
NR sidelink enhancements | Rel-17 | N | Q1’25 | 2 | Q4’22-Q1’25 | 0.5 | NR_SL_enh-UEConTest
NR sidelink relay | Rel-17 | N | Q1’25 | 40 | Q4’22-Q21’25 | 2.5 | NR_SL_Relay-UEConTest
NR MIMO further enhancements | Rel-17 | N | Q2’24 | 10 | Q1’23-Q1’25 | 0.5 | NR_feMIMO-UEConTest
5G ATSSS – Phases 1 & 2 | R16to17 | N,W | Q3’24 | 15 | Q2’24-Q1’25 | 1 | ATSSS-UEConTest, ATSSS_Ph2-UEConTest
Dual Tx/Rx MUSIM for NR | Rel-18 | N | Q2’25 | 4 | Q3’24-Q3’25 | 0.5 | NR_DualTxRx_MUSIM-UEConTest
IoT NTN with enhancements | Rel-18 | L | Q4’25 | 5 | Q3’24-Q4’25 | 0.5 | IoT_NTN_enh_plus_CT1-UEConTest
Enhanced RedCap NR UE | Rel-18 | N | Q4’25 | 13 | Q3’24-Q4’25 | 1 | NR_redcap_enh_plus_CT1-UEConTest
NR multi-carrier enhancements | Rel-18 | N | Q4’25 | 24 | Q3’24-Q4’25 | 2 | NR_MC_enh-UEConTest
NR coverage further enhancements | Rel-18 | N | Q4’25 | 11 | Q3’24-Q4’25 | 1 | NR_cov_enh2-UEConTest
NR network energy savings | Rel-18 | N | Q4’25 | 8 | Q3’24-Q4’25 | 0.5 | Netw_Energy_NR-UEConTest
XR enhancements for NR | Rel-18 | N | Q4’25 | 18 | Q3’24-Q4’25 | 1.5 | NR_XR_enh_plus_CT1-UEConTest
NR mobility further enhancements | Rel-18 | N | Q4’25 | 10 | Q4’24-Q4’25 | 1 | NR_Mob_enh2-UEConTest
5G non-public networks (NPN) – Phase 2 | Rel-18 | N | Q4’25 | 9 | Q4’24-Q4’25 | 1 | eNPN_Ph2-NGRAN_plus_CT1-UEConTest
Expanded & improved NR positioning | Rel-18 | N | Q2’26 | 9 | Q4’24-Q4’26 | 1 | NR_pos_enh2-UEConTest
New/extended bands & band combinations | Rel-18 | L,N | Q2’25 | n/a | Q1’21-Q2’25 | 0.5 | NR_lic_bands_BW_R18-UEConTest, NR_CADC_NR_LTE_DC_R18-UEConTest, IoT_NTN_{extLband/FDD_LS_band}-UEConTest
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | 296 |  | 70 | person-months
Preparing for 2025 TTCN Work – Tasks List
2024 tasks completion and maintenance
Notes: Note: TTCN of some features initially started in 2024 will only be completed in 2025 due to availability of prose late in CY2024, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 15
2025 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2025 WkLoad | 3GPP related Work Item
LTE Band 106 (3 MHz BW) | Rel-18 | L | Q1’25 | n/a | Q1’25-Q2’25 | 2 | LTE_900MHz_US-UEConTest
NR FR1 less than 5MHz BW (3 MHz BW) | Rel-18 | N | Q4’25 | n/a | Q1’25-Q4’25 | 2 | NR_FR1_lessthan_5MHz_BW-UEConTest
NR MT SDT | Rel-18 | N | Q4’25 | 6 | Q1’25-Q4’25 | 1.5 | NR_MT_SDT-UEConTest
NR/MR-DC IDC enhancements | Rel-18 | N,W | Q2’26 | 5 | Q1’25-Q2’26 | 1 | NR_IDC_enh-UEConTest
NR Air-to-ground network | Rel-18 | N | Q2’25 | ~2 | Q1’25-Q4’25 | 0.5 | NR_ATG-UEConTest
NR MIMO evolution for DL & UL | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q4’25 | 0.5 | NR_MIMO_evo_DL_UL-UEConTest
Enhanced NR support for high-speed train scenario in FR2 | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q4’25 | 0.5 | NR_HST_FR2_enh-UEConTest
MCX Client – Rel-17 enhancements | Rel-17 | L,N | Q3’25 | ~30 | Q1’25-Q4’25 | 4 | MCProtoc17_enh3MCPTT_eMCData3_ MCOver5GS-UEConTest / new
LTE based 5G terrestrial broadcast | Rel-18 | L | Q4’25 | ~20 | Q1’25-Q4’25 | 3 | LTE_terr_bcast_bands / new
NR NTN enhancements | Rel-18 | N | Q4’25 | ~15 | Q1’25-Q4’25 | 3 | NR_NTN_enh_plus_CT-UEConTest / new
IMS data channel | Rel-18 | N,L | Q4’25 | ~6 | Q1’25-Q4’25 | 2 | NG_RTC-UEContest / new
5G ATSSS – Phase 3 | Rel-18 | N,W | 2025 | ~8 | 2025 | 2 | ATSSS_Ph3 / no test Work Item yet
NR support for UAV | Rel-18 | N | 2025 | TBD | 2025 | 2 | NR_UAV, UAS_Ph2 / no test Work Item yet
Enhanced LTE support for UAV | Rel-18 | L | 2025 | TBD | 2025 | 2 | LTE_UAV_enh, UAS_Ph2 / no test Work Item yet
NR MBS enhancements | Rel-18 | N | 2025 | TBD | 2025 | 1 | NR_MBS_enh / no test Work Item yet
NR sidelink relay enhancements | Rel-18 | N | 2025 | TBD | 2025 | 1 | NR_SL_relay_enh / no test Work Item yet
TEIx_Test (new TC coverage) | Rel-8+ | All | n/a | 20 | Q1’25-Q4’25 | 3 | TEIx_Test
Total: |  |  |  | >116 |  | 31 | person-months
Preparing for 2025 TTCN Work – Tasks List
New 2025 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 16
2025 Funding: 2025 workload is estimated at 101 person-months (pm), see previous slides.
  58 pm of funding to be requested to 3GPP PCG/OP.
  43 pm of resources to be obtained through additional funding and/or voluntary contributions from 3GPP companies and/or 3GPP MRPs.
    Commitments received to date:
    3GPP member companies and MRPs are respectfully asked to consider providing funding support for the TTCN tasks in 2025.
 Action to TSG RAN at RAN#105:
  TSG RAN is requested to endorse the 2025 TTCN Tasks List in slides 15 & 16, and to request for the 3GPP TTCN funding of 58 person-months at PCG#53 / OP#52.
Funding |  | 
Entity | Person-months | Comments
3GPP | TBD | 
TBD | TBD | 
Total: | TBD | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
Keysight | 1 | 
Rohde&Schwarz | 1 | 
Total: | 2 | 
Preparing for 2025 TTCN Work
Funding

## Slide 17: Annexes

## Slide 18: TTCN deliveries and baseline 2024 schedule
One TTCN-2 full delivery (FDD) and five TTCN-3 full deliveries.
Type definitions baseline upgrade to 3GPP Release 18 required in 2024:
  Rel-18 Stage3 freeze declared by 3GPP in March 2024.
  Rel-18 ASN.1 freeze declared by 3GPP in June 2024.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
 wk03 |  |  | 19-Jan |  | GCF CAG#77 (24-25 Jan)
 wk09 |  |  | 01-Mar |  | PTCRB PVG#104 (5-7 Mar)
 wk12 | 22-Mar | 18-Mar | 22-Mar | TTCN-3 | 
 wk16 |  |  | 19-Apr |  | GCF CAG#78 (23-24 Apr)
 wk19 |  |  | 10-May |  | PTCRB PVG#105 (14-16 May)
 wk22 |  |  | 31-May |  | GCF CAG#78bis (4 Jun)
 wk24 | 14-Jun | 10-Jun | 14-Jun | TTCN-3 | 
 wk29 |  |  | 19-Jul |  | GCF CAG#79 (23-24 Jul)
 wk32 | 09-Aug | 31-Jul |  | TTCN-3 Rel-18 Baseline upgrade | Move to Rel-18 Jun’24 baseline
 wk32 |  |  | 09-Aug |  | PTCRB PVG#106 (13-15 Aug)
wk37 | 13-Sep | 09-Sep | 13-Sep | TTCN-3 | 
wk41 |  |  | 11-Oct |  | GCF CAG#80 (15-16 Oct)
wk44 |  |  | 01-Nov |  | PTCRB PVG#107 (5-7 Nov)
wk49 | 06-Dec | 02-Dec |  | TTCN2 (FDD) | 
wk50 | 13-Dec | 09-Dec | 13-Dec | TTCN-3 |