## Cover sheet
3GPP TSG-RAN5 Meeting #104 | [7 empty] | R5-244471
Maastricht, Netherlands, Aug 19 - 23, 2024
Agenda Item: | 7.5.2
Source: | CMCC,Mediatek,CAICT
Title: | UE Conformance - IoT NTN enhancements
Work item code: | IoT_NTN_enh_plus_CT1-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At RAN#103 meeting in March 2024, a Release 18 work item for UE Conformance - IoT NTN enhancements plus CT1 aspects core & performance requirements for Non-Terrestrial Networks (NTN) was approved [1]. The objective of this work item is to define the UE conformance requirements corresponding to WID on IoT NTN UE with Unique identifier 1030073. This work item will cover RF/RRM/Demod conformance test specifications with IoT NTN.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 27% (+12%) | 2 (+2) | 12
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FDD) |  | 27.3% (+11.7%) | 2 (+2) | 12
FDD |  | 27.3% (+11.7%) | 2 (+2) | 12
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
LTE RF/RRM
RF common parts | 36.521-4
RF Demod test cases | 36.521-4 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2 | 0% |  |  | 0%
RRM test cases | 36.521-3 | 19.8% (-0%) | 0 | 7 | 19.8% (-0%) | 0 | 7
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 40% (+40%) | 2 (+2) | 5 | 40% (+40%) | 2 (+2) | 5
Applicability Protocol test cases | 36.523-2 | 40% (+40%) |  |  | 40% (+40%)
Test suites (TTCN) | 36.523-3
5 References
[1] RP-240784 | New WID on UE Conformance - IoT NTN enhancements plus CT1 aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - IoT NTN enhancements plus CT1 aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | IoT_NTN_enh_plus_CT1-UEConTest
WP Scope: |  | This work plan covers the tasks needed to include NB-IoT (Narrowband IoT) enhancement core & performance requirements for Non-Terrestrial Networks (NTN)
WP Resp: |  | Danni Song (CMCC); Danbo Fu (MediaTek); Yufeng Zhang(CAICT) |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD
27.3% (+11.7%)
29
18.9 (+0)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 36.508 | 8 | NB-IoT test environment | Clause header |  |  |  |  | 0
|  | 36.508 | 8.1 | NB-IoT Common test environment | Sub-clause header |  |  |  |  | 0
1 |  | 36.508 | 8.1.4.3 | NB-IoT Reference system configurations | Update SIB information for neighbor cell | MediaTek | RAN5#106 (Feb-25) | R5-245567 | allen.zhang@mediatek.com juan.huang@mediatek.com | 0.5 | 50% (+50%) | 50% (+50%) |  | 50%
2 |  | 36.508 | 8.1.5B | Common test environment for Vertical UEs | Update Common test environment | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com juan.huang@mediatek.com | 0.5 | 0% | 0% |  | 0%
|  | 36.508 | 8.4 | NB-IOT Test environment for RRM tests | Sub-clause header
3 |  | 36.508 | 8.4.2.1.3 | NB-IoT Common contents of system information messages | Update SIB information for neighbor cell | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com juan.huang@mediatek.com | 0.5 | 0% | 0% |  | 0%
4 |  | 36.508 | 8.4.6 | Test environment for NB-IoT NTN RRM testing | Update UE location and ephemeris information for location based test cases and NGSO multi-cell test cases |  |  |  |  | 0.5 | 0% | 0% |  | 0%
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0
TBD |  | 36.509 | <Clause> | TBD | TBD |  |  |  |  | 0
LTE RF/RRM
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
|  | 36.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 36.521-2 | 4 | Recommended test case applicability | Clause header |  |  |  |  | 0
5 |  | 36.521-2 | 4.3.3 | RRM conformance test cases for NB-IoT/eMTC NTN | Add test applicability for RRM test cases | CMCC | RAN5#109 (Nov-25) |  | zhaoluyang@chinamobile.com | 0.5 | 0% | 0% |  | 0%
TS 36.521-3: RRM test cases
|  | 36.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 36.521-3 | 13 | E-UTRAN Standalone Tests for UE Category NB for Satellite Access | Clause header |  |  |  |  | 0
|  | 36.521-3 | 13,1 | RRC_IDLE state for satellite access | Sub-clause header |  |  |  |  | 0
|  | 36.521-3 | 13.1.1 | Cell re-selection for satellite access | Sub-clause header |  |  |  |  | 0
6 |  | 36.521-3 | 13.1.1.1_1 | HD – FDD Intra frequency case for UE Category NB1 Standalone mode in normal coverage for GSO and NGSO | Introduce GSO and NGSO test case | MediaTek | RAN5#105 (Nov-24) |  | allen.zhang@mediatek.com | 0.5 | 0% | 0% |  | 0%
7 |  | 36.521-3 | 13.1.1.2_1 | HD – FDD Intra frequency case for UE Category NB1 Standalone mode in normal coverage with serving cell RRM measurement relaxation for GSO and NGSO | Introduce GSO and NGSO test case | MediaTek | RAN5#105 (Nov-24) |  | allen.zhang@mediatek.com | 0.5 | 0% | 0% |  | 0%
8 |  | 36.521-3 | 13.1.1.3_1 | HD – FDD Intra frequency case for UE Category NB1 Standalone mode in normal coverage with UE specific DRX for GSO and NGSO | Introduce GSO and NGSO test case | MediaTek | RAN5#105 (Nov-24) |  | allen.zhang@mediatek.com | 0.5 | 0% | 0% |  | 0%
9 | Y | 36.521-3 | 13.1.1.4 | HD – FDD Inter frequency case for UE Category NB1 Standalone mode in normal coverage | Test in A.13.1.1.4 in TS 36.133 (R4-2406522) | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com | 1 | 0% | 0% |  | 0%
10 | Y | 36.521-3 | 13.1.1.5 | HD – FDD Intra frequency case for UE Category NB1 Standalone mode in enhanced coverage, location-based cell reselection for NGSO | Test in A.13.1.1.5 in TS 36.133 (R4-2406522) | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com | 1 | 0% | 0% |  | 0%
11 | Y | 36.521-3 | 13.1.1.6 | HD – FDD Inter frequency case for UE Category NB1 Standalone mode in enhanced coverage, time-based cell reselection for NGSO | Test in A.13.1.1.6 in TS 36.133 (R4-2406522) | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com | 1 | 0% | 0% |  | 0%
|  | 36.521-3 | 13.3 | RRC connection mobility control for satellite access | Sub-clause header |  |  |  |  | 0
|  | 36.521-3 | 13.3.1 | RRC re-establishment for satellite access | Sub-clause header |  |  |  |  | 0
12 |  | 36.521-3 | 13.3.1.1_1 | HD-FDD Intra-frequency RRC Re-establishment for UE category NB1 in Standalone mode under normal coverage for GSO and NGSO | Introduce GSO and NGSO test case | MediaTek | RAN5#105 (Nov-24) |  | sapling.lin@mediatek.com | 0.5 | 0% | 0% |  | 0%
13 |  | 36.521-3 | 13.3.1.2_1 | HD-FDD Intra-frequency RRC Re-establishment for UE category NB1 in Standalone mode under enhanced coverage for GSO and NGSO | Introduce GSO and NGSO test case | MediaTek | RAN5#105 (Nov-24) |  | sapling.lin@mediatek.com | 0.5 | 0% | 0% |  | 0%
14 | Y | 36.521-3 | 13.3.1.3 | HD-FDD Inter-frequency RRC Re-establishment for UE category NB1 in Standalone mode under enhanced coverage | Test in A.13.3.1.3 in TS 36.133 (R4-2406522) | MediaTek | RAN5#106 (Feb-25) |  | sapling.lin@mediatek.com | 1 | 0% | 0% |  | 0%
|  | 36.521-3 | 13.5 | UE measurement procedures in RRC_CONNECTED state for UE category NB1 for satellite access | New Sub-clause header |  |  |  |  | 0
15 | Y | 36.521-3 | 13.5.1 | HD-FDD Intra-frequency neighbour cell measurement for UE category NB1 in standalone mode under normal coverage for Satellite Access | Test in A.13.5.1 in TS 36.133 (R4-2406522) | CMCC | RAN5#109 (Nov-25) | R5-243688, R5-243060 | zhaoluyang@chinamobile.com | 1 | 70% | 70% |  | 70%
16 | Y | 36.521-3 | 13.5.2 | HD-FDD Inter-frequency neighbour cell measurement for UE category NB1 in standalone mode under normal coverage for Satellite Access | Test in A.13.5.2 in TS 36.133 (R4-2406522) | CMCC | RAN5#109 (Nov-25) | R5-243689, R5-243060 | zhaoluyang@chinamobile.com | 1 | 70% | 70% |  | 70%
17 | Y | 36.521-3 | 13.5.3 | HD-FDD Intra-frequency location-based neighbour cell measurement for UE category NB1 in standalone mode under normal coverage for Satellite Access | Test in A.13.5.3 in TS 36.133 (R4-2406522) | CMCC | RAN5#109 (Nov-25) | R5-243690, R5-243060 | zhaoluyang@chinamobile.com | 1 | 70% | 70% |  | 70%
18 |  | 36.521-3 | Annex E | Annex E (normative): Cell configuration mapping | Add cell config information to "Table E-4: Cell configuration mapping for IoT NTN RRM testing" | CMCC | RAN5#109 (Nov-25) |  | zhaoluyang@chinamobile.com | 0.1 | 0% | 0% |  | 0%
|  | 36.521-3 | Annex F | Annex F (normative): Measurement uncertainties and Test Tolerances | clause header |  |  |  |  | 0
|  | 36.521-3 | F.1 | Acceptable uncertainty of Test System (normative) | Sub-clause header |  |  |  |  | 0
19 |  | 36.521-3 | F.1.2 | Measurement of RRM requirements | add MU analysis for new RRM test cases | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com | 0.5 | 0% | 0% |  | 0%
|  | 36.521-3 | F.3 | Test Tolerance and Derivation of Test Requirements (informative) | Sub-clause header |  |  |  |  | 0
20 |  | 36.521-3 | F.3.2 | Measurement of RRM requirements | add TT analysis for new RRM test cases | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com | 0.5 | 0% | 0% |  | 0%
TR 36.903: Test Tolerances analysis RRM test cases
|  | 36.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
21 |  | 36.903 | 5 | Grouping of test cases defined in TS 36.521-3 | Update grouping of new RRM test cases defined in TS 36.521-3. | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com | 0.5 | 0% | 0% |  | 0%
|  | 36.903 | 7 | Determination of Test Tolerances | Clause header |  |  |  |  | 0
22 |  | 36.903 | 7.1 | General | Add the zip files into the attachments. The RRM test cases which have been analysed to determine Test Tolerances are included as .zip files. The name of the zip file indicates the test cases covered in TS 36.521-3. | MediaTek | RAN5#106 (Feb-25) |  | allen.zhang@mediatek.com | 0.1 | 0% | 0% |  | 0%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NB-IoT
26 | Y | 36.523-1 | 22.2.17 | NB-IoT / NTN / cell reselection/ Intra E-UTRAN / distance based measurement | **** TP1: [TS 36.304, clause 5.2.4.1, 5.2.4.2a and 5.2.4.6] (1) with { UE in RRC_IDLE state supports location-based measurement initiation and has obtained its location information } ensure that { when { the distance between the UE and the serving cell reference location is larger than or equal to distanceThresh } then { UE performs intra-frequency measurements and reselects the new cell after UE detects the cell re-selection criteria are met } } | CAICT | RAN5#104 (Aug-24) | R5-245569 | zhangyufeng@caict.ac.cn | 1 | 100% (+100%) | 100% (+100%) |  | 100%
23 | Y | 36.523-1 | 22.3.1.14 | NB-IoT / NTN /Correct HARQ process/ HARQ disabling | **** TP1: [TS 36.321, clause 5.3.2.1, 5.3.2.2, 5.4.2.1 and 5.4.2.2.] Test Purpose (TP) (1) with { UE in E-UTRA RRC_CONNECTED state with DRB established and has 2 DL HARQ processes and the second HARQ process feedback is disabled by configuring downlinkHARQ-FeedbackDisabled } ensure that { when {the UE receives MAC PDUs for these two HARQ processes } then { the UE doesn`t transmits ACK/NACK for the second HARQ process while ACK is transmitted for the first HARQ} } (2) with { UE in E-UTRA RRC_CONNECTED state with DRB established and has 2 UL HARQ processes and the second HARQ process feedback is disabled by configuring HARQ Mode B } ensure that { when { UE transmits MAC PDUs but does not receive an ACK for these 2 HARQ processes } then { UE re-transmits the MAC PDU for the first HARQ process while not re-transmit for the second HARQ process } } | MediaTek | RAN5#104 (Aug-24) | R5-245568 | juan.huang@mediatek.com | 1 | 100% (+100%) | 100% (+100%) |  | 100%
24 | Y | 36.523-1 | 22.3.1.15 | NB-IoT / NTN / GNSS validity duration reporting | **** TP1: [TS 36.321 clauses 5.4.10] (1) with { UE in E-UTRA RRC_CONNECTED state and GNSS is valid } ensure that { when { UE is requested to report the remaining GNSS measurement validity duration } then { the UE transmits a GNSS Validity Duration Report MAC CE } } | MediaTek | RAN5#109 (Nov-25) |  | juan.huang@mediatek.com | 1 | 0% | 0% |  | 0%
25 | Y | 36.523-1 | 22.4.31 | NB-IoT / NTN / discontinuous coverage | **** TP1: [TS 36.331 clauses 5.3.3.23] (1) with { UE in E-UTRA RRC_CONNECTED state supports discontinuous coverage and SIB33-NB broadcasts neighbour cell information } ensure that { when { t-Service expires and T310 is still running } then { the UE enters RRC_IDLE state and reselects to the neighbour cell after UE is in its coverage } } | CMCC | RAN5#109 (Nov-25) |  | zhaoluyang@chinamobile.com | 1 | 0% | 0% |  | 0%
27 | Y | 36.523-1 | 22.5.24 | NB-IoT / NTN / enhanced discontinuous coverage | **** : [TS 24.301, clause 4.11.4, 5.5.1.2 and 5.5.3.2.] (1) with { the UE is switched-off and supports enhanced discontinuous coverage } ensure that { when { UE is powered on } then { the UE transmits an ATTACH REQUEST message with the EDC bit set to "Enhanced discontinuous coverage supported" in the UE network capability IE } } (2) with { UE in EMM-REGISTERED state and supports enhanced discontinuous coverage } ensure that { when {the UE is about to lose satellite coverage } then { the UE transmits a TRACKING AREA UPDATE REQUEST message with the unavailability type in the Unavailability information IE set to "unavailability due to discontinuous coverage".} (3) with { UE is not under satellite coverage and needs to report end of unavailability } ensure that { when { the unavailability period duration has ended } then { the UE transmits a TRACKING AREA UPDATE REQUEST message } | CMCC | RAN5#109 (Nov-25) |  | zhaoluyang@chinamobile.com | 1 | 0% | 0% |  | 0%
TS 36.523-2: Applicability for Protocol test cases
|  | 36.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
28 |  | 36.523-2 | 4 | Recommended Test Case Applicability | Addition of applicability for IoT NTN enh cases | CMCC | RAN5#109 (Nov-25) | R5-245570 R5-244673 | zhaoluyang@chinamobile.com | 0.1 | 40% (+40%) | 40% (+40%) |  | 40%
29 |  | 36.523-2 | A.4.4 | Additional information | PICS for IoT NTN enh | CMCC | RAN5#109 (Nov-25) | R5-245570 R5-244673 | zhaoluyang@chinamobile.com | 0.1 | 40% (+40%) | 40% (+40%) |  | 40%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.