3GPP TSG RAN Meeting #85		 RP- 191973

Newport Beach, USA, September 16-20, 2019

Agenda item:	9.4.5

Source: 	Nokia, Nokia Shanghai Bell

Title: 	Considerations on the scope of Physical Layer Enhancements for NR URLLC and Industrial IoT

Document for:	Discussion/Decision

# Introduction

The Status Report for WI on support of Physical Layer Enhancements for NR URLLC indicates that in principle it is on schedule for completion. However, there are aspects of this WI that depend on the NR Industrial Internet of Things WI, for which the status report indicates to be behind schedule [1]. This is particularly true for the objectives where RAN1 is involved. Given that in RAN1 those two WIs are treated under the same agenda item having a common pool of allocated TUs, in this document we provide our views on the progress in Physical Layer Enhancements for NR URLLC and NR Industrial Internet of Things from a physical layer perspective, including the proposed corrective actions. Detailed discussion on NR Industrial Internet of Things from rapporteur point of view can be found in [2].

# Summary of progress in URLLC WI and RAN1 aspects of IIoT WI

The status report for each of the WIs considered in this document detail the agreements made for the particular WI objectives, but in Table 1 and Table 2 below are Nokia’s more detailed analysis for each of the objectives.

Table 1: Progress on objectives of URLLC WID with RAN1 impact

| Objective | Overall progress | Comments |
| --- | --- | --- |
| Specification of PDCCH enhancements [RAN1] | Good | Configurable DCI format: support of new DCI format(s) agreed, some fields being configurable agreed – some fields still for discussion. Enhanced PDCCH monitoring capabilities: Basic framework based on monitoring spans for enhanced PDCCH monitoring is in place. The framework on how to handle the relation to Rel-15 per-slot capabilities is to be decided. Further details are still pending. |
| Specification of UCI enhancements [RAN1] | Good (other than the intra-UE prioritization/multiplexing part for supporting at least two HARQ-ACK codebook) | Sub-slot-based HARQ-ACK feedback: Good progress on this topic overall, some details still missing At least two HARQ-ACK codebooks: Good progress on how to identify/generate multiple codebooks. But this topic is very much related to the intra-UE prioritization and multiplexing discussions in the IIoT WI. Having more than one codebook defined without knowing how to prioritize or multiplex them for transmission makes the feature questionable/incomplete in the end. |
| Specification of PUSCH enhancements for both grant-based PUSCH and configured grant based PUSCH [RAN1] | Good | Baseline operation mode based on Option 4 agreed, details including possible post-poning and interaction with TDD operation (semi-static/dynamic flexible and DL symbols) are still pending. |
| Specification of enhancements to scheduling/HARQ [RAN1] | Poor | Not much progress on Out-of-Order HARQ-Ack, Out-of-Order PUSCH and overlapping PDSCHs so far (e.g. not a single decision available from RAN1#98) |
| Specification of enhanced inter UE Tx prioritization/multiplexing [RAN1] | Good | UL cancelation for eMBB: baseline decisions in place, details still missing including monitoring restrictions Enhanced TPC for URLLC: mechanism for dynamically scheduled PUSCH operation agreed (some details are FFS), decisions on CG PUSCH still pending |
| Specification of enhanced UL configured grant transmission [RAN1, RAN2] | Very good | Most important decisions are in place. Some details on activation / release and possible starting points for CG PUSCH still pending. |

Table 2: Progress on objectives of IIoT WID with RAN1 impact

| Objective | Overall progress | Comments |
| --- | --- | --- |
| SPS enhancements | Good | The decision on not supporting periodicity less than 1 slot in Rel-16 simplifies the further work on this topic. Details on HARQ-Ack feedback still missing. |
| Intra-UE prioritization/multiplexing | Poor for RAN1 part | Intra-UE prioritization/multiplexing is a complex topic progressing very slowly in RAN1, and RAN1 might not be able to finish it within R16 timeframe. Part of the work has not even started in RAN1 due to dependencies on discussion on PUSCH prioritization in RAN2. At the same time, lack of RAN1 progress on PUSCH vs. PUCCH prioritization slows down RAN2 progress considerably for PUSCH vs. PUSCH scenario. Additionally, this objective also impacts the work on supporting at least two HARQ-ACK codebooks simultaneously (see above in Table 1). |

As can be seen in the tables, good progress was achieved for specification of PDCCH enhancements, enhanced inter-UE Tx prioritization/multiplexing, and enhanced UL configured grant transmission. At the same time some topics are struggling due to the inherent complexity of the topic itself, the very limited time allocation, as well as due to dependencies with RAN2. These include intra-UE prioritization/multiplexing, support for at least two HARQ-ACK codebooks simultaneously, and it is our understanding that it is not possible to conclude all of those within Rel-16 timeframe in RAN1. Given the fact that there are strong inter-dependencies among those topics, it would be best to down-prioritize these topics for the remainder of Rel-16 in RAN1.

Proposal: RAN plenary is requested to consider moving objectives of support of at least two HARQ-ACK codebooks simultaneously constructed related to the URLLC WID, as well as RAN1 part of intra-UE prioritization/multiplexing related to the IIOT WID, out of Rel-16.

We believe that with such prioritization of the topics it would be possible to improve the progress on the remaining topics of eURLLC WI in RAN1, including specification of enhancements to scheduling/HARQ, which is currently struggling as well. Furthermore, thanks to removing RAN1-RAN2 interdependencies for intra-UE prioritization topic from IIoT WI, it would facilitate its progress in RAN2 considerably (please see our detailed proposal in [2]).

# URLLC WI objectives refinements

Based on the discussion above, we propose the following modifications to URLLC WID [3]:

- Specification of UCI enhancements [RAN1]

  - More than one PUCCH for HARQ-ACK transmission within a slot

  - At least two HARQ-ACK codebooks simultaneously constructed, intended for supporting different service types for a UE

In addition, we propose to simplify the intra-UE prioritization objective in the IIoT WID [4], so that physical layer impacts are avoided in Rel-16, letting RAN1 to focus on eURLLC work. The detailed proposal and explanation can be found in [2].

Proposal: RAN plenary is requested to consider approving the proposed changes to URLLC and IIoT WIDs.

# Summary

Proposal: RAN plenary is requested to consider moving objectives of support of at least two HARQ-ACK codebooks simultaneously constructed related to the URLLC WID, as well as RAN1 part of intra-UE prioritization/multiplexing related to the IIOT WID, out of Rel-16.

Proposal: RAN plenary is requested to consider approving the proposed changes to URLLC and IIoT WIDs.

# References

[1]	RP-191964, Status Report of WI: Support of NR Industrial Internet of Things (IoT); rapporteur: Nokia, Source: RAN2

[2] 	RP-191966, Considerations on the scope of WI on support of NR Industrial Internet of Things (IoT), Nokia, Nokia Shanghai Bell

[3]	RP-190728, URLLC WID; rapporteur: Huawei

[4]	RP-191965, Revised WID: Support of NR Industrial Internet of Things (IoT), Nokia, Nokia Shanghai Bell