3GPP TSG RAN meeting #85										RP-192010

Newport Beach, USA, September 16-20, 2019

## Status Report to TSG

Agenda item:			9.5.10

| WI / SI Name | Addition of wider channel bandwidth in NR band n1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: Yes | Performance part: Yes |  | Testing part: No |
| Acronym | NR_n1_BW |  |  |  |  |
| Unique ID | 840098 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-191595 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: NA | Core part: 03/2020 | Performance part: 03/2020 | Testing part: NA |  |
| Overall Completion level | Study Item: NA | Core part: 15% | Performance Part: 0% | Testing part: NA |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN WG4 |
| --- | --- | --- |
| Rapporteur | Name | Dominique Everaere |
|  | Company | Ericsson |
|  | Email | dominique.everaere@ericsson.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

Work plan was agreed [2]

#### 2.4.2	Remaining Open issues

Finalizing REFSENS (RB allocation) and A-MPR requirements for UE.

Finalize CRs to capture all necessary changes.

## 2.5	RAN5

#### 2.5.1	Agreements

#### 2.5.2	Remaining Open issues

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

## 4.	References

NOTE:	This can be e.g. a list of all related Tdocs in the affected WGs since last TSG, references to LSs, produced TRs/TSs, the work/study item description or status reports of previous TSGs.

[1] R4-1909585 	n1 30MHz Requirements, Qualcomm, RAN4#92

[2] R4-1908890	Band n1 – 30MHz CBW – Work Plan, Ericsson, RAN4#92

[3] R4-1908891	Band n1 – 30MHz CBW – Draft CR to TS 38.104, Ericsson, RAN4#92

[4] R4-1908892	Band n1 – 30MHz CBW – UE RF REFSENS, Ericsson, RAN4#92

[5] R4-1908893	Band n1 – 30MHz CBW – UE RF spurious and A-MPR simulation assumptions, Ericsson, RAN4#92

18.08.2019		minor adaptations for RAN #85

12.05.2019		minor adaptations for RAN #84

27.02.2019		minor adaptations for RAN #83

21.11.2018		completion levels with colours added (for RAN #82)

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects (for RAN #81)

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template