**3GPP TSG RAN Meeting #89-e RP-202096**

**Electronic Meeting, September 14 - 18, 2020**

**Agenda item:** 9.8.1

**Source:** Moderator (Samsung)

**Title:** Moderator’s summary for email discussion [90E][24][R17\_MIMO\_workflow]

**Document for:** Discussion and Decision

1. Introduction

Per chairman’s instruction, the goal and pertinent contributions for this email discussion is as follows:

* Goal: Generate an agreeable way forward.
* Input contributions covered:  2300 [1]

Table 1 Summary of the identified input contributions

|  |  |
| --- | --- |
| **Tdoc** | **Summary of issue and proposals** |
| RP-202300 | Issue: Sending LS to RAN2/4 in the early phase of Rel.17 NR FeMIMO WI:* RAN4 is occupied with Rel.16 NR\_eMIMO and RAN2 work load is close to critical
* RAN2/4 will not start until the last (2) RAN1 meeting(s) before RAN1 freeze with limited TU allocation
* Difficult to gauge the required amount of work in RAN2/4 to generate helpful LS response to RAN1
* Inter-WG ping-pong inevitably disrupts RAN1 progress

Proposal: RAN to discuss and (preferably) provide guideline (criteria) for the necessity of LS from RAN1 to RAN2/4 in early phase of Rel.17 NR FeMIMO |

1. Compilation of companies’ inputs: initial round

During the initial round, interested companies are encouraged to share their view on the following:

|  |
| --- |
| Given the issues with sending LS to RAN2/4 in the early phase of Rel.17 NR FeMIMO WI (e.g. those identified in RP-202300):* Q1: What general criteria should RAN1 employ to address this problem?
* Q2: If an LS is sent by RAN1 to RAN2/4 and the associated amount of required work seems infeasible, how should RAN2/4 respond?
 |

Table 2 Inputs – initial round

|  |  |
| --- | --- |
| **Company** | **View** |
| Samsung | On Q1: * In general, sending an LS to RAN2/4 in the early phase of FeMIMO is done only when it is extremely necessary.
* When a topic involves some RAN2/4 aspects, interested companies can discuss such aspects in RAN1 contributions and consolidate their inputs in RAN1. This also includes gauging the amount of RAN2/4 works involved in providing sufficiently helpful response if an LS is to be sent.

On Q2: * If the amount of works seems excessive, RAN2/4 may simply respond that at that stage, RAN2/4 cannot provide a response due to the current workload.
 |
| FUTUREWEI | Q1 and Q2 are simply of normal RAN WG work procedures and the answers to them may not address the issue when RAN2 and RAN4 effort are needed to provide answers to RAN1 questions. The proper solution is to ensure RAN2 and RAN4 enough time with or without TU assigned explicitly to work out the reply to RAN1 LS. |
| Apple | For Q1RAN1 can be cautious on sending LS to RAN2/4 during the early phase of the FeMIMO. For Q2RAN2/4 can reply the LS back to RAN1 indicating the situation that it is exceeding the RAN2/4 bandwidth. Then RAN1 can try to find a solution, or it can be escalated to RAN plenary  |
| vivo | In our view, for Q1, it is normal procedure to send LS to relevant WGs based on consensus in RAN1. There are even cases of LS being sent to RAN4 during “study item”. For Q2, it is up to RAN2/4 how and when to respond. It may have impact on progress of the issue in RAN1 depending on how closely the response(s) from RAN2/4 is related to the specific technique. If the specific issue is not possible to discuss/progress in RAN1 due to lack of input from RAN2/4 then it can be escalated to RAN or it can be discussed in future meetings depending on criticality and completion of WI. |
| ZTE | Q1:Due to the extremely stressful TU budget in RAN2 and RAN4, and the fact that the start time of RAN2/RAN4 FeMIMO WI is much later than RAN1, an LS out from RAN1 is expected to have large latency in terms of response. Hence we agree with the assessment that RAN1 should send out an LS only when it is extremely necessary, e.g., when it is not possible for RAN1 to find a solution.Q2:If so, RAN2/RAN4 should reply that it exceeds the RAN2/RAN4 capacity, and it is encouraged to find a solution in RAN1. |
| OPPO | For Q1:The information sharing by LS among different WGs are normal work procedures. Meanwhile, RAN1 should carefully consider the workload of RAN2 and RAN4, and try to only send out the “necessary” LS especially in the early phase. For example, without the feedback of the “necessary” LS, RAN1 work cannot move forward. For Q2:It is up to the discussion and final decision in RAN2/RAN4 for each LS. For different LS, RAN2/RAN4 may have different actions depending on their evaluation of the corresponding issues.  |
| LG | For Q1, we agree with most companies that sending LS from RAN1 to RAN2/4 should be very careful. On the other hand, we see some needs to start RAN2 work as early as possible especially for the support of MTRP BFR, which would require TU allocation for RAN2. For Q2, RAN2/4 can reply that they cannot provide a response due to the current workload, and may provide the answer later when they have enough TU to discuss that topic. |
| Qualcomm | For Q1: LS should be sent if the continuation of RAN1 work is dependent on information received from other WGs, where providing the information is not in RAN1’s expertise.For Q2: Other WGs can always respond with stating that immediate response is not possible and stating when response may be provided. |
| CATT | Q1: Sending LS to RAN2/RAN4 should only be considered when an official reply is needed for RAN1 to progress. Otherwise if the purpose is to notify about RAN1 decision or collect non-official information that can addressed internally within each company, LS should be avoided (until RAN2/RAN4 TU/workload frees up). Q2: RAN2 can always reply that the amount of work is infeasible based on their schedule.  |
| Nokia | Q1: RAN should not limit cross-WG communications. Instead sufficient TUs should be allocated to the RAN WGs like RAN2, which need to work with the given WID like feMIMO. In our view feMIMO work should start earlier in RAN2 and RAN4 and needed TUs should be added to RAN2 and RAN4 so that they can provide needed answers to RAN1 and also start their work sufficiently early. In Rel-16 RAN2 work on eMIMO was started far too late, which created lots of challenges for stable specification finalization. Q2: If a work item is approved in 3GPP RAN, it is necessary that all RAN WGs have TUs to address questions and issues in their areas. No new items or objectives should be considered before it is ensured that there are sufficient amount of TUs for the existing items and objectives.  |
| Huawei | Q1: It is fully up to RAN1 to decide whether a LS is needed for RAN2/4 to seek RAN2/RAN4 guidance, if extra RAN2/RAN4 information is considered to be necessary for further RAN1 design/discussion. There is no restriction about whether/when RAN1 can send a LS to other WGs, from RAN perspective. RAN1 can continue as usual. Q2: It is fully up to RAN2/4 to consider whether associated amount work for replying LS is feasible without dedicated TU. If RAN1 has concerns about RAN2/RAN4 workload of replying LS, related question can be asked in that LS and trigger RAN2/4 TU discussion/update for FeMIMO in RAN as soon as possible. |
| Ericsson | We share the same view as Qualcomm and Nokia. However, understanding the issues that caused this discussion, some improvements in FeMIMO with respect to LS would help the efficiency of the work (although it is nothing different than business as usual and does not need a RAN plenary conclusion or guidance to enforce.)Examples could be that for an issue in hand, first each company internally seeks the status across different working groups. Then the LS from RAN1, if needed, should be specific and clear on questions such that the response, would help the progress across different WGs. |
| RAN2 Chairman | The sending group need to determine the need for requesting information from another group, and the sender do not need to take into account the state in the other group. For R17 LSes sent to RAN2, RAN2 will handle these LSes with high priority to not stall work in other groups, regardless if TUs are allocated or not, within reasonable limits. If the LSes in fact represent work that RAN2 anyway need to do, sooner or later, it is not wasteful to do this work sooner if needed by other group. RP TU budget principles allows some flexibility for the chairman to do such prioritization on need basis. For eMIMO, RAN2 likely can support clear decisions on changes in signaling (RRC config, RRC UE caps, MAC CE) without extensive need for discussion. However, MAC is the most controversial TS in R2 so any change to BFD/BFR on procedure level may require discussion. Changes related to Acquisitions of Common channels, measurements and mobility, if any, may also require some time for convergence in R2.  |

1. Compilation of companies’ inputs: initial round

During the initial round, interested companies are encouraged to share their view on the proposed way forward (after the initial round), cf. section 4:

Table 3 Inputs – intermediate round

|  |  |
| --- | --- |
| **Company** | **View** |
| vivo | The proposed way forward is reasonable, in our view, this is the normal process. We don’t see necessity for additional measure in RAN1 since whether is LS to other WGs is agreed based on consensus in all WIs. For additional TU is RAN2/4 can be discussed separately in TU budget discussion which is in discretion of relevant chairpersons. |
| Xiaomi | The WF is fine with us. We think it should be fully up to RAN1 if guidance from other WGs is needed for RAN1 discussion/decision which is not RAN1’s expertise. And we don’t see the need to add additional restrictions to RAN1 procedures for sending LS to other WGs. Besides, the early startup of RAN2/RAN4 TU would be helpful for the current RAN1 MIMO discussions. |
|  |  |

1. Summary and moderator proposals

Based on the collected inputs in section 2, the following **observation** can be made:

On sending LS to RAN2/4 in the early phase of Rel.17 NR FeMIMO WI:

* From RAN1 side, most companies opined that RAN1 send an LS to RAN2/4 only when it is necessary to further/complete the work in RAN1. Whether this is the case is to be (fully) decided by RAN1 itself.
	+ Among these companies, several companies explicitly mentioned that additional measures can be beneficial, e.g. first, each company internally seeks the status across different working groups and, later, consolidate their inputs in RAN1 to see if an LS needs to be composed.
* From RAN2/4 side, whether to respond to the LS(s) from RAN1 on this matter is to be (fully) decided by RAN2/4 themselves.
	+ For a given LS, RAN2/4 always have an option to state that an immediate response is infeasible and, in addition, indicate when such response can be made.
	+ Note: RAN2 chairman indicated that RAN2 would treat LS(s) received from RAN1 “with high priority to not stall work in [RAN1], regardless if TUs are allocated or not, within reasonable limits”
* Several companies mentioned the possibility of starting RAN2/4 work considerably earlier – not only to facilitate RAN2/4 to respond to potential LS(s) from RAN1, but also to start the needed RAN2/4 work on RAN1 agreement(s)
	+ This implies that additional TU allocation for RAN2/4 may be needed.

|  |
| --- |
| **Proposed way forward (after the initial round)**: On sending LS to RAN2/4 in the early phase of Rel.17 NR FeMIMO WI:* From RAN1 side, most companies opined that RAN1 send an LS to RAN2/4 only when it is necessary to further/complete the work in RAN1. Whether this is the case is to be (fully) decided by RAN1 itself
	+ Further discuss if additional measures in RAN1 can be employed
* From RAN2/4 side, whether *or how* to respond to the LS(s) from RAN1 on this matter is to be (fully) decided by RAN2/4 themselves
* Further discuss and decide in RAN#91 whether to start RAN2/4 work considerably earlier, with the possibility to increase TU allocation in RAN2/4 for Rel.17 NR\_FeMIMO WI
 |

# References

1. RP-202300 On workflow for further enhancements on MIMO for NR Samsung
2. RP-202024 Revised WID: Further enhancements on MIMO for NR Samsung