## TU_overview_after_RAN_92-e
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 92 Jun.21 | 106 | 115 | 113 | 100 | 100 | 93 Sep.21 | 106bis | 107 | 116 | 114 | 101 | 101 | 94 Dec.21 | 107bis | 116bis | 114bis | 101bis | 101bis | 108 | 117 | 115 | 102 | 102 | 95 Mar.22
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-211586 | Samsung | Mar 22 | 19.5 | REL-17 |  | 4 | 0.5 |  | 0.25 | 1 |  | 4 | 4 | 0.5 |  | 0.25 | 1 |  |  | 0.5 |  | 0.25 | 1 |  | 1 |  | 0.25 | 1
R4 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-211586 | Samsung | Sept 22 | 0.75 | REL-17 | [18 empty] | 0.25 |  |  |  |  | 0.5
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Jun 21 | 20 | REL-17 |  | 2 | 0.5 |  | 2 | 1 |  | 2 | 2 | 0.5 |  | 2 | 1 |  |  | 0.5 |  | 2 | 1 |  | 0.5 |  | 2 | 1
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Sep.21 | 0.5 | REL-17 | [23 empty] | 0.5
R1 | NR | NR_pos_enh-Core | WI | Core Part: NR positioning enhancements | RP-210903 | CATT | Mar 22 | 21.5 | REL-17 |  | 2 | 2 | 1 |  | 1 |  | 2 | 2 | 2 | 0.5 |  | 1 |  |  | 2 | 1 |  | 1 |  | 2 | 1 |  | 1
R1 | NR | NR_pos_enh-Perf | WI | Perf Part: NR positioning enhancements | RP-210903 | CATT | Sept 22 | 0 | REL-17
R1 | NR | NR_redcap-Core | WI | Core Part: support of reduced capability NR devices | RP-211574 | Ericsson | Mar 22 | 18 | REL-17 |  | 2 | 1 | 0.5 | 0.5 | 1 |  | 2 | 2 | 1 | 0.5 | 0.5 | 1 |  |  | 1 | 0.5 | 0.5 | 1 |  | 1 | 0.5 | 0.5 | 1
R1 | NR | NR_redcap-Perf | WI | Perf Part: support of reduced capability NR devices | RP-211574 | Ericsson | Sept 22 | 0.75 | REL-17 | [18 empty] | 0.25 |  |  |  |  | 0.5
R1 | NR | NR_cov_enh-Core | WI | Core Part: NR coverage enhancements | RP-211566 | China Telecom | Mar 22 | 10 | REL-17 |  | 2 | 0.5 |  | 0.5 |  |  | 2 | 2 | 0.5 |  | 0.5 |  |  |  | 0.5 |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_cov_enh-Perf | WI | NR coverage enhancements | RP-211566 | China Telecom | Sept 22 | 0.75 | REL-17 | [18 empty] | 0.25 |  |  |  |  | 0.5
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-211340 | Huawei, Ericsson | Mar 22 | 13.5 | REL-17 |  | 1 | 1 | 0.5 | 0.5 | 0.5 |  | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 |  |  | 1 | 0.5 | 0.5 | 0.5 |  | 1 | 1 | 0.5 | 0.5
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf part: Additional enhancements for NB-IoT and LTE-MTC | RP-211340 | Huawei, Ericsson | Sept 22 | 0.75 | REL-17 | [18 empty] | 0.25 |  |  |  |  | 0.5
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-202846 | LG Electronics | Mar 22 | 20.5 | REL-17 |  | 2 | 1.5 |  | 1 | 1 |  | 2 | 2 | 1.5 |  | 1 | 1 |  |  | 1.5 |  | 1 | 1 |  | 2 |  | 1 | 1
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-202846 | LG Electronics | Sept 22 | 0.25 | REL-17 | [23 empty] | 0.25
R1 | NR | FS_NR_XR_eval | SI | Study on XR (Extended Reality) evaluations for NR | RP-201145 | Qualcomm | Dec 21 | 3 | REL-17 |  | 1 | [5 empty] | 1 | 1
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-202689 | MediaTek | Dec 21 | 0 | REL-17
R1 | LTE | LTE_NBIOT_eMTC_NTN | WI | NB-IoT/eMTC support for Non-Terrestrial Networks | RP‑211601 | MediaTek, Eutelsat, ZTE | Mar 22 | 5.5 | REL-17 |  | 1 | 1 |  |  |  |  | 1 | 1 | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-211345 | Ericsson | Mar 22 | 3 | REL-17 |  | 1 | [5 empty] | 1 | 1
R4 | NR | NR_DSS-Perf | WI | Perf part: NR Dynamic spectrum sharing (DSS) | RP-211345 | Ericsson | Sept 22 | 0 | REL-17
R1 | LTE | LTE_terr_bcast_bands-Core | WI | Revised WID for New bands and bandwidth allocation for 5G terrestrial broadcast (Part 1) | RP-211144 | EBU | Mar 22 | 1.5 | REL-17 |  | 0.5 | [5 empty] | 0.5 | 0.5
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 6 | REL-17 |  | 2 | [5 empty] | 2 | 2
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-210854 | Nokia | Mar 22 | 14 | REL-17 |  | 2 | 1 | 0.5 |  | 0.5 |  | 2 | 2 | 1 | 0.5 |  | 0.5 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5
R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-210854 | Nokia | Sept 22 | 0 | REL-17 | [12 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-211557 | Thales | Mar 22 | 21.5 | REL-17 |  | 1 | 1.5 | 1 | 2 | 0.5 |  | 1 | 1 | 1.5 | 0.5 | 2 | 0.5 |  |  | 1.5 | 0.5 | 2 | 0.5 |  | 2 |  | 2 | 0.5
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-211557 | Thales | Sept 22 | 0.75 | REL-17 | [18 empty] | 0.25 |  |  |  |  | 0.5
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-210938 | MediaTek | Mar 22 | 9 | REL-17 |  | 1 | 1 |  |  | 0.5 |  | 1 | 1 | 1 |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  | 1 |  |  | 0.5
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-210938 | MediaTek | Sept 22 | 0.25 | REL-17 | [23 empty] | 0.25
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-211548 | Qualcomm | Mar.22 | 19 | REL-17 |  | 1 | 1 | 1 | 1 | 0.5 |  | 1 | 1 | 1 | 2 | 1 | 0.5 |  |  | 1 | 1 | 1 | 0.5 |  | 1 | 2 | 1 | 0.5
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-211548 | Qualcomm | Sept 22 | 0.75 | REL-17 | [22 empty] | 0.5 | 0.25
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-201038 | Huawei | Mar.22 | 14.5 | REL-17 |  | 1 | 2 | 1 |  |  |  | 1 | 1 | 2 | 1 |  |  |  |  | 1.5 | 1 |  |  |  | 2 | 1
R4 | NR | NR_MBS_Perf | WI | Perf. part: NR multicast and broadcast services | RP-201038 | Huawei | Sept 22 | 0 | REL-17
R2 | NR | NR_SL_relay | WI | NR Sidelink Relay | RP-211050 | OPPO | Mar.22 | 11.5 | REL-17 |  |  | 2 |  |  | 0.5 |  |  |  | 2 | 0.5 |  | 0.5 |  |  | 2 | 0.5 |  | 0.5 |  | 2 | 0.5 |  | 0.5
R2 | NR | NR_Slice | WI | Enhancement of RAN Slicing for NR WID | RP-211289 | CMCC | Mar.22 | 3 | REL-17 |  |  | 0.5 | [6 empty] | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-211290 | CMCC | Jun.21 | 0 | REL-17
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Mar.22 | 8 | REL-17 |  |  | 1 | 0.5 |  | 0.5 |  |  |  | 1 | 0.5 |  | 0.5 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Dec.21 | 0 | REL-17
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-201305 | ZTE | Mar.22 | 10 | REL-17 |  |  | 1.5 | [6 empty] | 1.5 | 1 |  | 0.5 |  |  | 1.5 | 1 |  | 0.5 |  | 1 | 1 |  | 0.5
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-201305 | ZTE | Dec.21 | 0 | REL-17
R2 | NR, LTE | LTE_NR_MUSIM | WI | Support for Multi-SIM devices in Rel-17 | RP-211561 | vivo | Jun 21 | 3 | REL-17 |  |  | 1 | [6 empty] | 1 | [5 empty] | 1
R2 | NR | NR_UDC-Core | WI | NR UDC | RP-211203 | CATT | Jun 21
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Jun 21 | 0 | REL-16
R4 | NR | LTE_NR_DC_CA_enh-Perf | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Jun 21 | 0 | REL-16
R2 | NR |  | WI | NR Uplink Data Compression (UDC) | RP-210909 | CATT | Mar 22 | 0.5 | REL-17 | [15 empty] | 0.5
R2 | NR |  |  | R1 Misc items (DSS etc) |  |  |  | 2 | REL-17 |  |  | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R2 | NR, LTE |  |  | R17 Other (R4 items etc) |  |  |  | 5.5 | REL-17 |  |  | 1 | [6 empty] | 1.5 | [5 empty] | 1.5 |  |  |  |  | 1.5
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-201281 | CMCC | Mar 22 | 10 | REL-17 |  |  | 1 | 2 | [5 empty] | 1 | 2 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-211409 | China Unicom | Sep 21 | 1 | REL-17 |  |  |  | 1
R3 | NR | FS_NR_ENDC_data_collect | SI | Further Enhancments to Data Collection SI | RP-201620 | CMCC | Mar 22 | 2.5 | REL-17 |  |  |  | 0.5 | [12 empty] | 1 |  |  |  |  | 1
R3 | NR | NR_QoE | WI | NR QoE management and optimizations for diverse services | RP-211406 | China Unicom | Mar 22 | 6 | REL-17 |  |  | 0.5 | 1 | [5 empty] | 0.5 | 1 |  |  |  |  | 0.5 | 1 |  |  |  | 0.5 | 1
R3 | NR | NG_RAN_PRN_enh | WI | NR Private Networks Enhancement WI | RP-202363 | China Telecom | Mar 22 | 3.5 | REL-17 |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_FR2_enhTestMethods | SI | Study on enhanced test methods for FR2 in NR | RP-211600 | Apple，CAICT | Mar 22 | 2 | REL-17 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_NR_eff_BW_util | SI | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | RP-211468 | Ericsson | Dec 21 | 1 | REL-17 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | NR | FS_NR_PC2_UE_FDD | SI | Study on high power UE (power class 2) for one NR FDD band | RP-202870 | China Unicom | Sep 21 | 0.5 | REL-17 |  |  |  |  | 0.5
R4 | NR | FS_NR_600MHz_ext | SI | Study on extended 600MHz NR band | RP-202924 | Spark NZ Ltd | Sep 21 | 1 | REL-17 |  |  |  |  | 1
R4 | NR | NR_MIMO_OTA-Core | WI | MIMO OTA requirements for NR UEs | RP-201800 | CAICT | Mar 22 | 2 | REL-17 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_MIMO_OTA-Perf | WI | MIMO OTA requirements for NR UEs | RP-201800 | CAICT | Sep 22 | 2 | REL-17 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_demod_enh2-Perf | WI | Further enhancement on NR demodulation performance | RP-211135 | China Telecom | Mar 22 | 5.5 | REL-17 | [5 empty] | 1.5 | [6 empty] | 1.5 | [5 empty] | 1.5 |  |  |  |  | 1
R4 | NR | NR_DL1024QAM_FR1-Core | WI | Introduction of DL 1024QAM for NR FR1 | RP-202886 | Ericsson | Sep 21 | 0.25 | REL-17 |  |  |  |  | 0.25
R4 | NR | NR_DL1024QAM_FR1-Perf | WI | Introduction of DL 1024QAM for NR FR1 | RP-202886 | Ericsson | Mar 22 | 1.5 | REL-17 | [11 empty] | 0.25 | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R4 | NR | NR_RRM_enh2-Core | WI | Further RRM enhancement for NR and MR-DC | RP-202874 | Apple | Mar 22 | 5.5 | REL-17 | [5 empty] | 1.5 | [6 empty] | 1.5 | [5 empty] | 1.5 |  |  |  |  | 1
R4 | NR | NR_RRM_enh2-Perf | WI | Further RRM enhancement for NR and MR-DC | RP-202874 | Apple | Sep 22 | 0 | REL-17
R4 | NR | NR_HST_FR1_enh-Core | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC | Mar 22 | 2 | REL-17 | [5 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_HST_FR1_enh-Perf | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC | Sep 22 | 2 | REL-17 | [5 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_RF_FR2_req_enh2-Core | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-211538 | Nokia | Mar 22 | 12 | REL-17 |  |  |  |  | 2 | 1 | [5 empty] | 2 | 1 |  |  |  |  | 2 | 1 |  |  |  | 2 | 1
R4 | NR | NR_RF_FR2_req_enh2-Perf | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-211538 | Nokia | Jun 22 | 0 | REL-17
R4 | NR | NR_HST_FR2-Core | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung | Mar 22 | 4.75 | REL-17 |  |  |  |  | 0.25 | 1 | [5 empty] | 0.25 | 1 |  |  |  |  | 0.25 | 1 |  |  |  | 0.25 | 0.75
R4 | NR | NR_HST_FR2-Perf | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung | Sep 22 | 4.75 | REL-17 | [5 empty] | 0.5 |  |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  |  | 1 |  | 0.5 |  |  | 0.75
R4 | NR | NR_MG_enh-Core | WI | NR and MR-DC measurement gap enhancements | RP-211591 | MediaTek | Mar 22 | 5.5 | REL-17 | [5 empty] | 1 |  |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  |  | 1 |  | 0.5 |  |  | 1
R4 | NR | NR_MG_enh-Perf | WI | NR and MR-DC measurement gap enhancements | RP-211591 | MediaTek | Sep 22 | 0 | REL-17
R4 | NR | NR_RF_FR1_enh-Core | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-210899 | Huawei | Mar 22 | 9.5 | REL-17 |  |  |  |  | 1.5 | 0.5 | [5 empty] | 1.5 | 1 |  |  |  |  | 1.5 | 1 |  |  |  | 1.5 | 1
R4 | NR | NR_RF_FR1_enh-Perf | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-210899 | Huawei | Sep 22 | 0 | REL-17
R4 | NR | NR_repeaters-Core | WI | NR Repeaters | RP-210818 | Qualcomm, Commscope | Mar 22 | 4 | REL-17 |  |  |  |  | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | NR | NR_BCS4-Core | WI | Core part: Introduction of bandwidth combination set 4 (BCS4) for NR | RP-202832 | Ericsson | Mar 22 | 4 | REL-17 |  |  |  |  | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | NR | NR_FR1_TRP_TRS-Core | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-211158 | vivo, OPPO, CMCC | Mar 22 | 2 | REL-17 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_FR1_TRP_TRS-Perf | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-211158 | vivo, OPPO, CMCC | Sep 22 | 1.5 | REL-17 | [11 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_NR_Opt_pi2BPSK | SI | New study on optimizations of pi/2 BPSK uplink power in NR | RP-210910 | Qualcomm | Mar 22 | 2 | REL-17 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | TBD-Core | WI | New WI: UE RF requirements for Transparent Tx Diversity (TxD) for NR | RP-211597 | Qualcomm, Huawei | Mar 22 | 1.9 |  |  |  | 0.1 |  | 0.5 |  |  |  |  | 0.1 |  | 0.5 |  |  |  | 0.1 |  | 0.25 |  |  | 0.1 |  | 0.25
R4 | NR | TBD-Perf | WI | New WI: UE RF requirements for Transparent Tx Diversity (TxD) for NR | RP-211597 | Qualcomm, Huawei | Mar 22 | 0.1 | [23 empty] | 0.1
R4 | NR | TBD-Core | WI | Introduction of operation in full unlicensed band 5925-7125MHz | RP-211602 | Apple | Mar 22 | 4 | REL-17 |  |  |  |  | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | LTE | TBD | WI | New WID: New bands and bandwidth allocation for 5G terrestrial broadcast (Part 2) | RP-211145 | EBU | Mar 23 | 0
R4 | LTE | [HPUE_B12_B5_B13_Bn5_Bn13_Bn71_FWVM]-Core |  | High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, Band 13, Band n5, Band n13, and Band n71 | RP-211571 | Nokia | Mar 22 | 1 | REL-17 |  |  |  |  | 0.25 | [6 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | LTE | [HPUE_B12_B5_B13_Bn5_Bn13_Bn71_FWVM]-Perf |  | High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, Band 13, Band n5, Band n13, and Band n71 | RP-211571 | Nokia | Mar 22 | 0 | REL-17
R4 | NR | R17 NR Basket Wis |  | RP-202187 Rel-17 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) Ericsson RP-210495 Rel-17 NR Inter-band CA/DC for 2 bands DL with x bands UL (x=1,2) ZTE RP-202720 Rel-17 NR inter-band CA for 3 bands DL with 1 band UL CATT RP-210497 Rel-17 NR inter-band CA/DC for 3 bands DL with 2 bands UL ZTE RP-202189 Rel-17 NR inter-band CA for 4 bands DL with 1 band UL Ericsson RP-210802 Rel-17 NR inter-band CA/DC for DL 4 bands and 2UL bands Samsung RP-210560 Rel-17 NR inter-band CA for 5 bands DL with x bands UL (x=1, 2) Huawei RP-210204 Rel-17 DC of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL) CHTTL RP-210559 Rel-17 DC of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) Huawei RP-202188 Rel-17 DC of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) Ericsson RP-210766 Rel-17 DC of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) Nokia RP-210300 Dual connectivity (DC) of 5 bands LTE inter-band CA (5DL/1L) and 1 NR band (1DL/1UL) Samsung RP-202542 Dual Connectivity (DC) of x bands (x=2,3,4) LTE inter-band CA (xDL/1UL) and 1 NR FR1 band (1DL/1UL) and 1 NR FR2 band (1DL/1UL) Samsung RP-202292 Rel-17 DC of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)inter-band CA (2DL/1UL) LG RP-210344 Rel-17 DC of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL) ZTE RP-202194 Rel-17 DC of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL) ZTE RP-210563 Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) Huawei RP-210773 Study on band combination handling in RAN4 ZTE RP-202607 Introduction of channel bandwidths 35MHz and 45MHz for NR Huawei RP-210917 Rel-17 Adding CH BW support to existing NR bands Ericsson RP-210891 Support of full bandwidths Huawei RP-210890 Simultaneous Rx/Tx band combinations Huawei RP-210588 Band combinations on co-current operation between Uu frequency bands and V2X bands CATT RP-210557 Additional NR bands for UL-MIMO power class 3 (PC3) in Rel-17 Huawei RP-210478 Downlink interruption for band combinations to conduct dynamic Tx Switching China Telecom, CATT RP-201584 SAR schemes for UE PC2 for NR inter-band CA and SUL configs with 2 bands, China Telecom RP-210476 High power UE (power class 2) for NR inter-band Carrier Aggregation with 2 bands downlink and 2 bands uplink China Telecom RP-210327 Rel-17 High power UE (PC2) for EN-DC with 1 LTE band + 1 NR TDD band China Unicom RP-210543 Power Class 2 UE for NR inter-band CA and SUL configurations with x (x>2) bands DL and y (y=1, 2) bands UL Huawei, China Unicom RP-210816 PC2 for EN-DC with multiple DL bands Ericsson RP-210555 High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1 Huawei | RP-202187 RP-210495 RP-202720 RP-210497 RP-202189 RP-210802 RP-210560 RP-210204 RP-210559 RP-202188 RP-210766 RP-210300 RP-202542 RP-202292 RP-210344 RP-202194 RP-210563 RP-210773 RP-202607 RP-210917 RP-210891 RP-210890 RP-210588 RP-210557 RP-210478 RP-201584 RP-210476 RP-210327 RP-210543 RP-210816 RP-210555 |  |  | 12 | REL-17 |  |  |  |  | 3 | [6 empty] | 3 | [5 empty] | 3 |  |  |  |  | 3
R4 | NR | R17 NR spectrum related WI/SI |  | RP-202844 Introduction of 6GHz NR licensed bands Huawei, Ericsson, Nokia, ZTE RP-210762 Introduction of lower 6GHz NR unlicensed operation for Europe Nokia RP-210878 Introduction of 900 MHz spectrum to 5G NR applicable for Rail Mobile Radio (RMR) Union Inter. Chemins de Fer RP-210879 Introduction of 1900 MHz spectrum to 5G NR applicable for Rail Mobile Radio (RMR) Union Inter. Chemins de Fer RP-210827 introduction of NR 47 GHz band Nokia RP-202829 Introduction of n67 Ericsson RP-210707 Introduction of NR band n85 Ericsson RP-202912 High-power UE (PC1.5) operation in NR bands n77 and n78 Qualcomm RP-210843 High power UE (power class 1.5) for NR band n79 CMCC RP-210844 High power UE (power class 2) for NR band n34 CMCC RP-210845 High power UE (power class 2) for NR band n39 CMCC RP-210875 Introduction of FR2 FWA UE with maximum TRP of 23dBm for band n259 Qualcomm | RP-202844 RP-210762 RP-210878 RP-210879 RP-210827 RP-202829 RP-210707 RP-202912 RP-210843 RP-210844 RP-210845 RP-210875 |  |  | 8 | REL-17 |  |  |  |  | 2 | [6 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R4 | LTE | R17 LTE basket WIs |  | RP-210227 Rel-17 LTE inter-band CA for 2 bands DL with 1 band UL Qualcomm RP-210540 Rel-17 LTE inter-band CA for 3 bands DL with 1 band UL Huawei RP-210542 Rel-17 LTE inter-band CA for 2 bands DL with 2 band UL Huawei RP-202212 Rel-17 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL Nokia RP-202289 Rel-17 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 bands UL LG | RP-210227 RP-210540 RP-210542 RP-202212 RP-202289 |  |  | 4 | REL-17 |  |  |  |  | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | LTE | R17 LTE spectrum related WI/SI |  | RP-201646 Additional LTE bands for UE cat. M1/M2/NB1/NB2 in Rel-17 Ericsson RP-201356 Modification of LTE Band 24 specifications to comply with updated regulatory emission limits Ligado Networks | RP-201646 RP-201356 |  |  | 2 | REL-17 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | LTE,NR | R17 LTE/NR spectrum Perf part |  | All potential performance part for WIs in R17 NR Basket Wis, R17 NR spectrum related WI/SI, R17 LTE basket Wis,R17 LTE/NR spectrum Perf part |  |  |  | 1 | REL-17 | [5 empty] | 0.25 | [6 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | R17 LS activities | [5 empty] | 0 | REL-17
R4 | NR | R16 NR Maintenance and TEI | [5 empty] | 11 | REL-16 |  |  |  |  | 1.5 | 2 | [5 empty] | 1.5 | 1 |  |  |  |  | 1.5 | 1 |  |  |  | 1.5 | 1
R4 | NR | R15 NR Maintenance | [5 empty] | 1.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.25 | 0.25
R4 | LTE | LTE Maintenance | [5 empty] | 3 | [5 empty] | 0.5 | 0.25 | [5 empty] | 0.5 | 0.25 |  |  |  |  | 0.5 | 0.25 |  |  |  | 0.5 | 0.25
R5 | NR | FS_UE_5GNR_App_Data_Perf | SI | Study on 5G NR UE Application Layer Data Throughput Performance | RP-210710 | Qualcomm, AT&T |  | 0.25 | REL-17 | [5 empty] | 0.25
| NR |  |  | allocated above | [5 empty] | 0 | 26.5 | 24.1 | 11 | 29 | 19.75 | 0 | 26.5 | 26.5 | 25.1 | 11.5 | 27.75 | 20 | 0 | 0 | 25.1 | 11 | 26.75 | 21 | 0 | 24.1 | 12 | 27.35 | 22 | 0
| NR |  |  | Legacy | [6 empty] | 4 | 14.5 |  |  |  |  | 4 | 4 | 13 | [5 empty] | 0 |  |  |  |  | 13
| NR |  |  | TEI and other not planned issues | [6 empty] | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 0.5 |  |  |  |  | 2 | 0.5 |  |  |  | 2
| NR |  |  | Reserve | [7 empty] | 0.5 | [6 empty] | 1.5 | [5 empty] | 1.5 | 0.5 |  |  |  | 1.5 | 0.5
| NR |  |  | total used capacity | [5 empty] | 0 | 31.5 | 40.1 | 12 | 29 | 19.75 | 0 | 31.5 | 31.5 | 40.6 | 12 | 27.75 | 20 | 0 | 0 | 28.6 | 12 | 26.75 | 21 | 0 | 40.6 | 12.5 | 27.35 | 22 | 0
| NR |  |  | available capacity | [6 empty] | 31 | 40 | 12 | 24.5 | 20.5 |  | 31 | 31 | 40 | 12 | 24.5 | 20.5 |  |  | 28 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5
| NR |  |  | remaining/exceeded capacity | [6 empty] | -0.5 | -0.1 | 0 | -4.5 | 0.75 |  | -0.5 | -0.5 | -0.6 | 0 | -3.25 | 0.5 |  | 0 | -0.6 | 0 | -2.25 | -0.5 | 0 | -0.6 | -0.5 | -2.85 | -1.5
| LTE |  |  | allocated above
| LTE |  |  | Legacy
| LTE |  |  | TEI and other not planned issues
| LTE |  |  | Reserve
| LTE |  |  | total used capcaity
| LTE |  |  | available capacity
| LTE |  |  | remaining/exceeded capacity
| UTRA |  |  | allocated above
| UTRAN |  |  | Legacy
| UTRAN |  |  | TEI and other not planned issues
| UTRAN |  |  | Reserve
| UTRAN |  |  | total used capacity
| UTRAN |  |  | available capacity
| UTRAN |  |  | remaining/exceeded capacity
| GERAN |  |  | allocated above
| GERAN |  |  | Legacy
| GERAN |  |  | TEI and other not planned issues
| GERAN |  |  | Reserve
| GERAN |  |  | total used capacity
| GERAN |  |  | available capacity
| GERAN |  |  | remaining/exceeded capacity
R3 |  |  |  | RAN3 overall Status | [8 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  |  |  |  | -0.5