## Cover sheet
RAN5 meeting #92e | [10 empty] | R5-214734
Electronic Meeting, 16th Aug 2021 – 27th Aug 2021
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance Test Aspects - Rel-16 Optimisations on UE radio capability signalling – NR/E-UTRA
Work item code: | RACS-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 62% (+62%) | 3 (+3) | 12 (+12)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 67.2% (+67.2%) | 3 (+3) | 8 (+8)
FR1 |  | 67.5% (+67.5%) | 4 (+4) | 8 (+8)
FR2 |  | 66.9% (+66.9%) | 3 (+3) | 8 (+8)
NSA Option 3 (EN-DC) |  | 100% (+100%)
FR1 |  | 100% (+100%)
FR2 |  | 100% (+100%)
LTE |  | 42.4% (+42.4%) | 0 | 4 (+4)
FDD |  | 42.4% (+42.4%) | 0 | 4 (+4)
TDD |  | 42.4% (+42.4%) | 0 | 4 (+4)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC) | [5 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2 |  |  | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 100% (+100%) | [9 empty] | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 16% (+16%) | 0 | 4 (+4) | [13 empty] | 16% (+16%) | 0 | 4 (+4) | 16% (+16%) | 0 | 4 (+4)
Applicability Protocol test cases | 36.523-2 | 25% (+25%) | [15 empty] | 25% (+25%) |  |  | 25% (+25%)
Test suites (TTCN) | 36.523-3 | 0% | [15 empty] | 0% |  |  | 0%
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
UE specific test functions | 38.509 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 62.9% (+62.9%) | 3 (+3) | 8 (+8) | 55.6% (+55.6%) | 4 (+4) | 8 (+8) | 54.4% (+54.4%) | 3 (+3) | 8 (+8) |  | 100% (+100%) |  |  | 100% (+100%)
Applicability Protocol test cases | 38.523-2 | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%)
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-201153 | Optimizations on UE radio capability signalling - NR/E-UTRA Aspects
(2)RP-210714 | Revised WID - Optimizations on UE radio capability signalling - NR/E-UTRA Aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Optimisations on UE radio capability signalling - NR/E-UTRA Aspects | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | RACS-UEConTest
WP Scope: |  | <WP Scope description> | [14 empty] | vs Area
WP Resp: |  | Taran Dhuppad |  |  | tdhuppad@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC) |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 | FR2 | FDD | TDD
[14 empty] | Overall |  | 67.5% (+67.5%) | 66.9% (+66.9%) | 100% (+100%) | 100% (+100%) | 42.4% (+42.4%) | 42.4% (+42.4%)
[14 empty] | Number of WP items |  | 14 (+14) | 14 (+14) | 2 (+2) | 2 (+2) | 9 (+9) | 9 (+9)
[14 empty] | Sum weight of WP items |  | 15.8 (+15.8) | 15.8 (+15.8) | 3 (+3) | 3 (+3) | 9.4 (+9.4) | 9.4 (+9.4)
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
32 |  | 36.508 | 4.6, 4.7 | Introduction of General and Signaling Test Environment for Rel-16 RACS over EUTRA | ASN.1 updates RRC message updates from 36.331 NAS message updates from 24.301 | Qualcomm | RAN5#92 (Aug-21) | R5-213122 R5-213124 R5-216280 |  | 2 | 100% (+100%) |  | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100% | 100% | 100%
TS 36.509: UE specific testing functions
13 |  | 36.509 | 5.10, 6.19 | Special Test Function to test RRC Segmentation | Introduction of Rel-16 RACS Special conformance testing functions for User Equipment (UE) | Qualcomm | RAN5#94 (Feb-22) | draft_R5-211550 Revised WID R5-211364 to add 36.509 R5-212796 |  | 1 | 80% (+80%) |  |  | 80% (+80%) | [5 empty] | 80% | 80%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
RRC
|  | 36.523-1 | 8.5.4 | UE Capability Transfer | Exisiting sub-clause header |  |  |  |  | 0
41 |  | 36.523-1 | 8.5.4.1 | UE Capability Transfer/Success | TS 36.331 cl 5.6.22 |  | RAN5#94 (Feb-22) |  | Update of existing TC to allow for UE capability to be > 8188B. SS sends UECapabilityEnquiry message with rrc-SegAllowed-r16 set to enabled. | 1 | 0% |  |  | 0% | [5 empty] | 0% | 0%
45 |  | 36.523-1 | 8.5.5 | RACS / UL Message Segment transfer | New sub-clause header |  |  |  |  | 0
42 | Y | 36.523-1 | 8.5.5.1 | RACS / UL Message Segment transfer / UECapabilityInformation / Success | TS 36.331 cl 5.6.22, cl 5.6.3 | Qualcomm | RAN5#94 (Feb-22) | R5-216281 |  | 1 | 80% (+80%) |  |  | 80% (+80%) | [5 empty] | 80% | 80%
NAS
44 |  | 36.523-1 | 9.2.5 | RACS | New sub-clause header |  |  |  |  | 0
39 | Y | 36.523-1 | 9.2.5.1 | RACS / Network assigned UE radio capability ID | TS 24.301, cl 5.3.20 |  | RAN5#94 (Feb-22) |  |  | 1 | 0% |  |  | 0% | [5 empty] | 0% | 0%
40 | Y | 36.523-1 | 9.2.5.2 | RACS / USIM change / Handling of URCID | TS 24.301, cl 5.3.20 |  | RAN5#94 (Feb-22) |  |  | 1 | 0% |  |  | 0% | [5 empty] | 0% | 0%
43 | Y | 36.523-1 | 9.2.5.3 | RACS /Handling of delete indication for NW assigned UE radio capability ID | TS 24.301, cl 5.3.20 |  | RAN5#94 (Feb-22) |  |  | 1 | 0% |  |  | 0% | [5 empty] | 0% | 0%
TS 36.523-2: Applicability for Protocol test cases
22 |  | 36.523-2 | 4 | Introduce PICS parameters and add test case applicability statements for the new test cases introduced in 36.523-1 for Rel-16 RACS | NAS Support of RACS/URCID feature in LTE UE support of RRC UL segmentation | Qualcomm | RAN5#94 (Feb-22) | R5-215140 |  | 0.4 | 25% (+25%) |  |  | 25% (+25%) | [5 empty] | 25% | 25%
TS 36.523-3: Protocol test suites (TTCN)
36 |  | 36.523-3 | TBD | Introduction of General and Signaling Test Environment for RACS in LTE |  |  | RAN5#94 (Feb-22) |  |  | 1 | 0% |  |  | 0% | [5 empty] | 0% | 0%
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and Signaling Test Environment for Rel-16 RACS | ASN.1 and other updates All RRC updates from 38.331 NAS Msg REG (PC_RACS) and RRC_IDLE Gen Preamble | Qualcomm | RAN5#92 (Aug-21) | R5-206419 R5-206420 R5-213580 |  | 3 | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100%
TS 38.508-2: Common ICS
20 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-16 RACS | NAS Support of RACS/URCID feature. UE Declaration for UL segmentation UE declaration for test function support | Qualcomm | RAN5#92 (Aug-21) | R5-206421 R5-213581 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100%
TS 38.509: UE specific testing functions
12 |  | 38.509 | 5.10, 6.10 | Special Test Function to test RRC Segmentation and possible deletion of URCID | Introduction of Rel-16 RACS Special conformance testing functions for User Equipment (UE) | Qualcomm | RAN5#92 (Aug-21) | draft_R5-211550. Revised WID R5-211364 to add 38.509 R5-213582 R5-216275 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
RRC
|  | 38.523-1 | 8.1.5.1 | UE Capability Transfer | New sub-clause header |  |  |  |  | 0
2 |  | 38.523-1 | 8.1.5.1.1 | UE Capability Transfer / Success | TS 38.331 cl 5.6.1.3, cl 5.7.7 | Tech Mahindra | RAN5#92 (Aug-21) | R5-216276 | Update of existing TC to allow for UE capability to be be > 9K. SS sends UECapabilityEnquiry message with rrc-SegAllowed-r16 set to enabled | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100%
37 |  | 38.523-1 | 8.1.5.9 | RACS / UL Message Segment transfer | New sub-clause header |  |  |  |  | 0
4 | Y | 38.523-1 | 8.1.5.9.1 | RACS / UL Message Segment transfer / UECapabilityInformation | TS 38.331 cl 5.6.1.3, cl 5.7.7 (1) with { UE in NR RRC_CONNECTED state } ensure that { when { UE receives UECapabilityEnquiry message with rrc-segAllowed-r16 enabled } then { UE successfully segments UECapabilityInformation message at RRC layer and sends UlDedicatedMessageSegment messages with rrc-MessageSegmentType set accordingly for the first and last segment and rrc-MessageSegmentContainer containing the segments of UECapabilityInformation message } } (2) with { UE in NR RRC_CONNECTED state and UE having received UECapabilityEnquiry message with rrc-segAllowed-r16 enabled and having transmitted the firstSegment of UECapabilityInformation message within the ULDedicatedMessageSegment message } ensure that { when { UE detects radio link failure on expiry of timer T310 } then { UE successfully completes RRC re-establishment procedure and discards the remaining segments of UECapabilityInformation message } } | Qualcomm | RAN5#92 (Aug-21) | R5-213583 R5-216278 |  | 1 | 95% (+95%) | 95% (+95%) |  |  |  | 100% | 90%
|  | 38.523-1 | 8.2.1.1 | UE capability transfer / Success | [5 empty] | 0
23 |  | 38.523-1 | 8.2.1.1.1 | UE capability transfer / Success / EN-DC | TS 36.331 cl 5.6.22 | Tech Mahindra | RAN5#92 (Aug-21) | R5-216277 | Update of existing TC to allow for UE capability to be be > 8188B i.e SS sends UECapabilityEnquiry message with rrc-SegAllowed-r16 set to enabled. | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  |  | 100% | 100%
NAS
38 |  | 38.523-1 | 9.1.9 | RACS | New sub-clause header |  |  |  |  | 0
5 | Y | 38.523-1 | 9.1.9.1 | RACS / Network assigned UE radio capability ID | TS24.501, cl 4.16 TS24.501, cl 5.4.4, 5.5.1.2, 5.5.1.3 (1) with { UE is switched on and the UE has an applicable UE radio capability ID for the current UE radio configuration for the selected network } ensure that { when { the UE performs an initial registration procedure } then { the UE includes the UE radio capability ID in the REGISTRATION REQUEST message } } (2) with { UE in state 5GMM-REGISTERED and 5GMM-IDLE mode and having assigned a new UE Radio Capability ID in the Registration Accept message } ensure that { when { UE enters a new tracking area that is not in the list of tracking areas that the UE previously registered in the AMF } then { UE sends REGISTRATION REQUEST message including the new UE radio capability ID } } | Qualcomm | RAN5#91-e (May-21) | R5-213585 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100%
6 | Y | 38.523-1 | 9.1.9.2 | RACS / UE configuration update / UE radio capability ID | TS24.501, cl 4.16 TS24.501, cl 5.4.4, 5.5.1.2, 5.5.1.3 (1) with { UE in 5GMM-REGISTERED state and a UE Radio Capability ID assigned in REGISTRATION ACCEPT message } ensure that { when { UE receives CONFIGURATION UPDATE COMMAND with new UE Radio Capability ID and acknowledgement requested} then { UE sends CONFIGURATION UPDATE COMPLETE message } } (2) with { UE in state 5GMM-REGISTERED, and 5GMM-IDLE mode over 3GPP access and assigned a new UE Radio Capability ID in CONFIGURATION UPDATE COMMAND } ensure that { when { UE enters a new tracking area that is not in the list of tracking areas that the UE previously registered in the AMF } then { UE sends REGISTRATION REQUEST message including the new UE radio capability ID } } | Tech Mahindra | RAN5#90-e (Feb-21) | R5-210430 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100%
7 | Y | 38.523-1 | 9.1.9.3 | RACS / PLMN change within registration area / From NW assigned to Manufacturer assigned UE Radio Capability ID | TS24.501, cl 4.16 TS24.501, cl 5.4.4, 5.5.1.2, 5.5.1.3 | Qualcomm | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
8 | Y | 38.523-1 | 9.1.9.4 | RACS / USIM change / Handling of URCID | TS24.501, cl 4.16 TS24.501, cl 5.4.4, 5.5.1.2, 5.5.1.3 | Qualcomm | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
9 | Y | 38.523-1 | 9.1.9.5 | RACS / Handling of delete indication for NW assigned UE radio capability ID | TS24.501, cl 4.16 TS24.501, cl 5.4.4, 5.5.1.2, 5.5.1.3 (1) with { UE in 5GMM-REGISTERED state and a UE Radio Capability ID assigned in REGISTRATION ACCEPT message } ensure that { when { UE receives CONFIGURATION UPDATE COMMAND with UE radio capability ID deletion indication and indicating “registration requested” } then { UE deletes any stored Network-assigned UE radio capability IDs and then releases the existing N1 NAS signalling connection, starts a mobility registration procedure and does not include any Network-assigned UE radio capability IDs in the REGISTRATION REQUEST message } } (2) with { UE in state 5GMM-REGISTERED, and 5GMM-IDLE mode over 3GPP access and assigned a new UE Radio Capability ID, enters a new tracking area that is not in the list of tracking areas that the UE previously registered in the AMF } ensure that { when { UE receives REGISTRATRATION ACCEPT message with UE radio capability ID deletion indication } then { UE deletes the stored Network-assigned UE radio capability ID and initiate a registration procedure for mobility and periodic registration update over the existing N1 NAS signalling connection} } | Qualcomm | RAN5#91-e (May-21) | R5-213584 R5-216279 |  | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100%
46 | Y | 38.523-1 | 9.1.9.6 | RACS / Change in radio capability / NW assigned URCID | TS24.501, cl 4.16 TS24.501, cl 5.4.4, 5.5.1.2, 5.5.1.3 | Qualcomm | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
47 | Y | 38.523-1 | 9.1.9.7 | RACS / Inter-system mobility registration update / Handling of UE radio capability ID | TS24.501, cl 4.16 TS24.501, cl 5.4.4, 5.5.1.2, 5.5.1.3 TS24.301, cl 5.5.3.3.2, 5.3.20 | Qualcomm | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
19 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 |  |  | RAN5#94 (Feb-22) | R5-210513 R5-213586 |  | 0.8 | 50% (+50%) | 50% (+50%) |  |  |  | 50% | 50%
TS 38.523-3: Protocol test suites (TTCN)
11 |  | 38.523-3 | TBD | Introduction of General and Signaling Test Environment for RACS in NR |  |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.