3GPP TSG RAN Meeting #97-e						RP-221902

Electronic Meeting, September 12 - 16, 2022

3GPP TSG-CT Meeting #96	CP-221324

# Budapest, Hungary, 05th – 06th June 2022

# Title:	LS on allowing sufficient time for stage 3 work

Source:	CT

To:	SA

Cc:	RAN

Contact Person:

Name:	Lena Chaponniere

E-mail Address:	lguellec@qti.qualcomm.com

Send any reply LS to:	3GPP Liaisons Coordinator, mailto:3GPPLiaison@etsi.org

# Attachments:	None

1. Overall Description:

For the past couple of releases, a duration of 9 months between the stage 2 freeze date in SA WGs and the stage 3 freeze date in CT WGs has been strictly enforced during release schedule planning. This has in most cases worked well for the stage 2 requirements coming from SA2 and SA6, since 9 months generally allow sufficient time for CT WGs to specify the stage 3 and liaise with SA2 and SA6 for aspects which need clarification (even when multiple round-trips of LSs are required to reach a conclusion), although occasionally some SA2 or SA6 stage 2 requirements do get specified after the stage 2 freeze date.

However, there has been more frequent occurences of stage 2 requirements coming from SA3, SA4 or SA5 very late, which puts CT WGs under significant stress to try and meet the stage 3 freeze date. In several cases, the stage 2 requirements even came after the Rel-17 stage 3 freeze date of March 2022 (for instance for the EVEX WI, the 5G_ProSe WI and the eNPN WI).

CT believes that this stems from the fact that SA2 and SA6 are “stage 2-only” groups, while SA3, SA4 and SA5 produce both stage 2 and stage 3 specifications. As a result, SA2 and SA6 work toward a single deadline (the stage 2 freeze date) whereas many of the WIDs in SA3, SA4 and SA5 are approved with a target completion date set to the stage 3 freeze date. In other words, there is not enough visibility in the planning of the work into exactly when the stage 2 portion of it needs to be completed.

CT would like SA to discuss possible solutions to this issue to ensure that stage 2 requirements which will have stage 3 impacts in CT WGs are made available in a timely manner.

2. Actions:

To SA group.

ACTION: 	CT kindly asks SA to discuss possible ways to improve work management to ensure timely completion of stage 2 work which has stage 3 impacts in CT WGs

3. Date of Next CT Meetings:

3GPP TSG CT#97-e		09/2022	Online