## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: SS: System Simulator
UE: User Equipment

## Slide 3
Release 17 – baseline upgrade:
  Presented the updates to type definitions of 3G UMTS / 4G LTE / 5G / IMS / POS / MCX necessary to align with 3GPP core specifications of version Release 17 September 2022.
Test Models – 5G:
  Rel-15:
    Endorsed special handling for NR CA bands with no UL frequency (e.g. CA_n66B).
  Rel-16:
    5G V2X: endorsed updated test model & ASPs.
  Prose CRs to TS 38.508-1 & TS 38.523-3 agreed at RAN5#97 for the above.
Test models & ASPs design Progress at TTCN Workshop #59 (25th Oct’22)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – NB-IoT:
  feNB-IoT: endorsed NB-IoT ASP updates to support NPRACH preamble format 2.
Test Models – MCX:
  Discussed issues related to SSRC values for audio, video and floor/transmission control. CT1 being contacted to clarify interpretation of their core specs.
  Discussed various MCX issues related to either core specs or test specs.
  Prose CRs to TS 36.579-x agreed at RAN5#97 for the above.
Test models & ASPs design Progress at TTCN Workshop #59 (25th Oct’22)

## Slide 5: TTCN development Progress for period: Sep to Nov’22
Completed:
  NB-IoT:
    New band 103
  5GS Rel-15:
    NR/5GC single carrier
    NR/5GC NR-DC
  5GS Rel-16:
    NR UE power saving
  Type def. baseline:
    Baseline upgrade to Rel-17 Sep’22 core specs (in iwd-22wk43)
Progressed 5G:
  5GS Rel-15:
    NR/5GC NE-DC
  5GS Rel-16:
    5G non-public network
    NR IIoT
    NR SON/MDT
    5G V2X
  IMS over NR/5GC:
    IMS emergency
    IMS eCall
  POS:
    Rel-16 NR positioning
Started:
  5GS Rel-16:
    RRC DL segmentation
    MR-DC & NR CA enh.
Progressed 4G:
  NB-IoT:
    Rel-15 enhancements
  Mission Critical over LTE:
    MCVideo
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 6: TTCN verification Progress for period: 11th Aug --> 10th Nov’22
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
Inter-RAT handover from NR/5GC to EN-DC | Rel-16 | 516_HO | 1 / 1 | +1 | 
5G private network - CAG | Rel-16 | 519 | 5 / 5 | +5 | Prio1: 3/3 ; Prio2: 2/2
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 7: TTCN verification Progress for period: 11th Aug --> 10th Nov’22
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 92 / 102 | +2 | +1 under verification
NR/5GC access stratum | Rel-15 | 503 | 146 / 158 | +2 | Prio1: 89/95 ; Prio2: 57/63 +1 under verification
NR/5GC NR-DC | Rel-15 | 503 | 9 / 13 | = | Prio1: 8/11 ; Prio2: 1/2
NR/5GC NAS | Rel-15 | 504 | 74 / 76 | +4 | Prio1: 35/35 ; Prio2: 39/41 +1 under verification
NR/5GC NR CA | Rel-15 | 510 | 30 / 32 | = | Prio1: 14/15 ; Prio2: 16/17
EN-DC NR CA | Rel-15 | 512 | 9 / 17 | = | Prio1: 9/13 ; Prio2: 0/4 +1 under verification
Intra-NR SON/MDT | Rel-16 | 517_A | 30 / 31 | +3 | Prio1: 23/24 ; Prio2: 7/7 +1 under verification
Inter-RAT SON/MDT | Rel-16 | none | 3 / 4 | +1 | 
NR RACS | Rel-16 | 520 | 6 / 8 | +2 | +1 under verification
NR mobility enhancements | Rel-16 | 522 | 4 / 13 | = | Prio1: 2/27 ; Prio2: 2/6 +2 under verification
5G network slicing enhancements | Rel-16 | 523 | 4 / 5 | +1 | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 11th Aug --> 10th Nov’22
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
VoLTE (GSMA IR.92) | Rel-8 | WI-103 | 45 / 51 | = | 
SMS over IMS | Rel-8 | WI-128 | 2 / 5 | = | 
IMS emergency over LTE | Rel-9 | WI-154 | 31 / 35 | = | 
LTE positioning | Rel-9+ | WI-166 | 15 / 27 | = | 
VoWiFi (GSMA IR.51) | Rel-11 | WI-267 | 18 / 22 | = | Prio1: 5/9 ; Prio2: 13/13
VoLTE over CAT-M1 (GSMA NG.108) | Rel-13 | WI-283 | 10 / 11 | = | Left: TC J.15.5(TIR)
SMS over CAT-M1 (GSMA NG.108) | Rel-13 | WI-128M | 1 / 2 | = | Left: TC J.18.1(MO SMS)
MCPTT over LTE | Rel-14 | WI-288, RFT-153 | 37 / 51 | +1 | Prio1: 32/42 ; Prio2: 5/9
IMS eCall over LTE (34.229) | Rel-14 | WI-298 | 5 / 12 | = | 
IMS over NR/5GC | Rel-15 | 505 | 89 / 100 | +6 | Prio1: 21/21 ; Prio2: 68/79 +4 under verification
5G Positioning | Rel-15 | 506 | 9 / 10 | = | Left: TC 9.3.3.1B
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 11th Aug --> 10th Nov’22
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE/C2K Inter-RAT | Rel-8 | WI-088 | 13 / 14 | = | Left: TC 8.4.5.4(LTE to HRPD HO)
LTE/UMTS Inter-RAT | Rel-9 | WI-167 | 11 / 12 | = | Left: TC 13.1.21(emergency call)
LTE/GERAN Inter-RAT | Rel-9 | WI-168 | 3 / 4 | = | Left: TC 13.1.21(emergency call)
LTE/C2K Inter-RAT | Rel-10 | WI-180 | 1 / 2 | = | Left: TC 8.6.5.3(MDT RLF logging)
LTE/GERAN Inter-RAT | Rel-10 | WI-182/184 | 1 / 2 | = | Left: TC 8.6.5.2(MDT RLF logging)
CA intra-band contiguous | Rel-11 | WI-162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | WI-245 | 6 / 9 | = | 
eDRX | Rel-13 | WI-253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | WI-254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | WI-254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | WI-257 | 72 / 73 | +1 | Left: TCs 22.1.1.M2
LAA | Rel-13 | WI-272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | WI-295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
L2 latency reduction | Rel-14 | WI-306 | 1 / 4 | = | 
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 10: TTCN verification Progress for period: 11th Aug --> 10th Nov’22
Started:
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
MCData over LTE | Rel-14 | WI-329 | 4 / 28 | +4 | Prio1: 3/15 ; Prio2: 1/13
MCPTT enh. over LTE | Rel-15 | WI-330 | 2 / 22 | +2 | Prio1: 2/15 ; Prio2: 0/7
5G private network - SNPN | Rel-16 | 518 | 5 / 8 | +5 | Prio1: 3/4 ; Prio2: 2/4
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
IMS eCall over LTE (36.523) | Rel-14 | WI-298 | 0 / 9 |  | +1 under verification
NR RRC DL segmentation | Rel-16 | none | 0 / 1 |  | +1 under verification
NR positioning | Rel-16 | none | 0 / 29 |  | +5 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 11
2021 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | TTCN Status (as of Nov’22) / Comments
MCX: PTT, Video, Data | Rel-14 | L | Q3’20 | 106 | Q3’17-Q4’22 | 4 | 85% (@iwd-22wk37)
LTE CA band combinations | R15to16 | L | Q4’22 | n/a | Q1’19-Q4’22 | 0.1 | 46% (@iwd-22wk37)
MTC (even) further enhanced | R14to15 | L | Q4’21 | 18 | Q1’18-Q4’22 | 1 | 11% (@iwd-21wk49)
NB-IoT further enhanced | Rel-15 | L | Q3’21 | 8 | Q2’20-Q4’22 | 0.5 | 85% (@iwd-22wk37)
MCX enhancements | Rel-15 | L | Q2’22 | 58 | Q3’21-Q1’23 | 6 | 45% (@iwd-22wk37)
LTE mobility even further enhancements | Rel-16 | L | Q2’22 | 12 | Q4’20-Q4’22 | 1 | Not started
5GS: NR/5GC (option 2) | Rel-15 | N,L | Q4’22 | 449 | Q3’18-Q4’22 | 1.5 | 99% (@iwd-22wk37)
UE RACS optimisations | Rel-16 | N,L | Q1’22 | 17 | Q4’20-Q2’22 | 1 | 100% (@iwd-22wk23)
NR UE power saving | Rel-16 | N | Q4’22 | 9 | Q4’20-Q4’22 | 0.5 | 100% (@iwd-22wk37)
NR industrial IoT | Rel-16 | N,L | Q1’22 | 7 | Q4’20-Q4’22 | 1 | 80% (@iwd-22wk37)
5G V2X with NR sidelink | Rel-16 | N,L | Q2’23 | 72 | Q4’20-Q2’23 | 6 | 17% (@iwd-22wk37)
5G non-public network | Rel-16 | N | Q4’22 | >15 | Q4’20-Q4’22 | 0.8 | 90% (@iwd-22wk37)
NR mobility enhancements | Rel-16 | N | Q2’22 | 13 | Q4’20-Q1’22 | 0.5 | 100% (@iwd-22wk12)
NR SON & MDT | Rel-16 | NLWB | Q2’22 | 47 | Q1’21-Q4’22 | 1 | 91.5% (@iwd-22wk37)
NR URLLC phy layer enhancements | Rel-16 | N | Q4’22 | 10 | Q2’21-Q4’22 | 1 | 40% (@iwd-22wk12)
NW slicing enhancements | Rel-16 | N | Q4’21 | 5 | Q3’21-Q1’22 | 0.1 | 100% (@iwd-22wk12)
IMS eCall over NR | Rel-16 | N | Q1’23 | 20 | Q3’21-Q1’23 | 2 | 40% (@iwd-22wk37)
NR positioning | Rel-16 | N | Q2’23 | 29 | Q2’21-Q2’23 | 0.5 | 80% (@iwd-22wk37)
NR MIMO enhancements | Rel-16 | N | Q4’22 | 1 | Q4’20-Q1’23 | 0.5 | Not started
NR new/extended bands | R16to17 | N | Q4’22 | n/a | Q1’21-Q4’22 | 0.2 | 56% (@iwd-22wk37)
5G CA/DC band combinations | R16to17 | N,L | Q4’23 | n/a | Q1’21-Q4’23 | 0.2 | 26.5% (@iwd-22wk37)
Total: |  |  |  | 896 |  | 29.4 | person-months
TTCN workplan 2022 Status of 2021 tasks carried over
Notes: Note: TTCN of some features initially started in 2021 will only be completed in 2022 due to availability of prose late in CY2021, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2022 Tasks & Maintenance | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2022 WkLoad | TTCN Status (as of Nov’22) / Comments
5GS: NE-DC (option 4) | Rel-15 | N,L | Q1’23 | 35 | Q1’22-Q1’23 | 6 | 31% (@iwd-22wk37)
NR 2-step RACH | Rel-16 | N | Q4’22 | 8 | Q3’22-Q1’23 | 1 | 2% ; Test Model work
MR-DC & NR CA enhancements | Rel-16 | N,L | Q2’23 | 29 | Q1’22-Q2’23 | 3 | 10% (@iwd-22wk37)
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q2’23 | 22 | Q1’22-Q3’23 | 3 | Not started ; no prose
NB-IoT new band 103 | Rel-17 | L | Q4’22 | n/a | Q3’22-Q4’22 | 0.1 | 100% (@iwd-22wk37)
NW slicing enhancements - Phase2 | Rel-17 | N | Q2’23 | 13 | Q4’22-Q2’23 | 1 | Not started
Reduced capability NR UE (RedCap) | Rel-17 | N | Q2’23 | >8 | Q4’22-Q4’23 | 1 | 2% ; Test Model work
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q2’23 | >11 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR multi/broadcast services (MBS) | Rel-17 | N | Q2’23 | 44 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q4’23 | 0.5 | Not started
NR UE power saving enhancements | Rel-17 | N | Q3’23 | 5 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR RAN slicing enhancements | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR sidelink enhancements | Rel-17 | N | Q3’23 | 2 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 0.5 | Not started ; no prose
TEIx_Test (new TC coverage) | Rel-8+ | All | n/a | 20 | Q1’22-Q4’22 | 2 | 2022 total after RAN5#97: 4 new tests
TTCN maintenance & deliveries |  |  |  |  | Q1’22-Q4’22 | 45 | 
Release & configuration management |  |  |  |  | Q1’22-Q4’22 | 6 | 
Total: |  |  |  | >227 |  | 71.6 | person-months
TTCN workplan 2022 Status of new 2022 tasks and maintenance tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13
2022 workload is estimated at 101 person-months, see previous slides.
PCG#47/OP#46 approved the 3GPP funding of 58 person-months for 2022 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2022.
Current commitments for 2022 are as follows:
3GPP companies / 3GPP MRPs committed to provide 17 person-months as voluntary contributions for 2022 TTCN development.
Total resources of 101 person-months  no estimated funding gap.
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#47/OP#46 approved (decision OP46/08)
CTIA/PTCRB | 12 | 5GS, MCX
GCF | 12 | 5GS, MCX
Qualcomm | 2 | RACS, NPN, IMSoNR eCall
Total: | 84 | person-months
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 5GS, V2X, NB-IoT, LCR TDD
Anritsu | 1 | 5GS
Keysight | 1 | 5GS
Rohde&Schwarz | 1 | 5GS
Total: | 17 | person-months
TTCN funding 2022 Status

## Slide 14: Preparing for 2023 TTCN Work Overview
Course of action to secure funding for TF160 work in 2023:
  Prior to RAN5#96-e meeting (August), a request to identify the potential TTCN development tasks in 2023 has been made to 3GPP members.
  At RAN5#96-e, a provisional ‘TTCN Tasks List’ has been endorsed by RAN5.
  The TTCN Tasks List has been presented at RAN#97-e (Sep) and endorsed by TSG RAN.
  The RAN Chair has presented the List to 3GPP PCG/OP (end of Sep) in order to support TF160 request for the TTCN funding in 2023. 3GPP PCG/OP has approved the 2023 TTCN funding request from TSG RAN of 58 person-months.
  The finalized TTCN Tasks List has been reviewed and endorsed at RAN5#97 (Nov) for TSG RAN approval at RAN#98-e (Dec).
 The finalized TTCN Tasks List is to be approved by TSG RAN at RAN#98-e.
Based on inputs to RAN5#97, the updated list of TTCN tasks is presented in the next slides.

## Slide 15
2022 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | 3GPP related Work Item
5GS: NE-DC (option 4) | Rel-15 | N,L | Q1’23 | 35 | Q1’22-Q1’23 | 1 | 5GS_NR_LTE-UEConTest
5G V2X with NR sidelink | Rel-16 | N,L | Q2’23 | 74 | Q4’20-Q2’23 | 2 | 5G_V2X_NRSL_eV2XARC-UEConTest
MR-DC & NR CA enhancements | Rel-16 | N,L | Q2’23 | 29 | Q1’22-Q2’23 | 1 | LTE_NR_DC_CA_enh-UEConTest
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q2’23 | 22 | Q1’22-Q3’23 | 2 | NR_unlic-UEConTest
IMS eCall over NR | Rel-16 | N | Q1’23 | 20 | Q3’21-Q1’23 | 0.5 | NR_EIEI-UEConTest
NR positioning | Rel-16 | N | Q2’23 | 29 | Q2’21-Q2’23 | 0.2 | NR_pos-UEConTest
NR MIMO enhancements | Rel-16 | N | Q4’22 | 1 | Q4’22-Q1’23 | 0.3 | NR_eMIMO-UEConTest
NR 2-step RACH | Rel-16 | N | Q4’22 | 8 | Q3’22-Q1’23 | 0.5 | NR_2step_RACH-UEConTest
NW slicing enhancements - Phase2 | Rel-17 | N | Q2’23 | 13 | Q4’22-Q2’23 | 1 | eNS_Ph2-UEConTest
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q2’23 | >11 | Q4’22-Q4’23 | 2 | NR_ENDC_SON_MDT_enh-UEConTest
Reduced capability NR UE (RedCap) | Rel-17 | N | Q2’23 | >8 | Q4’22-Q4’23 | 1.5 | NR_redcap_plus_ARCH-UEConTest
NR multi/broadcast services (MBS) | Rel-17 | N | Q2’23 | 44 | Q4’22-Q4’23 | 4 | NR_MBS_5MBS_5MBUSA-UEConTest
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q4’23 | 1.5 | LTE_NR_MUSIM-UEConTest
NR UE power saving enhancements | Rel-17 | N | Q3’23 | 5 | Q4’22-Q4’23 | 1.5 | NR_UE_pow_sav_enh_plus_CT-UEConTest
NR RAN slicing enhancements | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 1.5 | NR_slice-UEConTest
NR sidelink enhancements | Rel-17 | N | Q3’23 | 2 | Q4’22-Q4’23 | 0.5 | NR_SL_enh-UEConTest
NR sidelink relay | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 1.5 | NR_SL_Relay-UEConTest
TEIx_Test (new TC coverage) | Rel-15+ | All | n/a | 10 | Q1’23-Q4’23 | 1 | TEIx_Test
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | >341 |  | 74.5 | person-months
Preparing for 2023 TTCN Work – Tasks List
2022 tasks completion and maintenance
Notes: Note: TTCN of some features initially started in 2022 will only be completed in 2023 due to availability of prose late in CY2022, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 16
2023 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | 3GPP related Work Item
Inter-system mobility between untrusted non-3GPP and 3GPP | Rel-15 | L,N | Q2’23 | 8 | Q1’23-Q4’23 | 3 | TEI15_Test
NB-IoT/eMTC for non-terrestrial networks (NTN) | Rel-17 | L | Q3’23 | 14 | Q1’23-Q4’23 | 3 | LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest
NR coverage enhancements | Rel-17 | N | Q2’23 | 6 | Q1’23-Q3’23 | 1.5 | NR_cov_enh-UEConTest
NR UL data compression (UDC) | Rel-17 | N | Q2’23 | 11 | Q1’23-Q3’23 | 2 | NR_UDC-UEConTest
NR industrial IoT and URLLC enhancements | Rel-17 | N | Q2’23 | >3 | Q1’23-Q3’23 | 1.5 | NR_IIoT_URLLC_enh-UEConTest
NR small data transmissions in INACTIVE state | Rel-17 | N | Q3’23 | 8 | Q1’23-Q4’23 | 1.5 | NR_SmallData_INACTIVE-UEConTest
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q4’23 | >13 | Q1’23-Q1’24 | 3 | NR_NTN_Solutions-UEConTest
5G non-public network enhancements | Rel-17 | N | Q4’23 | 12 | Q1’23-Q1’24 | 2 | NG_RAN_PRN_enh-UEConTest
NR MIMO further enhancements | Rel-17 | N | Q4’23 | 3 | Q1’23-Q1’24 | 1 | NR_feMIMO-UEConTest
MCX enhancements | R15to16 | L | Q3’24 | 43 | Q1’23-Q4’24 | 4 | MCenh_UEConTest ; MCProtoc16-UEConTest
5G access traffic steering, switch and splitting | Rel-16 | N | Q4’23 | 6 | Q1’23-Q1’24 | 1.5 | NR_ATSSS-UEConTest
User plane integrity protection for EPC | Rel-17 | L | Q2’23 | 11 | Q1’23-Q3’23 | 1.5 | UPIP_SEC_LTE-RAN-UEConTest
NR QoE management and optimizations | Rel-17 | N | Q3’23 | 4 | Q1’23-Q4’23 | 1 | NR_QoE-UEConTest
5G control plane steering of roaming for UE in connected mode enhancements (CP SOR) | Rel-17 | N | Q3’23 | 5 | Q1’23-Q4’23 | 1 | eCPSOR_CON-UEConTest
NR positioning enhancements | Rel-17 | N | Q2’24 | 6 | Q1’23-Q3’24 | 1.5 | NR_pos_enh-UEConTest
New/extended bands & band combinations | R15to18 | L,N | Q4’23 | n/a | Q1’23-Q4’23 | 0.5 | NR_lic_bands_BW_R1x-UEConTest NR_CADC_NR_LTE_DC_R1x-UEConTest, LTE_NBIOT_eMTC_NTN_req-UEConTest (new)
Total: |  |  |  | >153 |  | 29.5 | person-months
Preparing for 2023 TTCN Work – Tasks List
New 2023 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 17
2023 workload is estimated at 104 person-months (pm), see previous slides.
PCG#49/OP#48 approved the 3GPP funding of 58 pm for 2023 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2023.
Current commitments for 2023 are as follows:
3GPP companies / 3GPP MRPs committed to provide 20 pm as voluntary contributions for 2023 TTCN development.
Total resources of 104 pm  no estimated funding gap.
Preparing for 2023 TTCN Work
Funding
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#49/OP#48 approved (decision OP48/05)
CTIA/PTCRB | 12 | NE-DC, NR IIoT/URLLC, MCX, RedCap
GCF | 12 | NR V2X, NR 2-step RACH, NR Rel-17 enh., RedCap, MCX
Qualcomm | 2 | NR-U, SDT, NTN-IoT
Total: | 84 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Anritsu | 1 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | 
Total: | 20 | 

## Slide 18: Annexes

## Slide 19: TTCN deliveries and baseline 2022 schedule
One TTCN-2 full delivery (FDD & LCR TDD) and five TTCN-3 full deliveries.
  Type definitions baseline upgrade to 3GPP Release 17 required in 2022:
  Rel-17 Stage3 freeze declared by 3GPP in March 2022.
  Rel-17 ASN.1 declared frozen by 3GPP in June 2022, but may not be fully implementable.
  Rel-17 ASN.1 declared fully implementable by 3GPP in September 2022.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk04 |  |  | 21-Jan |  | 
wk12 | 25-Mar | 21-Mar | 25-Mar | TTCN-3 | 
wk16 |  |  | 14-Apr |  | GCF CAG#70 (19-22 Apr)
wk19 |  |  | 06-May |  | PTCRB PVG#97 (10-12 May)
wk23 | 10-Jun | 06-Jun | 10-Jun | TTCN-3 | 
wk30 |  |  | 22-Jul |  | GCF CAG#71 (26-29 Jul)
wk32 |  |  | 22-Jul |  | PTCRB PVG#98 (9-11 Aug)
wk37 | 16-Sep | 12-Sep | 16-Sep | TTCN-3 | 
wk42 |  |  | 14-Oct |  | GCF CAG#72 (18-21 Oct)
wk43 | 28-Oct | 19-Oct | 28-Oct | TTCN-3 Rel-17 Baseline upgrade | Move to Rel-17 Sep'22 baseline
wk45 |  |  | 04-Nov |  | PTCRB PVG#99 (8-10 Nov)
wk48 | 01-Dec | 28-Nov |  | TTCN2 (FDD) | 
wk48 | 02-Dec | 28-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 09-Dec | 05-Dec | 09-Dec | TTCN-3 | 

## Slide 20: TTCN deliveries and baseline 2023 schedule
One TTCN-2 full delivery (FDD & LCR TDD) and four TTCN-3 full deliveries.
No type definitions baseline upgrade planned in 2023 (for now).
  Note: Rel-18 ASN.1 freeze scheduled by 3GPP in March 2024.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk05 |  |  | 03-Feb |  | GCF CAG#73 (7-9 Feb)
wk07 |  |  | 17-Feb |  | PTCRB PVG#100 (21-23 Feb)
wk12 | 24-Mar | 20-Mar | 24-Mar | TTCN-3 | 
wk16 |  |  | 21-Apr |  | GCF CAG#74 (25-28 Apr)
wk19 |  |  | 12-May |  | PTCRB PVG#101 (16-18 May)
wk24 | 16-Jun | 12-Jun | 16-Jun | TTCN-3 | 
wk29 |  |  | 21-Jul |  | GCF CAG#75 (25-28 Jul)
wk32 |  |  | 11-Aug |  | PTCRB PVG#102 (15-17 Aug)
wk37 | 15-Sep | 11-Sep | 15-Sep | TTCN-3 | 
wk41 |  |  | 13-Oct |  | GCF CAG#76 (17-20 Oct)
wk44 |  |  | 03-Nov |  | PTCRB PVG#103 (7-9 Nov)
wk48 | 30-Nov | 27-Nov |  | TTCN2 (FDD) | 
wk48 | 01-Dec | 27-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 08-Dec | 04-Dec | 08-Dec | TTCN-3 | 

## Slide 21: 5GS Rel-15 – Protocol test case numbers After RAN5#97
5GS Rel-15 | TCs # | Details
NR/5GC (5G option 2) | Total: 449 | IdleMode: 62, NR L2: 81, NR RRC: 106, 5GC: 57, Multilayer: 36, IMS: 97, POS: 10.
EN-DC (5G option 3) | Total: 125 | NR L2: 71, RRC: 51, EPC: 3, IMS, POS: none.
NE-DC (5G option 4) | Total: 35 | NR L2: 2, NR RRC: 33, IdleMode, 5GC, Multilayer, IMS, POS: none.
TOTAL: | 609 | 
Notes: Legend:
Blue: changes from last MCC TF160 report.