## Cover sheet
3GPP TSG-RAN WG5 Meeting #97 | [10 empty] | R5-226707
Toulouse, France, November 14 - 18, 2022
Agenda Item: | 7.4.2
Source: | China Telecom,CATT,ZTE
Title: | UE Conformance Test Aspects - Access Traffic Steering, Switch and Splitting support in 5G system
Work item code: | ATSSS-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
This work item covers the protocol conformance testing for Rel-16 Access Traffic Steering, Switch and Splitting support in 5G system
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 6 (+6)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 6 (+6)
FR1 |  | 5% (+5%) | 0 | 6 (+6)
FR2 |  | 5% (+5%) | 0 | 6 (+6)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 6 (+6) | 0% | 0 | 6 (+6) | 0% | 0 | 6 (+6)
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-222547 | New WID on UE Conformance Test Aspects– Access Traffic Steering, Switch and Splitting support in 5G system
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - Access Traffic Steering, Switch and Splitting support in 5G system | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | ATSSS-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-16 ATSSS features(UID=970076) | [12 empty] | vs Area
WP Resp: |  | Jing Zhao，China Telecom |  |  | zhaoj16@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 5% (+5%) | 5% (+5%)
[14 empty] | 6 (+6) | 6 (+6)
[14 empty] | 6 (+6) | 6 (+6)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.7 | General and Signaling Test Environment for Rel-16 ATSSS testing | Add changes to default messages | China Telecom | RAN5#98 (Feb-23) |  | zhaoj16@chinatelecom.cn | 0.5
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | <Clause> | Introduction of common implementation conformance statements for Rel-16 ATSSS testing | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | China Telecom | RAN5#98 (Feb-23) |  | zhaoj16@chinatelecom.cn | 0.5
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NAS
|  | 38.523-1 | 10.4 | ATSSS session management
|  | 38.523-1 | 10.4.1 | UE-requested MA PDU session management
3 | Y | 38.523-1 | 10.4.1.1 | UE-requested MA PDU session establishment / ATSSS / Registered to same PLMNs over 3GPP and non-3GPP accesses / Success | ****TP1: [TS 24.501: 6.4.1.2]**** WITH: UE is registered over both 3GPP and non-3GPP accesses and SS informs the UE that it supports ATSSS feature in the 5GS network feature support information element. WHEN: UE is configured to request a new MA PDU session THEN: UE sends a PDU Session Establishment Request over any of the two accesses and sets the request type to "MA PDU request" in the UL NAS TRANSPORT message and sets the ATSSS-ST bits in the 5GSM capability IE of the PDU SESSION ESTABLISHMENT REQUEST message accroding to the ATSSS functionality and steering mode that UE supports ****TP2: [TS 24.501: 6.4.1.2]**** WITH: UE is registered over 3GPP access and an MA PDU session has been established successfully on this access WHEN: UE registers over non-3GPP access in the same PLMN THEN: UE initiates the UE-requested PDU session establishment procedure with the same PDU session ID of 3GPP access | China Telecom | RAN5#98 (Feb-23) |  | zhaoj16@chinatelecom.cn | 1 | 0% | 0% |  | 0% | 0%
4 | Y | 38.523-1 | 10.4.1.2 | UE-requested MA PDU session establishment / ATSSS / Registered to different PLMNs over 3GPP and non-3GPP accesses / Success | ****TP1: [TS 24.501: 6.4.1.2]**** WITH: UE in registered over 3GPP and non-3GPP accesses and SS informs the UE that it supports ATSSS feature in the 5GS network feature support information element. WHEN: UE is configured to request a new MA PDU session THEN: UE sends a PDU Session Establishment Request over one access and after this PDU Session is established, UE sends another PDU Session Establishment Request over the other access and provides the same PDU Session ID and Request Type as "MA PDU Request" in the UL NAS Transport message. ****TP2: [TS 24.501: 6.4.1.2]**** WITH: UE is registered over 3GPP access and an MA PDU session has been established successfully on this access WHEN: UE registers over non-3GPP access in the different PLMN THEN: UE initiates the UE-requested PDU session establishment procedure with the same PDU session ID of 3GPP access | ZTE | RAN5#98 (Feb-23) |  | ma.wei4@zte.com.cn | 1 | 0% | 0% |  | 0% | 0%
5 | Y | 38.523-1 | 10.1.4.3 | UE-requested MA PDU session modification / ATSSS / Success | ****TP1: [TS 24.501: 6.4.2.4]**** WITH: the UE in PDU SESSION ACTIVE state and 5GMM-CONNECTED mode WHEN: UE requested to modify the PDU session from EPS to an MA PDU session with the Request type IE set to "MA PDU request" in the UL NAS TRANSPORT message THEN: UE transmits an PDU SESSION MODIFICATION COMPLETE message | CATT | RAN5#98 (Feb-23) |  | chenxiaozhong@catt.cn | 1 | 0% | 0% |  | 0% | 0%
6 | Y | 38.523-1 | 10.1.4.4 | UE-requested MA PDU session modification / ATSSS / Abnormal / MA PDU session is not allowed | ****TP1: [TS 24.501: 6.4.2.4]**** WITH: UE is in PDU SESSION ACTIVE state and requested to modify the PDU session from EPS to an MA PDU session with the Request type IE set to "MA PDU request" in the UL NAS TRANSPORT message WHEN: UE receives PDU SESSION MODIFICATION REJECT message with 5GSM cause IE set to "requested service option not subscribed" THEN: UE stops timer T3581, release the allocated PTI value, and enter the state PROCEDURE TRANSACTION INACTIVE | CATT | RAN5#99 (May-23) |  | chenxiaozhong@catt.cn | 1 | 0% | 0% |  | 0% | 0%
|  | 38.523-1 | 10.4.2 | Network-requested MA PDU session management
7 | Y | 38.523-1 | 10.4.2.1 | Network-requested MA PDU session modification / ATSSS / Success | ****TP1: [TS 24.501: 6.3.2]**** WITH: UE is in 5GMM-REGISTERED state with an established MA PDU session that has user-plane resources established on both 3GPP access and non-3GPP access, and the Steering mode indicates by the ATSSS rule is "Active-standby" and "Active 3GPP and no standby" WHEN: UE receives a PDU SESSION MODIFICATION COMMAND message with updated ATSSS rule which indicates the steer mode to "Active-standby" and "Active non-3GPP and no standby" THEN: UE distributes all the uplink traffic across non-3GPP access in this MA PDU session | ZTE | RAN5#99 (May-23) |  | ma.wei4@zte.com.cn | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 38.523-1 | 10.4.2.2 | Network-requested MA PDU session release / ATSSS / Accepted | ****TP1: [TS 24.501: 6.3.3.3]**** WITH: UE is in PDU SESSION ACTIVE state and the MA PDU session has user-plane resources established on both 3GPP access and non-3GPP access WHEN: UE receives the PDU SESSION RELEASE COMMAND includes the Access type IE with "Non-3GPP access" THEN: UE transmits PDU SESSION RELEASE COMPLETE message and the user-plane resources on non-3GPP access is released ****TP2: [TS 38.331: 6.3.3.3]**** WITH: UE is in PDU SESSION ACTIVE state and the MA PDU session has user-plane resources established on 3GPP access WHEN: UE receives the PDU SESSION RELEASE COMMAND includes the Access type IE with "3GPP access" THEN: UE transmits PDU SESSION RELEASE COMPLETE message and the whole MA PDU session was released | China Telecom | RAN5#99 (May-23) |  | zhaoj16@chinatelecom.cn | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
9 |  | 38.523-2 | 4.1 | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 | China telecom | RAN5#98 (Feb-23) |  | zhaoj16@chinatelecom.cn | 0.2
10 |  | 38.523-2 | 4.2 | <Title> | Add Applicability Condition for new NR Multi-SIM test cases | China telecom | RAN5#98 (Feb-24) |  | zhaoj16@chinatelecom.cn | 0.2
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.