## R16 NR bands and CBW extensions
WP Title: | UE Conformance Test Aspects - Rel-16 NR bands and extension of existing NR bands (NR_bands_BW_R16-UEConTest) | [9 empty] | Overall config. Completion | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common clauses (chapter 5) | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.523-3: Protocol | 38.533: RRM & 38.571-1: LCS | 38.903: MU and TT | 38.905: Test point analysis | End of work plan columns. Note! Do not remove this column. | [6 empty] | Columns U to X is only used for WP rapporteur guide and notes and will be removed when the work plan is published
WP rapporteur's guide: All WP rows that represent WP work tasks must have a WP item ID number assigned. Other WP rows such as header rows used to group WP Items should NOT have any WP item ID numbers assigned (leave empty). How to assign unique WP item ID numbers (column A): In the WP item ID column double-click in the cell for the WP item row to assign the next free WP item ID number. Note! If You add numbers manually make sure each WP item row have an unique WP item ID number.
WP Scope: | This work plan covers the tasks needed to include new Rel-16 NR bands and new channel bandwidths added to existing Rel-15 bands. NOTE! The company listed in column H is responsible to secure that required information for the NR bands or extended channel bandwidth is complete in the TSs and TRs as listed in columns P to Y. New NR bands and CBW extensions since previous version are highlighted in red text.
WP Resp: | Leif Mattisson, Ericsson
TS Resp: | - | [20 empty] | Maximum reported status to RP before WI scope extension: |  |  |  |  | 76%
WP Item ID | Source TS | Type | RAN4 WI code | RAN4 WID | RAN4 completion | Sub-WI Scope | Company | Target | Comments | Weight | [11 empty] | WP | 5% | Work plan contribution to WI completion |  |  |  | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[22 empty] | Grp | completion | #configs | #assigned | #completed | #ongoing | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[6 empty] | (New band/Ref. Config/New CBW) | [15 empty] | Overall | 79.65% | 26 | 22 | 18 | 3 |  |  | CMCC | songdan@chinamobile.com
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [11 empty] | 2 | 1 | 1 | 3 | 3 | 0.1 | 1 | 5 | 5 | [9 empty] | Dish Network | jussi_kuusisto@outlook.com; aleksi.heino@wecertification.com
| 38.101-1 | New Rel-16 NR FR1 bands | [19 empty] | 1 | 84.65% | 7 | 7 | 5 | 1 |  |  | NTT DOCOMO, INC. | takashi.akao.wa@nttdocomo.com; takahiro.arai.kw@nttdocomo.com
1 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n14 | RP-190965 | 100% | n14 | AT&T | RAN5#90 (Feb-21) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [11 empty] | China Unicom | shiyu19@chinaunicom.cn
2 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n18 | RP-191556 | 100% | n18 | KDDI | RAN5#96 (Aug-22) |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | [9 empty] | Softbank | kenichi.kihara@g.softbank.co.jp
17 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n26 | RP-192736 | 100% | n26 | Dish Network | RAN5#89 (Nov-20) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | [9 empty] | Ericsson | mats.e.johansson@ericsson.com
4 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n30 | RP-190967 | 100% | n30 | AT&T | RAN5#96 (Aug-22) | Everything complete except for a number of UL MIMO test clauses. | 1 | 92.55% | 100% | 100% | 100% | 60% | 100% | 100% | 100% |  | 100% | [9 empty] | China Telecom | zhaoj16@chinatelecom.cn | Jing Zhao
5 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n48 | RP-190908 | 100% | n48 | Ericsson | RAN5#88 (Aug-20) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
27 | 38.101-1 | New Rel-16 NR FR1 bands | NR_n53 | RP-192409 | 100% | n53 | Globalstar, Nokia | RAN5#90 (Feb-21) | RAN5#90-e: 38.523-3 => clause 11 updated 38.508-2 => Add Band n53 into A.4.3.9 38.508-1 => Correction of test frequencies | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | [9 empty] | Softbank | kenichi.kihara@g.softbank.co.jp
6 | 38.101-1 | New Rel-16 NR FR1 bands | NR_band_n65 | RP-190360 | 100% | n65 | Dish Network | RAN5#87 (May-20) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | [9 empty] | CMCC, CBN | songdan@chinamobile.com
2 | 38.101-1 | New Rel-16 NR FR1 bands | NR_FDD_bands_varduplex | RP-192820 | 100% | n91 | Orange, Nokia | RAN5#97 (Nov-22) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | [9 empty] | Softbank | kenichi.kihara@g.softbank.co.jp
2 | 38.101-1 | New Rel-16 NR FR1 bands | NR_FDD_bands_varduplex | RP-192820 | 100% | n92 | Orange, Nokia | RAN5#97 (Nov-22) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | [9 empty] | Softbank | kenichi.kihara@g.softbank.co.jp
2 | 38.101-1 | New Rel-16 NR FR1 bands | NR_FDD_bands_varduplex | RP-192820 | 100% | n93 | Orange, Nokia | RAN5#97 (Nov-22) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | [9 empty] | Softbank | kenichi.kihara@g.softbank.co.jp
2 | 38.101-1 | New Rel-16 NR FR1 bands | NR_FDD_bands_varduplex | RP-192820 | 100% | n94 | Orange, Nokia | RAN5#97 (Nov-22) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | [9 empty] | Softbank | kenichi.kihara@g.softbank.co.jp
| 38.101-1 | New Rel-16 NR FR1 SDL bands and reference CA configurations included in the associated RAN4 WID (if any) | [19 empty] | 2 | 100% | 1 | 1 | 1 | 0 |  |  | AT&T | rb354e@att.com
7 | 38.101-1 | New Rel-16 NR FR1 SDL bands and reference CA configurations included in the associated RAN4 WID (if any) | NR_n29 | RP-192236 | 100% | n29 and CA_n29A-n66A | Dish Network | RAN5#87 (May-20) | For CA_n29A_n66A , the configuration specific work is 100%. | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | [9 empty] | Anritsu | Masafumi.Setsu@anritsu.com | Setsu, Masafumi
| 38.101-1 | New Rel-16 NR FR1 SUL bands and reference CA configurations included in the associated RAN4 WID (if any) | [19 empty] | 3 | 50% | 2 | 1 | 1 | 0 |  |  | KDDI | ta-matsuyoshi@kddi.com | Taiki Matsuyoshi
8 | 38.101-1 | New Rel-16 NR FR1 SUL bands and reference CA configurations included in the associated RAN4 WID (if any) | NR_SUL_UL_n5 | RP-191116 | 100% | n89 SUL |  | TBD |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0%
18 | 38.101-1 | New Rel-16 NR FR1 SUL bands and reference CA configurations included in the associated RAN4 WID (if any) | NR_SUL_band_2010_2025MHz | RP-192584 | 100% | n95 SUL | CMCC | RAN5#87 (May-20) |  | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100%
| 38.101-2 | New Rel-16 NR FR2 bands | [19 empty] | 4 | 57.16% | 1 | 1 | 0 | 1
9 | 38.101-2 | New Rel-16 NR FR2 bands | NR_n259 | RP-200249 | 100% | n259 | NTT DOCOMO, INC. | RAN5#96 (Aug-22) | Remains: - 38.521-2, 3: MU and TT | 1 | 57.16% | 100% | 0% | 60% | 50% | 40% | 60% | 20% | 60% | 70%
| 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | [19 empty] | 5 | 73.85% | 15 | 12 | 11 | 1
10 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n1_BW | RP-192009 | 100% | n1 adding CBW 30 and 40 MHz | China Unicom | RAN5#89 (Nov-20) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
19 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n1_BW2 | RP-192801 | 100% | n1 adding CBW 25 and 50 MHz | China Unicom | RAN5#89 (Nov-20) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
25 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n3_BW | RP-200305 | 100% | n3 adding CBW 40MHz | China Telecom | RAN5#91 (May-21) |  | 1 | 100% | 100% |  | 100% |  | 100%
11 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n7_BW | RP-190137 | 100% | n7 adding CBW 25MHz, 30MHz, 40MHz and 50MHz | Orange | RAN5#96 (Aug-22) |  | 1 | 7.786% | 0% |  | 100% | 3% | 0% |  |  |  | 0%
20 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n25_BW | RP-192401 | 100% | n25 adding CBW 25, 30 and 40 MHz | T-Mobile, Ericsson, Rhode&Schwarz | TBD | RAN5#93-e: CBW 35 MHz removed from the Sub-WI scope as deferred by RAN4 to Rel-17. | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
21 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n28_BW | RP-192261 | 100% | n28 adding CBW 30 MHz | CMCC, CBN | RAN5#88-e (Aug-20) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
12 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n38_BW | RP-191472 | 100% | n38 adding CBW 40MHz | Huawei | RAN5#89 (Nov-20) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
22 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n38_BW2 | RP-192215 | 100% | n38 adding CBW 25 MHz and 30 MHz | Anritsu | RAN5#94 (Feb-21) | RAN5#93-e: CBW 50 MHz removed from the Sub-WI scope as not included in the RAN4 Rel-16 CR for the RAN4 WI. | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
13 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n41_BW | RP-191681 | 100% | n41 adding CBW 30MHz | Softbank | RAN5#89 (Nov-20) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
14 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n50_BW | RP-182829 | 100% | n50 adding CBW 30MHz |  | TBD |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
26 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n65_BW | RP-200306 | 100% | n65 adding CBW 50MHz |  | TBD |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
23 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n66_BW | RP-200265 | 100% | n66 adding CBW 25, 30 MHz and asymmetric channel bandwidth combination set 1 | Huawei | RAN5#87 (May-20) |  | 1 | 100% | 100% |  | 100% |  | 100%
24 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n75_BW | RP-192216 | 100% | n75 adding CBW 25 MHz, 30 MHz, 40 MHz and 50 MHz |  | TBD |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
15 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n77_n78_BW | RP-192349 | 100% | n77 adding CBW 25MHz, 30MHz and 70MHz | China Unicom | RAN5#95 (May-22) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
16 | 38.101-1 | Channel bandwidth addition to existing Rel-15 FR1 bands | NR_n77_n78_BW | RP-192349 | 100% | n78 adding CBW 25MHz, 30MHz and 70MHz | China Unicom | RAN5#95 (May-22) |  | 1 | 100% | 100% |  | 100% | 100% | 100% |  |  |  | 100%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on O1: Todo for 38.508-1: - Add test frequencies to clause 4.3.1 for the new band. - Add test frequencies to clause 6.2.3.1 for protocol testing based on the default CBW chosen for protocol testing of teh band. - Add RF low, Mid and High test channel bandwidth in clause 4.3.1
Note on P1: To do 38.508-2: - Add the new band to the relevant table in clause A.4.3.1
Note on Q1: To do 38.521-x chapter 5: - Add operating band to clause 5.2. - Add the channel bandwidth for the band to clause 5.3.5. - Add the applicable NR-ARFCN for teh band to Table 5.4.2.3-1. - Add the applicable SS raster for teh band to Table 5.4.3.3-1. - Add the default UE TX-RX frequency separation for teh band to Table 5.4.4-1.
Note on T1: Todo for 38.523-3: If the band's overall bandwidth is less than 4*default CBW for protocol testing then thenexecution guidelineneed to be added to 38.523-3 clause 11. Remark: Some protocol test cases use up to 4 inter-frequency cells. If not then there is no impact on 38.523-3 and the completion can be set to 100%.
Note on U1: 38.533: Add band to NR band groups in clause 3A.4 in TS 38.533. This clause is referenced from TSuse is referenced from TS 37.571-1 clause 4.12.3 for defintion of NR band groups.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.
Note on AG6: The company and email addresses are used by the WP support tool when creating WP status update request emails. The companies in the company column should be the assigned companies in column F of the WP.
Note on AH7: Use email address format as used in the address fields of emails. If needed multipe email addresses may be included separated by semicolon (;).

## Revision History WP item status
Revision History WP item status | [5 empty] | Changed FROM | [12 empty] | Changed TO
Meeting | Date | Type of change | Source file name | WP Item | Description | TDOC(s) | Comments | Weight | Overall config. Completion | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common clauses (chapter 5) | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.523-3: Protocol | 38.533: RRM & 38.571-1: LCS | 38.903: MU and TT | 38.905: Test point analysis | TDOC(s) | Comments | Weight | Overall config. Completion | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common clauses (chapter 5) | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.523-3: Protocol | 38.533: RRM & 38.571-1: LCS | 38.903: MU and TT | 38.905: Test point analysis
2021-11-19 13h20: 12 status request email(s) sent
RAN5#93-e | 2021-11-19 | Request sent | Softbank-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to kenichi.kihara@g.softbank.co.jp
RAN5#93-e | 2021-11-19 | Request sent | NTT DOCOMO_ INC_-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to takashi.akao.wa@nttdocomo.com; takahiro.arai.kw@nttdocomo.com
RAN5#93-e | 2021-11-19 | Request sent | Huawei-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to Huawei
RAN5#93-e | 2021-11-19 | Request sent | Globalstar_ Nokia-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to Globalstar, Nokia
RAN5#93-e | 2021-11-19 | Request sent | Ericsson-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to mats.e.johansson@ericsson.com
RAN5#93-e | 2021-11-19 | Request sent | Dish Network-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to jussi_kuusisto@outlook.com; aleksi.heino@wecertification.com
RAN5#93-e | 2021-11-19 | Request sent | CMCC_ CBN-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to CMCC, CBN
RAN5#93-e | 2021-11-19 | Request sent | CMCC-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to songdan@chinamobile.com
RAN5#93-e | 2021-11-19 | Request sent | China Unicom-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to shiyu19@chinaunicom.cn
RAN5#93-e | 2021-11-19 | Request sent | China Telecom-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to zhaoj16@chinatelecom.cn
RAN5#93-e | 2021-11-19 | Request sent | AT_T-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to AT&T
RAN5#93-e | 2021-11-19 | Request sent | Anritsu-Draft R5-216629 R93e_WP_NR_bands_BW_R16-UEConTest_v1 WORK 2021-11-19 13h20 | - | Sent to Anritsu
2021-08-27 19h37: 11 status request email(s) sent
RAN5#92-e | 2021-08-27 | Request sent | Softbank-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to Softbank
RAN5#92-e | 2021-08-27 | Request sent | NTT DOCOMO_ INC_-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to NTT DOCOMO, INC.
RAN5#92-e | 2021-08-27 | Request sent | Huawei-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to Huawei
RAN5#92-e | 2021-08-27 | Request sent | Globalstar_ Nokia-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to Globalstar, Nokia
RAN5#92-e | 2021-08-27 | Request sent | Ericsson-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to Ericsson
RAN5#92-e | 2021-08-27 | Request sent | Dish Network-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to Dish Network
RAN5#92-e | 2021-08-27 | Request sent | CMCC_ CBN-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to CMCC, CBN
RAN5#92-e | 2021-08-27 | Request sent | CMCC-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to CMCC
RAN5#92-e | 2021-08-27 | Request sent | China Unicom-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to China Unicom
RAN5#92-e | 2021-08-27 | Request sent | China Telecom-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to China Telecom
RAN5#92-e | 2021-08-27 | Request sent | AT_T-Draft R5-21xxxx R92e_WP_NR_bands_BW_R16-UEConTest_v0 2021-08-27 19h37 | - | Sent to AT&T
End of revision history table rows (Do not remove)
Revision History Templates (Do not remove):
<Template WP item status change - Do not remove>
<Template WP item requests - Do not remove>

## Sheet1
Row Labels
Anritsu
AT&T
China Telecom
China Unicom
CMCC
CMCC, CBN
Dish Network
Ericsson
Globalstar, Nokia
Huawei
NTT DOCOMO, INC.
Softbank
(blank)
Grand Total