## Cover sheet
3GPP TSG-RAN WG5 Meeting #97 | [10 empty] | R5-227371
Toulouse, France, 14th - 18th Nov, 2022
Agenda Item: | 7.4.2
Source: | Apple
Title: | UE Conformance - New WID on UE Conformance Test Aspects – NR RRM enhancements
Work item code: | NR_RRM_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this RAN5 WI is to enable UE conformance testing for the Release 16 RRM enhancements related requirements. RAN5 conformance test procedures will be created to verify test requirements as per the scope being covered in RAN4 namely:
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 9% | 0 | 1
Completion Compensation |  | 1.388e-15%
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 11% | 0 | 1
FR1 |  | 12% | 0 | 0
FR2 |  | 8% | 0 | 0
FR1 + FR2 |  | 3%
NSA Option 3 (EN-DC) |  | 8% | 0 | 0
FR1 |  | 9% | 0 | 0
FR2 |  | 7% | 0 | 0
FR1 + FR2 |  | 2%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
NR RF TRP and TRS requirements and test methodologies for FR1 (SA and EN-DC)
EN_DC with PSCell in FR1 | 38.533
EN_DC with PSCell in FR2 | 38.533
NR Standalone in FR1 | 38.533 |  | 0 | 1 |  |  | 1 | [8 empty] | 4
NR Standalone in FR2 | 38.533 |  | 0 | 0 |  |  | 0 | [8 empty] | 4
5 References
[1] RP-221705 | New WID on UE Conformance Test Aspects – NR RRM enhancements
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - New WID on UE Conformance Test Aspects – NR RRM enhancements | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RRM_enh-UEConTest
WP Scope: |  | The purpose of this document is to create and track development of test requirements and procedures for new Release 16 RRM Enhancements | [13 empty] | vs Area
WP Resp: |  | Ashwin Mohan |  |  | ashwin_mohan@apple.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 5% | 5% | 5% | 5% | 5% | 5%
[15 empty] | 8 | 7 | 1 | 7 | 7 | 1
[15 empty] | 7.5 | 6.5 | 0.5 | 5.6 | 6.5 | 0.5
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
EN_DC with PSCell in FR1
|  | 38.533 | 4.5.2.7 | Void | [5 empty] | 0.1 | 0% |  | 0% |  |  |  |  | 0%
1 | Y | 38.533 | 4.5.2.8 | E-UTRAN - NR FR1 interruptions at NR SRS carrier based switching in asynchronous EN-DC | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#98 (Feb-23) | R5-227188, R5-227189 | Aligned with TS 38.133 Clause A.4.5.2.8 | 1 | 10% |  | 10% |  |  |  |  | 10%
2 | Y | 38.533 | 4.5.2.9 | E-UTRAN – NR interruptions at E-UTRA SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#98 (Feb-23) | R5-227190 | Aligned with TS 38.133 Clause A.4.5.2.9 | 1 | 10% |  | 10% |  |  |  |  | 0%
3 | Y | 38.533 | 4.5.3.4 | SCell Activation and deactivation of multiple unknown SCells in FR1 with single activation/deactivation command | Rel16 test requirements for Multiple Scell activation | Huawei, HiSilicon | RAN5#98 (Feb-23) |  | Aligned with TS 38.133 Clause A.4.5.3.4 | 1 | [7 empty] | 0%
|  | 38.533 | 4.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs | Rel16 test requirements for RRC based Active BWP switch | Huawei, HiSilicon |  |  |  | 0.1
4 | Y | 38.533 | 4.5.6.3.1 | Simultaneous E-UTRAN – NR PSCell FR1 DL active BWP switch in non-DRX in EN-DC on multiple CCs | Rel16 test requirements for RRC based Active BWP switch | Huawei, HiSilicon | RAN5#98 (Feb-23) |  |  | 0.1
|  | 38.533 | 4.5.6.5 | Simultaneous RRC-based Active BWP Switch on multiple CCs | Rel16 test requirements for RRC based Active BWP switch | Huawei, HiSilicon |  |  |  | 0.1
5 | Y | 38.533 | 4.5.6.5.1 | E-UTRAN – NR PSCell FR1 DL active BWP switch in non-DRX in synchronous EN-DC on multiple CCs | Rel16 test requirements for RRC based Active BWP switch | Huawei, HiSilicon |  |  |  | 0.1
6 | Y | 38.533 | 4.5.9.1 | UE specific CBW change on FR1 NR PSCell with non-DRX in synchronous EN- DC | Rel16 test requirements for UE specific CBW change |  | RAN5#98 (Feb-23) |  | Aligned with TS 38.133 Clause A.4.5.x.1. sub-clause number to be updated after RAN4 updates the same | 1 | [7 empty] | 0%
|  | 38.533 | 4.6.6 | Measurements with Autonomous Gaps | New sub-clause |  |  |  |  | 0.1
7 | Y | 38.533 | 4.6.6.1 | EN-DC intra-frequency CGI identification of NR FR1 cell with autonomous gaps in synchronous EN-DC | Rel16 test requirements for CGI Reading |  | RAN5#98 (Feb-23) |  | Aligned with TS 38.133 Clause A.4.6.6.1 | 1 | [7 empty] | 0%
EN_DC with PSCell in FR2
8 | Y | 38.533 | 5.5.2.7 | E-UTRAN – NR FR2 interruptions at E-UTRA SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227192 | Aligned with TS 38.133 Clause A.5.5.2.7 | 1 | 10% |  | 10% | [5 empty] | 0%
9 | Y | 38.533 | 5.5.2.8 | E-UTRAN – NR FR2 interruptions at NR SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227193 | Aligned with TS 38.133 Clause A.5.5.2.8 | 1 | 10% |  | 10% | [5 empty] | 0%
10 | Y | 38.533 | 5.5.3.4 | Multiple SCell Activation and deactivation of one unknown SCell and one known SCell in FR2 | Rel16 test requirements for Mandatory Gap Patterns |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.5.5.3.4 | 1 | 0% |  | 0% | [5 empty] | 0%
10 | Y | 38.533 | 5.5.3.x | Multiple SCell Activation and deactivation of one unknown SCell and one known SCell in FR2 | Rel16 test requirements for Multiple Scell activation. Clause number to be updated once RAN4 updates the same |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.5.5.3.x | 1 | 0% |  | 0% | [5 empty] | 0%
|  | 38.533 | 5.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs | Rel16 test requirements forActive BwP Switch |  |  |  | Aligned with TS 38.133 Clause A.5.5.10.1 | 1 | 0% |  | 0% | [5 empty] | 0%
11 | Y | 38.533 | 5.5.6.3.1 | E-UTRAN – NR PSCell FR2 and NR SCell FR2 DL active BWP switch on multiple CCs in synchronous EN-DC | Rel16 test requirements forActive BwP Switch |  | RAN5#99 (May-23)
|  | 38.533 | 5.5.6.4 | Uplink Spatial Relation Switch | Rel16 test requirements for Scell Dormancy Switch |  |  |  | Aligned with TS 38.133 Clause A.5.5.10.1 | 1 | 0% |  | 0% | [5 empty] | 0%
12 | Y | 38.533 | 5.5.6.4.1 | E-UTRAN – NR FR2 PSCell SCell dormancy switch of single FR2 SCell inside active time | Rel16 test requirements for Scell Dormancy Switch |  | RAN5#99 (May-23)
|  | 38.533 | 5.5.9 | Uplink Spatial Relation Switch | Rel16 test requirements for UE uplink spatial relation switch |  |  |  | Aligned with TS 38.133 Clause A.5.5.10.1 | 1 | 0% |  | 0% | [5 empty] | 0%
|  | 38.533 | 5.5.9.1 | MAC-CE based Uplink Spatial Relation Switch | Rel16 test requirements for UE uplink spatial relation switch |  |  |  | Aligned with TS 38.133 Clause A.5.5.10.1 | 1 | 0% |  | 0% | [5 empty] | 0%
13 | Y | 38.533 | 5.5.9.1.1 | E-UTRAN – NR PSCell FR2 uplink spatial relation switch for a known spatial relation | Rel16 test requirements for UE uplink spatial relation switch |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.5.5.10.1 | 1 | 0% |  | 0% | [5 empty] | 0%
|  | 38.533 | 5.5.9.2 | RRC based Uplink Spatial Relation Switch | Rel16 test requirements for UE uplink spatial relation switch |  |  |  | Aligned with TS 38.133 Clause A.5.5.10.1 | 1 | 0% |  | 0% | [5 empty] | 0%
14 | Y | 38.533 | 5.5.9.2.1 | UE specific CBW change on FR2 NR PSCell | Rel16 test requirements for UE uplink spatial relation switch |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.5.5.10.1 | 1 | 0% |  | 0% | [5 empty] | 0%
15 | Y | 38.533 | 5.5.10.1 | UE specific CBW change on FR2 NR PSCell | Rel16 test requirements for UE specific CBW change |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.5.5.10.1 | 1 | 0% |  | 0% | [5 empty] | 0%
|  | 38.533 | 5.6.5 | Measurements with Autonomous Gaps | New sub-clause |  |  |  |  | 0.1
16 | Y | 38.533 | 5.6.5.1 | EN-DC inter-frequency CGI identification of NR neighbor cell in FR2 | Rel16 test requirements for CGI Reading |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.5.6.6.1 | 1 | 0% |  | 0% | [5 empty] | 0%
NR Standalone in FR1
17 | Y | 38.533 | 6.5.2.2 | SA interruptions at NR SRS carrier based switching | Rel16 test requirements for SRS carrier based switching | Ericsson | RAN5#99 (May-23) | R5-227830, R5-227194 | Aligned with TS 38.133 Clause A.6.5.2.2 | 1 | 10% | 10% |  |  | 0%
|  | 38.533 | 6.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs | Rel16 test requirements for UE Active BW Switch |  |  |  | Aligned with TS 38.133 Clause A.6.5.8.1 | 1 | 0% | 0% |  |  | 0%
18 | Y | 38.533 | 6.5.6.3.1 | NR FR1- NR FR1 DL active BWP switch on multiple CCs with non-DRX in SA | Rel16 test requirements for UE Active BW Switch | Huawei, HiSilicon | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.6.6.2.9 | 1 | 0% | 0% |  |  | 0%
18 | Y | 38.533 | 6.5.6.5.1 | RRC based BWP switch on multiple CCs | Rel16 test requirements for UE Active BW Switch | Huawei, HiSilicon | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.6.6.2.9 | 1 | 0% | 0% |  |  | 0%
19 | Y | 38.533 | 6.5.8.1 | UE specific CBW change on PCell in FR1 in non-DRX | Rel16 test requirements for UE specific CBW change |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.6.5.8.1 | 1 | 0% | 0% |  |  | 0%
20 | Y | 38.533 | 6.6.2.9 | SA event triggered reporting tests with additional mandatory gap pattern | Rel16 test requirements for Mandatory Gap Patterns | Ericsson | RAN5#99 (May-23) | R5-227197, R5-227196 | Aligned with TS 38.133 Clause A.6.6.2.9 | 1 | 10% | 10% |  |  | 0%
21 | Y | 38.533 | 6.6.2.10 | SA event triggered reporting tests for FR1 when DRX is used | Rel16 Inter-Frequency Measurement without MG | Ericsson | RAN5#99 (May-23) | R5-227198 | Aligned with TS 38.133 Clause A.6.6.2.10 | 1 | 10% | 10% |  |  | 0%
22 | Y | 38.533 | 6.6.2.11 | SA event triggered reporting tests for FR1 without gap when DRX is not used | Rel16 Inter-Frequency Measurement without MG | Ericsson | RAN5#99 (May-23) | R5-227199 | Aligned with TS 38.133 Clause A.6.6.2.11 | 1 | 10% | 10% |  |  | 0%
|  | 38.533 | 6.6.7 | NR Measurements with autonomous gaps | New sub-clause |  |  |  |  | 0.1
23 | Y | 38.533 | 6.6.7.1 | SA intra-frequency CGI identification of NR neighbor cell in FR1 | Rel16 test requirements for CGI Reading |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.6.6.7.1 | 1 | 0% | 0% |  |  | 0%
24 | Y | 38.533 | 6.6.7.2 | Identification of a new CGI of inter-RAT E-UTRA cell using autonomous gaps in NR SA | Rel16 test requirements for CGI Reading |  | RAN5#99 (May-23) |  | Aligned with TS 38.133 Clause A.6.6.7.2 | 1 | 0% | 0% |  |  | 0%
NR Standalone in FR2
25 | Y | 38.533 | 7.5.2.2 | SA interruptions at NR SRS carrier-based switching | Rel16 test requirements for FR2 Inter-Band CA |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.7.5.3.3 | 1 | 0% | 0% |  |  |  | 0%
26 | Y | 38.533 | 7.5.3.3 | SCell Activation and deactivation for SCell in FR2 inter-band in non-DRX | Rel16 test requirements for FR2 Inter-Band CA |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.7.5.3.3 | 1 | 0% | 0% |  |  |  | 0%
27 | Y | 38.533 | 7.5.3.x | Multiple SCell Activation and deactivation of unknown SCell in both FR1 and FR2 in non-DRX | Rel16 test requirements for Multiple Scell activation. Clause number to be updated once RAN4 updates the same |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 7.5.6.3 | Simultaneous DCI-based and Timer-based Active BWP Switch on multiple CCs | New sub-clause |  |  |  |  | 0.1
28 | Y | 38.533 | 7.5.6.3.1 | Active BWP switch on multiple SCells with non-DRX in SA | Rel16 test requirements for BWP switching on multiple CCs |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.6.6.7.1 | 1 | 0% | 0% |  |  | 0%
|  | 38.533 | 7.5.9 | Uplink Spatial Relation Switch Delay | New sub-clause |  |  |  |  | 0.1
|  | 38.533 | 7.5.9.1 | MAC-CE based Spatial Relation switch | Rel16 test requirements for UE uplink spatial relation switch |  |  |  | Aligned with TS 38.133 Clause A.6.6.7.1 | 1 | 0% | 0% |  |  | 0%
29 | Y | 38.533 | 7.5.9.1.1 | NR PCell FR2 spatial relation associated with known DL-RS | Rel16 test requirements for UE uplink spatial relation switch |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.6.6.7.1 | 1 | 0% | 0% |  |  | 0%
|  | 38.533 | 7.5.9.2 | RRC based spatial relation switch | Rel16 test requirements for UE uplink spatial relation switch |  |  |  | Aligned with TS 38.133 Clause A.6.6.7.1 | 1 | 0% | 0% |  |  | 0%
30 | Y | 38.533 | 7.5.9.2.1 | NR PCell FR2 spatial relation switch associated with a known DL-RS | Rel16 test requirements for UE uplink spatial relation switch |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.6.6.7.1 | 1 | 0% | 0% |  |  | 0%
31 | Y | 38.533 | 7.5.10.1 | NR FR2 UE specific CBW change of PCell with non-DRX in SA | Rel16 test requirements on UE specific CBW |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.7.5.10.1 | 1 | 0% | 0% |  |  |  | 0%
32 | Y | 38.533 | 7.6.2.10 | SA event triggered reporting test without gap under non-DRX | Rel16 test requirements for Measurements without MG for Ues supporting interFrequencyMeas-NoGap-r16 | Ericsson | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.7.6.2.10 | 1 | 10% | 10% |  |  |  | 0%
33 | Y | 38.533 | 7.6.2.11 | SA event triggered reporting test without gap under DRX | Rel16 test requirements for Measurements without MG for Ues supporting interFrequencyMeas-NoGap-r16 | Ericsson | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.7.6.2.11 | 1 | 10% | 10% |  |  |  | 0%
34 | Y | 38.533 | 7.6.2.9 | SA event triggered reporting tests For FR2 without SSB time index detection when DRX is not used (PCell in FR2) (rel16 additional mandatory gap pattern 17) | Rel16 test requirements for Mandatory Gap Patterns |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.7.6.2.9 | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | 7.6.5 | NR Measurements with autonomous gaps | Rel16 test requirements for Measurements with autonomous gaps |  |  |  | Aligned with TS 38.133 Clause A.7.6.5.1 | 1 | 0% | 0% |  |  |  | 0%
35 | Y | 38.533 | 7.6.5.1 | SA interfrequency CGI reporting in autonomous gaps test (PCell in FR2) | Rel16 test requirements for Mandatory Gap Patterns |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 Clause A.7.6.5.1 | 1 | 0% | 0% |  |  |  | 0%
Annex A.3
36 |  | 38.533 | Annex A.3.x | Channel bandwidth (CBW) configurations | Rel16 updates for DL and UL CBW patterns for UE specific CBW configuration |  | RAN5#100 (Aug-23) |  | Aligned with TS 38.133 clause A.3.25 | 0.5 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.