## Cover sheet
3GPP TSG-RAN5 Meeting #98e | [10 empty] | RP-223013
Electronic meeting, 12th Dec 2022 - 16th Dec 2022
Agenda Item: | 13.4.31
Source: | Nokia, Nokia Shanghai Bell
Title: | WP for Enhanced IIoT and URLLC support for NR for RAN WG5 97
Work item code: | NR_IIOT_URLLC_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to the WID on Rel-17 NR-IIOT_URLLC_enh, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-17.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 5 (+5)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 5 (+5)
FR1
FR2
FR1 + FR2 |  | 5% (+5%) | 0 | 5 (+5)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
NR RF/RRM
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533 | 0% | 0 | 2 (+2) | [6 empty] | 0% | 0 | 2 (+2)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% | [8 empty] | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 3 (+3) | [6 empty] | 0% | 0 | 3 (+3)
Applicability Protocol test cases | 38.523-2 | 0% | [8 empty] | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-221416 | UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | <WP title> | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_IIOT_URLLC_enh-UEConTest
WP Scope: |  | Introduce common test environment and test cases for NR IIoT and URLLC enhancements in Rel-17 | [12 empty] | vs Area
WP Resp: |  | Matti Kangas |  |  | matti.kangas@nokia.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | TBD |  |  | TBD
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2 | FR1 + FR2
5% (+5%)
[14 empty] | 0 | 0 | 9 (+9)
[14 empty] | 0 | 0 | 5.4 (+5.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-2 | TBD | TBD | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#99 (May-23) |  |  | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
2 |  | 38.522 | 4.0 | Test case conditions and selection criteria | Add test case conditions for the new test cases introduced for 38.521-x. |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
3 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  | 0.1
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
4 | Y | 38.533 | 6.6.X | UE Rx-Tx time difference measurement for propagation delay compensation | Test Purpose(s): Measurement for Propagation Delay Compensation. UE shall perform and report the UE Rx-Tx time difference measurements within the specified UE Rx-Tx time difference measurement time. TS: 38.133; Clause(s): 7.1.2(?), 9.12, A.6.6.X |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  |  | 0%
5 | Y | 38.533 | 6.7.X | UE Rx-Tx time difference measurement accuracy for propagation delay compensation | Test Purpose(s): Measurement accuracy for Propagation Delay Compensation. UE Rx-Tx time difference measurement time fulfils the UE Rx-Tx measurement accuracy requirements. TS: 38.133; Clause(s): 7.1.2(?), 9.12, A.6.7.X |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  |  | 0%
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
6 | Y | 38.523-1 | 7.x.y.z.g | TBD | Test Purpose(s): Trigger survival time state entry for a DRB which activates all the RLC entities configured for PDCP duplication TS:38.321; Clause(s) 5.4.1 |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  |  | 0%
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
7 | Y | 38.523-1 | 8.x.y.z.b | TBD | Test Purpose(s): Propagation delay compensation (PDC) based on round-trip-time (RTT) measurements TS:38.331; Clause(s) 5.5, 5.7.1.3, 6.2.2, 6.3.2 | Nokia | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  |  | 0%
8 | Y | 38.523-1 | 8.x.y.z.c | TBD | Test Purpose(s): Propagation delay compensation (PDC) based on timing advance (TA) TS:38.331; Clause(s) 5.7.1.3, 6.2.2 | Nokia | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  |  |  | 0%
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
9 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
10 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add test case applicability conditions for the new test cases introduced in 38.523-1 |  | RAN5#99 (May-23) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | TBD | TBD | TBD |  | RAN5#99 (May-23) |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.