# 3GPP TSG RAN Meeting #98-e	RP-223229

Electronic Meeting, December 12-16, 2022

## Status Report to TSG

Agenda item:			13.4.30

| WI / SI Name | UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: No | Performance part: No |  | Testing part: Yes |
| Acronym | LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest |  |  |  |  |
| Unique ID | 960087 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-221548 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: - | Core part: - | Performance part: - | Testing part: 09/2023 |  |
| Overall Completion level | Study Item: - | Core part: - | Performance Part: - | Testing part: 95% |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | TSG RAN WG5 |
| --- | --- | --- |
| Rapporteur | Name | Daiwei Zhou |
|  | Company | MediaTek Inc. |
|  | Email | daiwei.zhou@mediatek.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

#### 2.4.2	Remaining Open issues

## 2.5	RAN5

#### 2.5.1	Agreements

At RAN #96-e the WID for UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects was approved. Work Plan was created in [1].

#### Status after RAN5 #97 (the detail can be found in R5-226034)

- 95% overall completeness achieved.

- For Protocol test, 15 CRs were agreed.

#### 2.5.2	Remaining Open issues

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

## 4.	References

NOTE:	This can be e.g. a list of all related Tdocs in the affected WGs since last TSG, references to LSs, produced TRs/TSs, the work/study item description or status reports of previous TSGs.

General Papers:

[1]    R5-226034	WP UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects, MediaTek Inc.

TS 36.508 CRs

- R5-226377   Update of SIB Combinations for IoT NTN, MediaTek Inc.

- R5-227490   Update of SystemInformationBlockType1-BR-r13 for IoT NTN, MediaTek Inc.

TS 36.523-1 CRs

- R5-226445   Correction of IoT NTN TC 22.3.1.13, MediaTek Inc.

- R5-226458   Correction of IoT NTN TC 22.3.1.5a and 22.3.2.7a, MediaTek Inc.

- R5-226797   Correction of IoT NTN TC 22.2.13, MediaTek Inc.

- R5-227491   Addition of IoT NTN TC eMTC / NTN / GEO, MediaTek Inc.

- R5-227492   Addition of IoT NTN TC eMTC / NTN / DRX / (UL)HARQ RTT, MediaTek Inc.

- R5-227493   Addition of IoT NTN TC eMTC / NTN / UE specific TA report / UE specific Koffset, MediaTek Inc.

- R5-227494   Addition of IoT NTN TC eMTC / NTN / AM RLC / Receiver status triggers / extended t-Reordering configured, MediaTek Inc.

- R5-227495   Addition of IoT NTN TC eMTC / NTN / Ephemeris information update / T317 Expiry / T318 Expiry, MediaTek Inc.

- R5-227266   Addition of NTN test case 6.1.1.11, Qualcomm Tech. Netherlands B.V

- R5-227269   Addition of NTN test case 9.2.1.1.34, Qualcomm Tech. Netherlands B.V

TS 36.523-2 CRs

- R5-226032    Addition of PICS for Rel-17 NTN IoT, MediaTek Inc.

- R5-226033    Addition of applicability for NTN IoT cases, MediaTek Inc.

- R5-227270    Addition of applicability for IOT NTN test cases, Qualcomm Tech. Netherlands B.V

14.11.2019		minor adaptations for RAN #86

18.08.2019		minor adaptations for RAN #85

12.05.2019		minor adaptations for RAN #84

27.02.2019		minor adaptations for RAN #83

21.11.2018		completion levels with colours added (for RAN #82)

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects (for RAN #81)

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template