3GPP TSG-RAN WG2 #113bis-e								R2-2102889

E-meeting, April 2021

Agenda Item:	8.7.1

Source:	OPPO, CMCC

Title:	Work planning of R17 Sidelink Relay WI

Document for:	Discussion, Decision

Introduction

This is for the discussion working planning of R17 Sidelink Relay WI.

Discussion

  - WID Scope

In RP-210904, the scope of the work item is described as follows:

- Specify mechanisms for U2N relay discovery and (re)selection for L3 and L2 relaying [RAN2, RAN4]

  - Re-use LTE relay discovery and (re)selection as baseline

- Specify mechanisms for Relay and Remote UE authorization for L3 and L2 relaying [RAN3]

  - Re-use LTE as baseline

Work Item objectives specific to Layer-2 (L2) relaying:

- Specify mechanisms for E2E, i.e. PC5 and Uu, QoS management [RAN2]:

- Specify mechanisms for service continuity

  - Limited to intra-gNB cases [RAN2]

- Specify mechanisms for U2N Adaptation layer design [RAN2]

  - For bearer mapping and Remote UE identification, incl. RAN related security aspects if any

- Specify Control Plane procedures for U2N, including RRC connection management, system information delivery, paging mechanism and access control for Remote UE [RAN2, RAN3]

  - Work Planning

| Quarter | Meeting # | TU | Work Plan |
| --- | --- | --- | --- |
| Q2, 2021 | RAN2#113bis | 1.5 | NOTE: Start from the ones which has SA/CT impact as early as possible. - Specify mechanisms for U2N relay discovery and (re)selection for L3 and L2 relaying [RAN2, RAN4] - Re-use LTE relay discovery and (re)selection as baseline NOTE: Start from the ones which is related to RAN3 as well. - Specify Control Plane procedures for U2N, including RRC connection management, system information delivery, paging mechanism and access control for Remote UE [RAN2, RAN3] NOTE: Start the key part of the L2 U2N relay, in a best effort manner, i.e., deprioritized compared with the others - Specify mechanisms for U2N Adaptation layer design [RAN2] - For bearer mapping and Remote UE identification, incl. RAN related security aspects if any |
|  | RAN2#114 | 1 | NOTE: Continue work on the following bullets, prioritize the completion of this bullet in this meeting - Specify mechanisms for U2N relay discovery and (re)selection for L3 and L2 relaying [RAN2, RAN4] - Re-use LTE relay discovery and (re)selection as baseline NOTE: Continue work on the following bullets. - Specify Control Plane procedures for U2N, including RRC connection management, system information delivery, paging mechanism and access control for Remote UE [RAN2, RAN3] NOTE: Start the key part of the L2 U2N relay, in a best effort manner, i.e., deprioritized compared with the others - Specify mechanisms for U2N Adaptation layer design [RAN2] - For bearer mapping and Remote UE identification, incl. RAN related security aspects if any |
| Q3, 2021 | RAN2#115 | 2 | NOTE: Continue work on the following bullets. - Specify Control Plane procedures for U2N, including RRC connection management, system information delivery, paging mechanism and access control for Remote UE [RAN2, RAN3] NOTE: Start the following bullets (if objective-5 has not started yet). Prioritize the one on adaptation layer design which is the key part of this WI - Specify mechanisms for service continuity - Limited to intra-gNB cases [RAN2] - Specify mechanisms for U2N Adaptation layer design [RAN2] - For bearer mapping and Remote UE identification, incl. RAN related security aspects if any |
| Q4, 2021 | RAN2#115bis | 2 | NOTE: Complete the work as much as possible. - Specify Control Plane procedures for U2N, including RRC connection management, system information delivery, paging mechanism and access control for Remote UE [RAN2, RAN3] NOTE: Continue work on the following bullets, prioritize the work on adaptation layer design which is the key aspect of this WI - Specify mechanisms for E2E, i.e. PC5 and Uu, QoS management [RAN2]: - Specify mechanisms for service continuity - Limited to intra-gNB cases [RAN2] - Specify mechanisms for U2N Adaptation layer design [RAN2] - For bearer mapping and Remote UE identification, incl. RAN related security aspects if any |
|  | RAN2#116 | 2 | NOTE: Continue work on the following bullets.. - Specify mechanisms for E2E, i.e. PC5 and Uu, QoS management [RAN2]: - Specify mechanisms for service continuity - Limited to intra-gNB cases [RAN2] - Specify mechanisms for U2N Adaptation layer design [RAN2] - For bearer mapping and Remote UE identification, incl. RAN related security aspects if any |
|  | RAN3#114 | 0.5 | - Specify mechanisms for Relay and Remote UE authorization for L3 and L2 relaying [RAN3] NOTE: Based on RAN2 progress, work on RAN3 aspects if any for the following objectives - Specify Control Plane procedures for U2N, including RRC connection management, system information delivery, paging mechanism and access control for Remote UE [RAN2, RAN3] |
| Q1, 2022 | RAN2#117 | 2 | NOTE: Finish work on the following bullets.. - Specify mechanisms for E2E, i.e. PC5 and Uu, QoS management [RAN2]: - Specify mechanisms for service continuity - Limited to intra-gNB cases [RAN2] - Specify mechanisms for U2N Adaptation layer design [RAN2] - For bearer mapping and Remote UE identification, incl. RAN related security aspects if any |
|  | RAN3#114bis | 0.5 | NOTE: Finish work on the following objective. - Specify mechanisms for Relay and Remote UE authorization for L3 and L2 relaying [RAN3] NOTE: Continue work on the following lobjective. - Specify Control Plane procedures for U2N, including RRC connection management, system information delivery, paging mechanism and access control for Remote UE [RAN2, RAN3] |
|  | RAN3#115 | 0.5 | NOTE: Finish work on the following objective. 6. Specify Control Plane procedures for U2N, including RRC connection management, system information delivery, paging mechanism and access control for Remote UE [RAN2, RAN3] |

Reference

- 3GPP RP-RP-210904 " WID on NR sidelink relay".