3GPP TSG-RAN WG2 Meeting #119 electronic                                              R2-2207282

Online, August 15 – 26, 2022

Agenda item: 		8.12.1

Source: 		Qualcomm Incorporated (WI Rapporteur)

Title: 	Workplan for Rel-18 mobile IAB

Document for:	Information

# 1	Introduction

At RAN#94e, the Work Item on Mobile IAB (Integrated Access and Backhaul) for NR (NR_mobile_IAB) was agreed [1]. As WI Rapporteur, in this contribution, we recommend a work plan for RAN2, RAN3 and RAN4. The workplan captures interdependences among tasks and timeline for RAN2/3/4.

The WID [1] introduced the following objectives in the core part:

The detailed objectives of the WI are listed as follows: - Define Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration) [RAN3, RAN2] - Enhancements for mobility of an IAB-node together with its served UEs, including aspects related to group mobility. No optimizations for the targeting of surrounding UEs. [RAN3, RAN2] Note: Solutions should avoid touching upon topics where Rel-17 discussions already occurred and where the topic was excluded from Rel-17, except for enhancements that are specific to IAB-node mobility. - Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g. PCI, RACH). [RAN3, RAN2] Note: At the beginning of the work period, RAN3, RAN2 should discuss the potential complexity of a scenario where a mobile IAB node connects to a stationary (intermediate) IAB node, with respect to the scenario where a mobile IAB node connects directly to an IAB-donor. The following principles should be respected: - Mobile IAB-nodes should be able to serve legacy UEs. - Solutions providing optimization for Mobile IAB may entail Rel-18 UE enhancements, provided that such enhancements are backwards compatible RAN4 is expected to study impact on RF and RRM requirements: - Conduct co-existence study to assess the impact of moving cells. Based on the study outcome, specify RF and RRM requirements and mechanisms for the mobile IAB-node to enable co-existence, if needed. - Specify RRM requirements for the mobile IAB-node to enable IAB-node mobility, if needed. The involvement of RAN1 may be needed, depending on work progress.

The WID [1] introduced the following objectives in the performance part:

- Specify RF conformance requirements for the mobile IAB-node, if needed. - Specify RRM and demodulation performance requirements for the mobile IAB-node by taking into account IAB-node mobility, if needed.

The WID further emphasizes on interaction with SA2:

- Alignment and coordination with Rel-18 SA2 work on VMR should be considered, if needed.

# 2	Workplan

## 2.1	Prioritization of efforts

This section captures prioritization of the various tasks defined as well as interdependences among these tasks handled by different RAN WGs.

RAN3/2-related efforts:

- Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration):

This objective primarily focuses on the migration of the mobile IAB-node. The following topics should be considered:

  - Inter-donor migration of the entire IAB-node (full migration): RAN3 can be expected to take the lead in this effort. RAN3 can continue the discussion on full migration started in Rel-17. Since this discussion is expected to have impact on RAN2 and potentially also RAN1 and RAN4, RAN3 should start with this effort in the first meeting. RAN2 and potentially other RAN WGs may wait for RAN3 progress on this topic.

  - Other new procedures or enhancements to existing procedures related to this objective can be defined by RAN3 and RAN2. New procedures should be identified at the beginning of the WI since such work typically takes significant time and may further affect other RAN WGs. As always, new functionality that is necessary to support IAB-node mobility should be given higher priority than optimizations to existing functionality.

  - Topology adaptation in absence of Xn was identified in Rel-18 SA2 Study on VMR as part of key issue #3. RAN3 may want to consider discussing the relevance of this issue for RAN independent of SA2’s effort. This discussion should start early in case interaction with SA2 is necessary.

- Enhancements needed for the mobility of an IAB-node together with its served UEs, including aspects related to group mobility:

This objective primarily focuses on the impact on the UE connected to or camping on a mobile IAB-node cell. It can also include handover to and/or reselection of a mobile IAB-node cell. The objective allows for enhancements in a variety of areas; a few of them are given below. The discussion should include the consideration of the support for legacy UEs. RAN2 and RAN3 should identify the enhancements to be handled in Rel-18 at the beginning of the WI so that sufficient time remains for thorough discussion. In this discussion, the definition of new functionality should be given priority over optimizations. For new procedures, optimizations should only be considered after a baseline has been defined.

The following areas may be explored by RAN2 and RAN3:

  - Enhancements to cell (re-)selection between stationary network and mobile IAB-node, and between mobile IAB-nodes.

  - Enhancements to UE access to the mobile IAB-node vs. the stationary network.

  - Enhancements to UE handover between stationary network and mobile IAB-node and between mobile IAB-nodes.

  - Enhancements for location updates (TA, RNA) for UEs that are camping on or connected to mobile IAB-node cells. This issue was identified in Rel-18 SA2 Study on VMR as key issues #5 and #6. RAN3 and RAN2 may want to consider discussing the relevance of this issue for RAN independently of SA2’s effort.

  - Signalling optimizations due to collective migration of UEs connected to a mobile IAB-node. This may include the bundling of UE-associated information into one common message. RAN3 should consider optimizations of this nature at a later stage of the WI after the baseline procedures (i.e., w/o such bundling) have been established.

- Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g., PCI, RACH):

The following topics may be explored under this objective:

  - PCI collision avoidance: RAN3 may discuss means for PCI collision avoidance. RAN2 may discuss potential means for PCI collision detection.

  - RACH resource collision avoidance: RAN2 may discuss potential issues related to this topic.

  - Other issues related to interference mitigation may be identified and discussed in RAN2 and RAN3.

- Note on potential complexity related to multi-hop backhauling for mobile IAB:

  - Aspects of the potential complexity related to multi-hop backhauling should be briefly discussed at the beginning of the WI in RAN2 and RAN3.

RAN4-related efforts (Core Part):

- Co-existence study to assess the impact of moving cells.

  - The co-existence criteria defined in Rel-16/17 only apply to stationary IAB-nodes, and they were based on a specific minimum distance between IAB-nodes and macro-cell. For mobile IAB-nodes, the assumption on the minimum distance and the implications on power control, receiver dynamic range, etc. need to be revised. RAN4 may need to consider if additional simulation work is needed. These topics should be discussed early during the RAN4 effort since they are expected to consume a lot of time.

- RRM requirements for the mobile IAB-node to enable IAB-node mobility.

  - RRM requirements defined in Rel-16/17 only included RLF recovery. For mobile IAB, the IAB-node is expected to undergo frequent topology adaptations. The associated RRM requirements need to be discussed. This discussion should include identification of the relevant mobile IAB scenarios. The prior RAN work on high-speed trains should be included into these considerations. These topics should be discussed early since they are expected to consume a lot of time.

RAN4-led efforts (Performance Part):

- The topics related to the performance part need to be handled based on the progress of the discussion on the Core Part.

Alignment and coordination with Rel-18 SA2 work on VMR

- RAN WGs should try to align efforts on mobile IAB with SA2 normative work on VMR if such normative work is agreed by SA2. It is expected that such alignment will be discussed by TSG RAN before.

- RAN WGs may want to include into the discussion all aspects related to the key issues identified by the SA2 Study on VMR that have RAN impact and are aligned with the RAN WI objectives. The above outline has captured some aspects that might be considered.

## 2.2	Timeline

Table 1 summarizes a timeline for RAN2/3/4. This timeline is based on RP-221060 [2].

Table 1: Timeline for RAN2, 3, 4 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | #119e | Aug 2022 | 0.5 | In the first meeting, RAN2 should aim to identify and converge on the topics and enhancements to be handled in Rel-18. AI 8.12.2: Enhancements for the mobility of an IAB-node together with its served UEs, including aspects related to group mobility. This objective primarily focuses on the impact on the UE connected to or camping on a mobile IAB-node. - Identify and converge on enhancements related to this objective that are in RAN2 scope and should be handled in Rel-18. - This may include enhancements related to: - Cell (re-)selection between mobile IAB-node and stationary RAN or between mobile-IAB-nodes. - Cell access to mobile IAB-node. - Handover between mobile IAB-node and stationary RAN or between mobile-IAB-nodes. - Location updates for UEs camping on or connected to mobile IAB-node. - Others. AI 8.12.3: Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration) This objective primarily focuses on the migration of the mobile IAB-node. - Identify and converge on enhancements to existing procedures related to this objective that are in RAN2 scope and should be handled in Rel-18. - This may include: - Enhancements related to the mobility of the IAB-node - Consideration of DAPS for BH or CHO enhancements Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g. PCI, RACH) - Identify and converge on enhancements related to this objective that are in RAN2 scope and should be handled in Rel-18. - This may include enhancements related to: - PCI collision detection - RACH resource collision avoidance - Others. Potential complexity of multi-hop backhauling - RAN2-related aspects related of this topic should be discussed. |
| RAN3 | #117e | Aug 2022 | 1.0 | In the first meeting, RAN3 should aim to identify and converge on the topics and enhancements to be handled in Rel-18. AI 13.2: Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration) This objective primarily focuses on the migration of the mobile IAB-node. - Continue the discussion on the functionality needed for full migration started during Rel-17. - Identify and converge on other enhancements related to this objective that are in RAN3-scope and should be supported during Rel-18. - Discuss if topology adaptation in absence of Xn should be supported in Rel-18, and, if applicable, converge on the necessary enhancements. AI 13.3: Enhancements for the mobility of an IAB-node together with its served UEs, including aspects related to group mobility. This objective primarily focuses on the impact on the UE connected to or camping on a mobile IAB-node. - Identify and converge on enhancements related to this objective that are in RAN3 scope and should be handled in Rel-18. - This may include enhancements related to: - Handover between mobile IAB-node and stationary RAN or between mobile-IAB-nodes, including aspects of group mobility. - Location updates for UEs camping on or connected to mobile IAB-node. - Others. AI 13.4: Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g. PCI, RACH) - Identify and converge on enhancements related to this objective that are in RAN3 scope and should be handled in Rel-18. - This may include enhancements related to: - PCI reconfiguration, dynamic PCI change of mobile IAB-node, etc. - Others. AI 13.1: Potential complexity of multi-hop backhauling - RAN3-related aspects related of this topic should be discussed. |
| RAN | #97 | Sept 2022 |  |  |
| RAN2 | #119bis-e | Oct 2022 | 0.5 | Discuss technical issues of enhancements to be handled in Rel-18. |
| RAN3 | #117bis-e | Oct 2022 | 1.5 | Discuss technical issues of enhancements to be handled in Rel-18. |
| RAN2 | #120 | Nov 2022 | 0.5 | Continue discussion |
| RAN3 | #118 | Nov 2022 | 1.5 | Continue discussion |
| RAN | #98 | Dec 2022 |  |  |
| RAN2 | #121 | Feb 2023 | 0.5 | Continue discussion |
| RAN3 | #119 | Feb 2023 | 1 | Continue discussion |
| RAN4RF | #106 | Feb 2023 | 0.25 | TBD |
| RAN4RD | #106 | Feb 2023 | 0.25 | TBD |
| RAN | #99 | March 2023 |  |  |
| RAN2 | #121bis | April 2023 | 0.5 | Continue discussion |
| RAN3 | #119bis | April 2023 | 1.5 | Continue discussion |
| RAN4RF | #106bis | April 2023 | 0.5 |  |
| RAN4RD | #106bis | April 2023 | 0.5 |  |
| RAN2 | #122 | May 2023 | 0.5 | Continue discussion |
| RAN3 | #120 | May 2023 | 1.5 | Continue discussion |
| RAN4RF | #107 | May 2023 | 0.5 |  |
| RAN4RD | #107 | May 2023 | 0.5 |  |
| RAN | #100 | June 2023 |  |  |
| RAN2 | #123 | Aug 2023 | 0.5 | Continue discussion |
| RAN3 | #121 | Aug 2023 | 1.0 | Continue discussion |
| RAN4RF | #108 | Aug 2023 | 0.5 |  |
| RAN4RD | #108 | Aug 2023 | 0.5 |  |
| RAN | #101 | Sept 2023 |  |  |
| RAN2 | #123bis | Oct 2023 | 0.5 | Finalize St2 discussion |
| RAN3 | #121bis | Oct 2023 | 1.5 | Finalize St2 discussion |
| RAN4RF | #108bis | Oct 2023 | 0.5 |  |
| RAN4RD | #108bis | Oct 2023 | 0.5 |  |
| RAN2 | #124 | Nov 2023 | 0.5 | Finalize St3 discussion |
| RAN3 | #122 | Nov 2023 | 1.5 | Finalize St3 discussion |
| RAN4RF | #109 | Nov 2023 | 0.5+0.25 | Finalize discussion on Core Part. Start discussion on Performance part. |
| RAN4RD | #109 | Nov 2023 | 0.5+0.25 | Finalize discussion on Core Part. Start discussion on Performance part. |
| RAN | #102 | Dec 2023 |  | Functional freeze |

# References

- RP-221815: Revised WID for NR_mobile_IAB; TSG RAN Meeting #96, Budapest, Hungary, June 6 - 9, 2022

- RP-221060: Draft Status of TU RAN1 to 4 after RAN#96 v01, Budapest, Hungary, June 6 - 9, 2022