3GPP TSG-RAN WG2 Meeting #119bis-e		R2-2210500

Online, October 10 – 19, 2022

Agenda Item:	8.4.1

Source: 	MediaTek Inc., Apple

Title:  	RAN2 Work Plan for Rel-18 Further NR Mobility Enhancements WI

Document for:	Information

# Introduction

In last RAN2 meeting, we presented a RAN2 work plan [1]. The plan was marked as “noted (need improvement)”, due to companies’ concerns, mainly about the scenario of inter-DU for L1/L2-based inter-cell mobility. It was then clarified in the meeting that L1/L2-based inter-cell mobility is supported for both intra-DU and inter-DU scenarios.

Confirm to Support L1/L2-based inter-cell mobility for inter-DU scenario (as well as intra-DU scenarios). The design for intra-DU and inter-DU L1/L2-based mobility should share as much commonality as reasonable. FFS which aspects need to be different.

We also conclude on a time chart showing common understanding about the components of mobility latency and interruption. The time chart is captured in TS 38.300 running CR [2].

Moreover, in RAN#97-e meeting, the WI of Further NR mobility enhancements was revised [3]. Now Objective 3 does not need RAN2 involvement.

- To specify mechanism and procedures of L1/L2 based inter-cell mobility for mobility latency reduction: - Configuration and maintenance for multiple candidate cells to allow fast application of configurations for candidate cells [RAN2, RAN3] - Dynamic switch mechanism among candidate serving cells (including SpCell and SCell) for the potential applicable scenarios based on L1/L2 signalling [RAN2, RAN1] - L1 enhancements for inter-cell beam management, including L1 measurement and reporting, and beam indication [RAN1, RAN2] - Note 1: Early RAN2 involvement is necessary, including the possibility of further clarifying the interaction between this bullet with the previous bullet - Timing Advance management [RAN1, RAN2] - CU-DU interface signaling to support L1/L2 mobility, if needed [RAN3] Note 2: FR2 specific enhancements are not precluded, if any. Note 3: The procedure of L1/L2 based inter-cell mobility are applicable to the following scenarios: - Standalone, CA and NR-DC case with serving cell change within one CG - Intra-DU case and intra-CU inter-DU case (applicable for Standalone and CA: no new RAN interfaces are expected) - Both intra-frequency and inter-frequency - Both FR1 and FR2 - Source and target cells may be synchronized or non-synchronized - To specify mechanism and procedures of NR-DC with selective activation of the cell groups (at least for SCG) via L3 enhancements: - To allow subsequent cell group change after changing CG without reconfiguration and re-initiation of CPC/CPA [RAN2, RAN3, RAN4] Note 4: A harmonized RRC modelling approach for objectives 1 and 2 could be considered to minimize the workload in RAN2. - To specify data forwarding optimizations for CHO including target MCG and target SCG in NR-DC [RAN3]. - To specify CHO including target MCG and candidate SCGs for CPC/CPA in NR-DC [RAN3, RAN2] - CHO including target MCG and target SCG is used as the baseline - To specify RRM core requirements for the following, as necessary [RAN4]: - L1/L2-based inter-cell mobility - Enhanced CHO configurations addressed by this WI - To specify RF requirements to cover inter-frequency L1/L2-based mobility, as necessary [RAN4]. - To study the following, with completion targeted by RAN#98 meeting [RAN4]: - The impact of FR2 RRM mobility measurement acquisition and reporting on FR2 SCell/SCG setup/resume delay for a UE connecting from idle/inactive mode. - The level of feasible improvement in FR2 SCell/SCG setup delay from defining new UE measurement procedures and RRM core requirements, and whether additional information from the network would help the UE to perform those measurements effectively. The following sequence of events should be assumed. - The UE initiates and performs improved measurements when it requests RRC connection setup/resume. - After acquiring those improved measurements, the UE subsequently reports those measurements to the network to support SCell/SCG setup.

In this contribution, we provide revised RAN2 work plan for the WI, in accordance with the above progress and changes.

# Work plan

We propose the following work plan.

| Month | Meeting# | #TU | Work plan |
| --- | --- | --- | --- |
| August 2022 | RAN2#119-e | 2 | - Work plan approval L1/L2 inter-cell mobility: - Investigate target performance enhancements, by establishing a latency model and determine which parts of latency / step are expected to be enhanced with the new L1/L2-based method. - Evaluate mobility performance with reduced latency. - Discuss the scenarios to be supported (e.g., inter-DU/ inter-frequency/ CA/ DC). - Identify candidate solutions for mobility latency reduction. Identify baseline working directions and inform other WGs. L3 enhancements: - Clarify the scenarios to be supported in Rel-18 - Investigate potential RRC impacts for CHO/CPC/CPA enhancements to support selective CG activation and CHO with (one or multiple) candidate SCGs |
|  | RAN3#117 | 1 | - Work Plan approval L1/L2 inter-cell mobility: - Investigate potential impacts for CU/DU to support candidate cells configuration in L1/L2 mobility - Investigate the need of CU-DU interface signalling to support L1/L2 mobility L3 enhancements: - Clarify the scenarios to be supported in Rel-18 - Investigate potential procedural impacts (e.g., configuration, initiation, data forwarding) for selective CG activation and CHO with candidate SCGs |
|  | R4-104 | 0.5 (RD) | - Work plan approval - Investigate FR2 SCell/SCG setup delay improvement and potential impacts on requirements - Investigate potential impacts on requirements for inter-frequency L1-RSRP inter-cell BM |
| October 2022 | RAN1#110bis | 1 | - Work plan approval - Investigate the applicability of Rel-17 inter-cell beam management (ICBM) to scenario with mobility support, and potential enhancements - Investigate potential enhancements for TA management |
|  | RAN2#119bis | 2 | L1/L2 inter-cell mobility: - Continue to investigate target performance enhancements based on the latency model and determine which parts of latency / step are expected to be enhanced with the new L1/L2-based method. - Discuss RRC modelling for candidate cells - Discuss dynamic switch procedures for intra-DU/inter-DU mobility - Discuss the inter-frequency mobility scenarios to support - Identify potential enhancements for TA management. L3 enhancements: - Confirm enhancement scenarios to be supported in Rel-18 and identify RRC impacts |
|  | RAN3#117bis | 1 | L1/L2 inter-cell mobility: - Identify required changes to support candidate cells for L1/L2 mobility, considering RAN2 progress L3 enhancements: - Identify procedural impacts of NR-DC with selective activation of the cell groups - Identify data forwarding optimizations and other potential enhancements for CHO including target MCG and target SCG. - Identify procedural impacts for CHO including target MCG and candidate SCGs |
|  | RAN4#104bis | 0.5 (RD) | - Continue discussion on FR2 SCell/SCG setup delay improvement and inter-frequency L1-RSRP inter-cell BM - Investigate potential impacts on requirements for L1/L2-based mobility - Investigate potential impacts on requirements for L3 mobility enhancements |
| November 2022 | RAN1#111 | 1 | - List the changes needed for ICBM to support mobility - Conclusion on the solutions for TA management |
|  | RAN2#120 | 2 | L1/L2 inter-cell mobility: - Conclude which parts of latency / step are expected to be enhanced with the new L1/L2-based method. - Conclude on candidate cells RRC modelling - Conclude the dynamic switch procedures - Refine enhancements for TA management L3 enhancements: - Discuss RRC modelling and procedures for selective CG activation - Discuss the procedures for CHO including target MCG and candidate SCGs |
|  | RAN3#118 | 1 | L1/L2 inter-cell mobility: - Discuss on new signalling and procedures to support L1/L2 mobility L3 enhancements: - Discuss the procedures for selective CG activation - Discuss the procedures for CHO including target MCG and target/candidate SCGs |
|  | RAN4#105 | 0.5 (RD) | - Conclude on FR2 SCell/SCG setup delay - Discuss remaining issues on RRM requirements |
| February 2023 | RAN1#112 | 1 | - Confirm the L1 enhancements for inter-cell beam management, including L1 measurement and reporting, and beam indication, considering the RRC modelling and dynamic switch procedure defined by RAN2 - Start stage-3 discussions |
|  | RAN2#121 | 2 | L1/L2 inter-cell mobility: - Confirm overall procedures of L1/L2-based inter-cell mobility - Discuss the need of harmonization with candidate cells in L3 mobility L3 enhancements: - Procedure of selective SCG activation - Procedure of CHO with target MCG and candidate SCGs |
|  | RAN3#119 | 1 | L1/L2 inter-cell mobility: - Conclusion on new signaling and procedures to support L1/L2 mobility L3 enhancements: - Conclusion on the procedures for selective CG activation - Conclusion on the procedures for CHO including targe MCG and target/candidate SCGs |
|  | RAN4#106 | 0.25/1 (RF/RD) | - Discuss remaining issues on RRM requirements - Work split on draft CRs |
| April 2023 | RAN1#112bis | 1 | - Stage-3 discussion on solution details |
|  | RAN2#121bis | 2 | L1/L2 inter-cell mobility: - Identify required L2/3 support for inter-cell beam management and TA management, based on solution determined by RAN1 and RAN3 L3 enhancements: - Conclusion on the procedures |
|  | RAN3#119bis | 1 | - Conclusion on the remaining issues about the solutions, considering RAN1 &RAN2 inputs |
|  | RAN4#106bis | 0.5/1.5 (RF/RD) | - Discuss remaining issues on RRM requirements - Provide draft CRs |
|  | RAN1#113 | 1 | - Stage-3 discussion on solution details |
|  | RAN2#122 | 2 | - Start stage-2 discussion on solution details - Conclusion on the remaining issues about the solutions, if any |
|  | RAN3#120 | 1 | - Start Stage-2 discussion on solution details |
|  | RAN4#107 | 0.5/1.5 (RF/RD) | - Discuss remaining issues on RRM requirements - Approve the CRs |
|  | RAN1#114 | 1 | - Finalization of Stage-3 works - Approve corresponding CRs - RRC parameter list |
| 2023 Q3 | RAN2#123 | 2 | - Continue stage-2 discussion - Start Stage 3 discussion on solution details |
|  | RAN3#121 | 1 | - Continue stage-2 discussion - Start Stage 3 discussion on solution details |
|  | RAN4#108 | 0.5/1.5 (RF/RD) | - Discuss and decide test case list and related parameters - Work split on test cases |
| 2023 Q4 | RAN2#123bis | 2 | - Stage-3 works |
|  | RAN3#121bis | 1 | - Stage-3 works |
|  | RAN4#108bis | 0.25/1.5 (RF/RD) | - Discuss test cases for RRM |
|  | RAN2#124 | 2 | - Finalization of Stage-3 works - Approve corresponding CRs |
|  | RAN3#122 | 1 | - Finalization of Stage-3 work - Approve corresponding CRs |
|  | RAN4#109 | 0.25/1.5 (RF/RD) | - Discuss test cases for RRM |

We propose that RAN2 endorse the above work plan.

Proposal 1:	RAN2 endorses the above work plan.

# Conclusion

It is proposed to discuss and decide on the following proposals:

Proposal 1:	RAN2 endorses the above work plan.

# Reference

- R2-2206981, RAN2 Work Plan for Rel-18 Further NR Mobility Enhancements WI, MediaTek Inc., Apple, August 2022

- R2-2209255, 38.300 running CR for introduction of NR further mobility enhancements, MediaTek Inc, Aug. 2022

- RP-222332, “Revised WID: Further NR mobility enhancements,” MediaTek, September 2022