3GPP TSG-RAN WG2 Meeting #98	R2-1709558

Berlin, Germany, 21 - 25 August 2017

Agenda item:	9.8.1

Source:	Nokia, Nokia Shanghai Bell

Title:	Updated work plan for UE Positioning Accuracy Enhancements for LTE work item

WID/SID:	LCS_LTE_acc_enh-Core - Release 15

Document for:	Discussion and Decision

# 1	Introduction

This paper provides an updated work plan for the Release 15 work item “UE Positioning Accuracy Enhancements for LTE”.

# 2	Background

A Release 15 work item “UE Positioning Accuracy Enhancements for LTE” [2] was approved in RAN#75. In RAN#76 this work item was updated [3] where the UE-based OTDOA objective was down prioritized as a second priority objective. Also, the completion date for the work item was updated from Dec 2017 to June 2018. The following is the updated set of objectives with changes highlighted in red text:

- GNSS positioning enhancements: - Specify the signalling and procedure to support RTK GNSS positioning over LPP and LPPa, taking into account both UE and network complexity. [RAN2, RAN3, RAN1] - Specify support for IMU positioning: - Specify the signalling and procedure to support IMU positioning over LPP and hybrid positioning including IMU related estimates. [RAN2, RAN1] - As second priority, specify the signalling and procedure to support UE-based OTDOA positioning [RAN2] - Broadcasting of assistance data [RAN2, RAN3, SA3, SA2] - Specify a new SIB to support signalling of positioning assistance information for A-GNSS, RTK and UE-based OTDOA assistance information. - Specify optional encryption procedure for broadcast assistance data, including mechanism for delivery of UE-specific encryption keys.

Due to changes to the work item objectives and completion date, an updated work plan is being provided here under clause 3. Status of completed tasks are also provided.

# 3	Discussion

## 3.1	Work plan and task break down per RAN WG

Following table details the work plan in terms of tasks for different RAN WG. It also shows the time line and planned allocation of time units for each meeting.

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | 98 | MAY 2017 | 1 | Agreements: - Correction data (for RTK GNSS) is provided by ESMLC. RAN2 will not discuss how ESMLC gets this data in 3GPP - LS sent to SA3 on the provision of an encryption solution for broadcast positioning information - Support both UE based and UE assisted modes for RTK GNSS. How to support them is FFS |
| RAN | 76 | JUN 2017 | - | Agreements: - WID updated in RP-171508 - UE based OTDOA is down prioritized as a 2nd priority objective |
| RAN1 | 90 | AUG 2017 | 0.5 | - Investigate any measurements to be defined for RTK GNSS, IMU positioning |
| RAN2 | 99 | AUG 2017 | 1 | - Discuss whether correction data is signalled transparently in the SIB and LPPa message and whether it is signalled using unicast LPP signalling - Discuss whether SSR representation of correction data and which RTK techniques are to be supported in Rel-15, especially PPP-RTK - Discuss details of carrier phase measurement (accumulated delta range) reporting which is already supported in LPP protocol - Liaise with RAN1 for any measurement requirements - Liaise with RAN3 to request investigation of LPPa impacts for RTK GNSS - Discuss encrypted broadcast for RTK GNSS if reply LS received from SA3 - Discuss use cases for IMU positioning and need for reporting raw sensor data to E-SMLC if time permits - Discuss broadcast assistance data support if time permits |
| RAN | 77 | SEP 2017 | - | - Discuss WI progress/status and any required updates to WID |
| RAN1 | 90bis | OCT 2017 | 0.5 | - Finalize any specification work for measurements to be defined in 36.214 for RTK GNSS, IMU positioning |
| RAN2 | 99bis | OCT 2017 | 1 | - Progress leftover items for RTK GNSS - Discuss IMU positioning, broadcast assistance data support, encrypted broadcast assistance data |
| RAN3 | 97bis | OCT 2017 | 0.5 | - Address any issues/work identified (via LS) for RAN3 by RAN2 - Investigate LPPa impacts for RTK GNSS and prepare CRs for 36.455 |
| RAN4 | 84bis | OCT 2017 | 0.5 | - Address any issues/work identified (via LS) for RAN4 by RAN1/RAN2 - Investigate core requirements work to be done for RTK GNSS |
| RAN2 | 100 | NOV 2017 | 1 | - Start creating running stage 2 (36.305) and stage 3 (36.355) CRs for RTK GNSS, IMU, and stage 3 (36.331) for broadcast assistance data |
| RAN3 | 98 | NOV 2017 | 0.5 | - Finalize specification work for RTK GNSS in 36.455 |
| RAN4 | 85 | NOV 2017 | 0.5 | - Continue discussions on core requirements for RTK GNSS positioning |
| RAN | 78 | DEC 2017 | - | - Discuss WI progress/status and any required updates to WID |
| RAN1 | 92 | FEB 2018 | - |  |
| RAN2 | 101 | FEB 2018 | 1 | - Continue working on stage 2 (36.305) and stage 3 (36.355) CRs for RTK GNSS, IMU, and stage 3 (36.331) for broadcast assistance data - Finalize stage 2 decisions for IMU positioning |
| RAN3 | 99 | FEB 2018 | - |  |
| RAN4 | 86 | FEB 2018 | 0.5 | - Continue discussions on core and performance requirements for RTK GNSS positioning |
| RAN | 79 | MAR 2018 |  | - Discuss WI progress/status and any required updates to WID |
| RAN1 | 92bis | APR 2018 | - |  |
| RAN2 | 101bis | APR 2018 | 1 | - Finalize running CR on 36.305, 36.355, 36.331 and agree in-principle - Discuss and decide UE-based OTDOA positioning support |
| RAN3 | 99bis | APR 2018 | - |  |
| RAN4 | 86bis | APR 2018 | 0.5 | - Continue discussions on core and performance requirements for RTK GNSS positioning |
| RAN1 | 93 | MAY 2018 | - |  |
| RAN2 | 102 | MAY 2018 | 1 | - Agree CRs to 36.305, 36.355, 36.331 |
| RAN3 | 100 | MAY 2018 | - |  |
| RAN4 | 87 | MAY 2018 | 0.5 | - Finalize discussions on core and performance requirements for RTK GNSS positioning |
| RAN | 80 | JUN 2018 |  | - Approve CRs to RAN1/RAN2/RAN3/RAN4 core specifications |

# 4	Conclusion

This paper provided an updated work plan for completion of the work item per the new schedule agreed in RAN#76.

# References

- 3GPP TS 21.801 Drafting Rules

- RP-170813 UE Positioning Accuracy Enhancements for LTE – 3GPP Work Item Description

- RP-171508 UE Positioning Accuracy Enhancements for LTE – 3GPP Work Item Description