## TP
# | Title | NRPPa | F1 | Status | Comment
1 | SRS Type criticality | 9.1.1.d1 |  |  | Nok - There should be an “M” in the Presence column for SRS type HW- we propose to remove E///- added "M" presence
2 | Typo | 9.1.x.1 |  |  | Nok - ENUMERTATED => ENUMERATED HW - Capture in update uploaded
3 | Typo | 9.1.x.4 |  |  | Nok - 65535 => 655365 HW - fine for us we can prooceed with it in next update E/// - you mean 65536?
4 | SFN Initialisation | 9.2.bb |  |  | Nok - For the SFN Initialisation Time IE, I suggest creating a dedicated IE for it since it is used in several different places and it would be preferable to avoid the lengthy semantics description in multiple places (i.e. create a section “9.2.y5 SFN Initialisation Time”) HW - fine for us we can prooceed with it in next update E/// - done. Wondering if Activation Time for SRS in 9.2.y4 is the same or if it should be differentiated
5 | Criticality and Assigned Criticality columns are not needed in Requested SRS Transmission Characteristics | 9.2.x |  |  | Nok - Criticality and Assigned Criticality columns are not needed HW - Criticality is motivated by container, which is not need but it is fine, if strong view we can correct both E/// - removed.
6 |  | 9.2.y: Refer to “9.2.y5 SFN Initialisation Time” |  |  | Nok - ENUMERTATED => ENUMERATED HW - Capture in update uploaded
7 | Refer to “9.2.y5 SFN Initialisation Time” | 9.2.y4 |  |  | Nok - Refer to “9.2.y5 SFN Initialisation Time” HW - related to 2? More clarification needed E/// -it should be clarified whether the Activation Time for SRS in 9.2.y4 is the same as SFN Initi Time
8 | Editorial | 9.2.z12 |  |  | Nok - : Remove the “1” in the Range column for PRS Information and SSB Information (which should be in italics rather than bold) HW - Capture in update uploaded, please note the editorial convention for choice is not clear and consistant
9 | Refer to “9.2.y5 SFN Initialisation Tim | 9.2.z13 |  |  | Nok - ENUMERTATED => ENUMERATED HW - linked to 2?
10 | Editorial | 9.2.xx1 |  |  | Nok - In the IE type column, there are many editorial issues with the INTEGER type (the commas should all be deleted) HW - Capture in update uploaded
11 | Blank IE SRS configuration | 9.2.y | 9.3.1.o |  | HW - propose same coding as R3-203599, for SRS configuration, draft updated E/// - corrected IE reference of SRS Resource and Positioning SRS resource IEs in 9.2.y
12 | Blank IE Measurement Result | 9.2.z1 | 9.3.1.a |  | HW- They are associated IEs e.g. NRPPa 9.2.z, 9.2.z10, 9.2.z3, 9.2.z4 HW - propose same coding as R3-203599HW- E///: there is FFS on max no of measurement?
13 | Blank IE PRS Configuration | 9.2.z6 | 9.3.1.f |  | HW - propose same coding as R3-203599, for SRS configuration, draft updated E/// - corrected IE reference of SRS Resource and Positioning SRS resource IEs in 9.2.y
14 | Blank IE SSB configuration | 9.2.z7 |  |  | HW - we propose a reference to TF configuration E/// - corrected typo SBB => SSB and IE reference
15 | SRS Spatial relation definition | 9.2.y2 | 9.3.1.h |  | HW - We do not think CSI-RS is needed, but OK to keep it considering tight schedule. Suggest to remove SRS (Spatial relation) as the spatial relation can be general, and we do not keep SRS relation information.we can proceed with change if no objection
16 | Spatial relation Information definition | 9.2.z12 |  |  | HW- ok remove the IE see above; we can proceed with change if no objection
17 | Spatial relation Information definition | x |  |  | HW _ IE can be removed see above: ; we can proceed with change if no objection
18 | SRS Type Indication | 9.2.x |  |  | HW -After further check we are fine to remove IE
19 | Several non-UE associated messages have UE IDs and lack Transaction ID |  | x |  | QC - let rapprteur manage the issue HW - fine with QC to let rapporteur to manage it
20 | Several UE-associated messages lack UE IDs |  | x |  | QC - let rapprteur manage the issue HW - fine with QC to let rapporteur to manage it
21 | Lot of otional IES does not have text procedure | x | x |  | HW- could be cover as correction next quarter
22 | Various FFS and safty warning | x | x |  | HW - could be removed unless sporting a dedicated issue
23 | UE associated meansurement FFS | 8.2.x.1 |  |  | HW - remove it
24 | Spatial Direction Information | 9.2.z8 |  |  | HW - remove it It is already covered by NR-PRS Beam Information (9.2.xx1)
25 | Additional Path List | 9.2.z11 |  |  | HW - propose same coding as R3-203599, for SRS configuration, draft updated, we propose a path delay value
26 | A-SRS | x |  |  | HW we propoe to introduce the SRS Resource Trigger as choice extendable to better cover the neigbourg aspects
27 | Access point location | 9.3.1.b |  |  | HW - we assume QC need check ASN fexibility
28 | NR-PRS Beam Information | 9.2.xx1 | 9.3.1.q |  | HW range and optionality of the list need to be check, unless issue clarify remove FFS HW - alignment F1 on NRPPA for the Maximum value
29 | maxnoofmeas is FFS | 9.2.z1 | 9.3.1.a |  | HW -6/17- the "maxnoofmeas" is FFS, can be 64

## ASN
1) In MeasurementUpdate-IEs, id-LMF-UE-Measurement-ID => id-LMF-Measurement-ID
2) In TRPInformationRequest-IEs, TRP List is missing (mismatch with tabular)
3) In PositioningActivationRequestIEs, for ActivationTime the criticality and presence are misaligned with the tabular
4) In SemipersistentSRS, the presence for sRSSpatialRelation is misaligned with the tabular
5) In RequestedSRSTransmissionCharacteristics, there is no need to use the extension container.