3GPP TSG RAN3 meeting #117bis-e			                                      R3-225836

10th Oct – 18th Oct 2022 Online

Agenda item: 	    11.1

Source: 	China Unicom (WI Rapporteur)

Title: 	Update Workplan for Rel-18 NR QoE Enhancement

Document for:	Information

1	Introduction

At RAN#96, the revised Work Item on NR QoE enhancement was agreed [1]. As WI Rapporteur, in this contribution, we recommend a work plan for RAN2 and RAN3. The workplan captures dependencies among tasks and timeline for RAN2/3.

The WID [1] introduced the following objectives in the core part:

The detailed objectives of the WI are listed as follows: - Support for new service type, such as AR, MR, MBS and other new service type defined or to be supported by SA4. Support RAN-visible parameters for the additional service types, and the existing service if needed, and the coordination with SA4 is needed [RAN3, RAN2]. - Specify the new service and the existing service defined or to be supported by SA4, combined with high mobility scenarios, e.g., High Speed Trains. - Specify for QoE measurement configuration and collection in RRC_INACTIVE and RRC_IDLE states for MBS, at least for broadcast service [RAN3, RAN2]. - Specify the mechanism to support the alignment of the existing radio related measurement and QoE reporting. - Specify to support for QoE in NR-DC, e.g. enable QoE reporting via SN [RAN3, RAN2]. - Specify the QoE configuration, and measurement reporting over MN/SN for NR-DC architecture, and specify the QoE measurement reporting over the other DC leg in order to maintain the reporting continuity. Note 1: The QoE measurements are not performed separately for each leg. - Support RAN-visible QoE and radio related measurement configuration and reporting in NR-DC scenarios. - Specify the QoE measurement continuity in mobility scenarios in NR-DC. - Specify the alignment of QoE measurements (including legacy QoE and RAN visible QoE measurements) and radio related measurement in NR-DC. - Left-over features from Rel-17, as well as the enhancements of existing features which are not included in Rel-17 normative phase, should be supported in Rel-18 if consensus on benefits are reached [RAN3, RAN2]. - Specify per-slice QoE measurement configuration enhancement. - Specify RAN visible QoE enhancements for QoE value, RAN visible QoE trigger event, RAN visible QoE Report over F1. - Specify QoE reporting handling enhancement for overload scenario. - Support the continuity of legacy QoE measurement job for streaming and MTSI service during intra-5GC inter-RAT handover process [RAN2, RAN3]. Note 2: If needed, co-operate with other working groups, e.g. SA4/SA5/SA2/CT1. Note 3: Radio related measurement reporting should be specified in the SON/MDT WI. Note 4: When the support for QMC in NR-DC is completed, how to reuse the NR-DC solution for supporting QMC in EN-DC should be considered, if time permits. Note 5: Specification of RAN visible QoE for XR related Service types shall take into account the outcome of XR SI and XR WI if applicable.

2	Workplan

2.2	Timeline

Table 1 summarizes a timeline for RAN2/3. This timeline is based on RP-221060 [2].

Table 1: Timeline for RAN2, 3 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | #119bis-e | Oct 2022 | 0.5 | Continue stage-2 and stage-3 discussion and try to make the decision on: 1. Left-over features from Rel-17, as well as the enhancements of existing features which are not included in Rel-17 normative phase, should be supported in Rel-18 if consensus on benefits are reached: - RAN visible QoE enhancements for QoE value, RAN visible QoE trigger event 2. Based on the RAN3 progress, support QoE for NR-DC in RAN2, e.g. enable QoE reporting via SN. 3. Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed |
| RAN3 | #117bis-e | Oct 2022 | 1 | Continue stage-2 and stage-3 discussion and try to make the decision on: - Support for new service type, such as AR, MR, MBS and other new service type defined or to be supported by SA4. Support RAN-visible parameters for the additional service types, and the existing service if needed； - QoE measurement configuration and collection in RRC_INACTIVE and RRC_IDLE states for MBS, at least for broadcast service - QoE in NR-DC, e.g. enable QoE reporting via SN - QoE configuration, and measurement reporting over MN/SN for NR-DC architecture, and specify the QoE measurement reporting over the other DC leg in order to maintain the reporting continuity. - RAN-visible QoE and radio related measurement configuration and reporting in NR-DC scenarios. - Left-over features from Rel-17, as well as the enhancements of existing features which are not included in Rel-17 normative phase, should be supported in Rel-18 if consensus on benefits are reached - RAN visible QoE enhancements for QoE value, RAN visible QoE trigger event, RAN visible QoE Report over F1. - QoE reporting handling enhancement for overload scenario. Handling LSs from RAN2 and other working groups. 5.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 6.Update BL CRs if needed. |
| RAN2 | #120 | Nov 2022 | 0.5 | Continue stage-2 and stage-3 discussion on: 1. Based on the RAN3 progress, specify to support for QoE in NR-DC in RAN2, e.g. enable QoE reporting via SN. 2. QoE measurement configuration and collection in RRC_INACTIVE and RRC_IDLE states for MBS, at least for broadcast service 3. Left-over features from Rel-17, as well as the enhancements of existing features which are not included in Rel-17 normative phase, should be supported in Rel-18 if consensus on benefits are reached: - RAN visible QoE enhancements for QoE value, RAN visible QoE trigger event - Based on the RAN3 progress, specify QoE reporting handling enhancement for overload scenario. 4. Support the continuity of legacy QoE measurement job for streaming and MTSI service during intra-5GC inter-RAT handover process 5. Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed 6. Update the stage-2 CR and stage-3 CR. |
| RAN3 | #118 | Nov 2022 | 1 | Continue stage-2 and stage-3 discussion on: - Support for new service type, such as AR, MR, MBS and other new service type defined or to be supported by SA4. Support RAN-visible parameters for the additional service types, and the existing service if needed,； - QoE measurement configuration and collection in RRC_INACTIVE and RRC_IDLE states for MBS, at least for broadcast service - QoE in NR-DC, e.g. enable QoE reporting via SN - QoE configuration, and measurement reporting over MN/SN for NR-DC architecture, and specify the QoE measurement reporting over the other DC leg in order to maintain the reporting continuity. - RAN-visible QoE and radio related measurement configuration and reporting in NR-DC scenarios. - QoE measurement continuity in mobility scenarios in NR-DC. - Discuss the alignment of QoE measurements (including legacy QoE and RAN visible QoE measurements) and radio related measurement in NR-DC. - Discussion on the solutions for left-over features from Rel-17: - RAN visible QoE enhancements for QoE value, RAN visible QoE trigger event, RAN visible QoE Report over F1. - QoE reporting handling enhancement for overload scenario. Handling LSs from RAN2 and other working groups. 5.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 6.Update BL CRs if needed. |
| RAN2 | #121 | Feb 2023 | 1 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update stage-2 CR and stage-3 CR if needed. |
| RAN3 | #119 | Feb 2023 | 1 | - Continue discussion for the above topics - Initial the discussion about the continuity of legacy QoE measurement job for streaming and MTSI service during intra-5GC inter-RAT handover process. 3.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 4.Update BL CRs if needed. |
| RAN2 | #121bis | April 2023 | 1 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update stage-2 CR and stage-3 CR if needed. |
| RAN3 | #119bis | April 2023 | 1 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update BL CRs if needed. |
| RAN2 | #122 | May 2023 | 0.5 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update stage-2 CR and stage-3 CR if needed. |
| RAN3 | #120 | May 2023 | 1 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update BL CRs if needed. |
| RAN2 | #123 | Aug 2023 | 1 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update stage-2 CR and stage-3 CR if needed. |
| RAN3 | #121 | Aug 2023 | 1 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update BL CRs if needed. |
| RAN2 | #123bis | Oct 2023 | 1 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update stage-2 CR and stage-3 CR if needed. |
| RAN3 | #121bis | Oct 2023 | 1 | 1. Continue discussion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update BL CRs if needed. |
| RAN2 | #124 | Nov 2023 | 0.5 | 1. Continue discussion and make the final conclusion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update stage-2 CR and stage-3 CR if needed. |
| RAN3 | #122 | Nov 2023 | 1 | 1. Continue discussion and make the final conclusion for the above topics 2.Coordinate with other working groups e.g. RAN3/SA4/SA5/SA2/CT1, and send the LS if needed. 3.Update BL CRs if needed. |
| RAN | #102 | Dec 2023 |  | Functional freeze |

Proposal 1 : RAN3 working group is kindly asked to endorse the workplan of RAN3 for NR QoE enhancement WI.

2.2	BLCR

The BLCR Rapporteur assignments for R18 NR QoE WI is listed as below:

| TS | BLCR Rapporteur |
| --- | --- |
| 38.300 | China Unicom |
| 38.306 | CMCC |
| 38.331 | Ericsson |
| 38.401 | Samsung |
| 38.410 | CATT |
| 38.413 | Huawei |
| 38.420 | Qualcomm |
| 38.423 | Ericsson |
| 38.470 | Lenovo |
| 38.473 | ZTE |
| 37.340 | Nokia |
| 36.331 | China Unicom |

Proposal 2 : RAN3 working group is kindly asked to endorse the BL CR rapporteurs for NR QoE enhancement WI.

References

- RP-221803: Revised WID for NR QoE enhancement; TSG RAN Meeting #96, Budapest, Hungary, June 6 - 9, 2022

- RP-221060: Draft Status of TU RAN1 to 4 after RAN#96 v01, Budapest, Hungary, June 6 - 9, 2022