3GPP TSG RAN3 meeting #125bis  	         	                               R3-245616

14th – 18th Oct 2024  Hefei, China

Agenda item: 	    10.1

Source: 	China Unicom, CMCC (WI Rapporteur)

Title: 	Workplan for Rel-19 SON_MDT Enhancement

Document for:	Information

1	Introduction

At RAN#102, the new Work Item on Data Collection for SON_MDT in NR standalone and MR-DC phase 4 was agreed [1]. As WI Rapporteur, in this contribution, we recommend a work plan for RAN2 and RAN3. The workplan captures dependencies among tasks and timeline for RAN2/3.

The WID [1] introduced the following objectives in the core part:

The objective of this work item is to specify data collection enhancement in NR standalone and MR-DC for SON/MDT purpose. The specific objectives of this work item are: - MRO enhancement for R18 mobility mechanisms, including, Lower layer triggered mobility (LTM), CHO with candidate SCGs, subsequent CPAC [RAN3, RAN2]: - Specification of the inter-node information exchange, including possible enhancements to interfaces [RAN3] - Identify and specify necessary UE reporting to enhance the mobility parameter tuning [RAN2] - Support of SON/MDT enhancements for [RAN3, RAN2]: - Intra-NTN mobility - Network Slicing - Support of the leftovers in Rel-18 SON/MDT [RAN3, RAN2]: - RACH optimization for SDT - MHI Enhancement for SCG Deactivation/Activation - MRO for MR-DC SCG failure If needed, co-operate with RAN1, SA2, SA5, CT4.

2	Workplan

2.1	Timeline

Table 1 summarizes a timeline for RAN2 and RAN3 while the timeline is based on the time budget approved at RAN#102 in [2].

Table 1: Timeline for RAN2, 3 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | #125bis | Apr. 2024 | 0.5 | In the first meeting, RAN2 can start working on the following items considering the limited TU: 1. Discussion on the scenario of MRO enhancement for R18 mobility mechanisms, where LTM can be prioritized. 2. Discussion on leftover features from R18 with corresponding specification impacts: - MHI enhancement with SCG activation/deactivation - RA report enhancement for SDT -Approval of the work plan -Update BL CRs if needed. |
| RAN3 | #123bis | Apr. 2024 | 1.5 | RAN3 can start working on the following items: - Discussion on the scenario and high-level solutions of MRO enhancement for R18 mobility mechanisms, including, Lower layer triggered mobility (LTM), CHO with candidate SCGs, subsequent CPAC, - Discussion on the scenario and high-level solutions for supporting SON/MDT enhancements for intra-NTN mobility - Discussion on the scenario and high-level solutions for supporting SON/MDT enhancements for network slicing Discussion on leftover features from R18 with corresponding specification impacts: MRO for MR-DC SCG failure - Approval of the work plan - Discuss and agree on the BL CR assignment -Update BL CRs if needed. |
| RAN2 | #126 | May 2024 | 0.5 | 1. Discussion on leftover features from R18 with corresponding specification impacts: - MHI enhancement with SCG activation/deactivation - RA report enhancement for SDT 2. Discussion on the scenario of MRO enhancement for R18 mobility mechanisms, where LTM can be prioritized. -Coordinate with other working groups, e.g. taking RAN3’s agreements into consideration and send the LS if needed |
| RAN3 | #124 | May 2024 | 1.5 | Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements, coordinate with other working groups, and send the LS if needed 1.MRO enhancements - Discussion on scenarios of near failure LTM. - Discussion on scenarios for the differentiation of too early LTM, too late LTM and LTM to wrong cell. - Discussion on MRO for CHO with candidate SCG failure and near failure cases, focusing on NR-DC - Discussion on the scenarios of failure in S-CPAC. The optimization of non-failure scenarios 2. Intra-NTN Mobility - Discussion on logged MDT enhancement based on scenarios for intra-NTN - Discussion on MRO for intra-NTN failure scenarios 3. Network slicing - Discussion on logged MDT and immediate MDT enhancements based on scenarios for network slicing 4. Leftovers - Discussion on scenario of RACH optimization for SDT - Check RAN2 progress regarding support MRO for SCG failure in EN-DC, NGEN-DC and NE-DC scenarios. -Update BL CRs if needed. |
| RAN2 | #127 | Aug. 2024 | 0.5 | 1. Discussion on the scenario of MRO enhancement for R18 mobility mechanisms, where LTM, CHO with candidate SCGs can be prioritized. 2. Discussion on leftover features from R18 with corresponding specification impacts:  MRO for MR-DC SCG failure  Further enhancement for SDT Update RRC CR according meeting agreements. |
| RAN3 | #125 | Aug. 2024 | 1.5 | Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements, coordinate with other working groups, and send the LS if needed 1.MRO enhancements - Discussion on definitions of failure LTM. - Discussion on whether DU or CU performs root cause analysis for failures due to inappropriate cell switch triggering. - Discussion on the error cases in CHO with candidate SCG. - Discussion on whether to include failure and near failure scenarios related with configuration of CHO with candidate SCG(s) and CHO only - Discussion on the use cases and solutions for S-CPAC 2. Intra-NTN mobility - Discussion on whether there are any enhancements to RLF report due to support for multiple trigger conditions in intra-NTN mobility. - Discussion on whether to consider any enhancement for MDT configuration e.g., area scope and trigger condition for NTN. -Discuss MRO for RACH-less HO of NTN, only for those different issues identified compared with MRO for LTM. 3. Network slicing - Discussion on which immediate MDT measurements can be collected per slice. - Discussion on whether to support logged MDT on specific area per slice(s). - Discussion on solutions are needed to optimize handovers in the case of slicing discontinuity for successful handover 4. Leftovers - Check RAN2 progress regarding support MRO for SCG failure in EN-DC, NGEN-DC and NE-DC scenarios. |
| RAN2 | #127bis | Oct. 2024 | 0.5 | 1. Discussion on the scenario of MRO enhancement for R18 mobility mechanisms, where LTM, CHO with candidate SCGs can be prioritized. 2. Discussion on leftover features from R18 with corresponding specification impacts |
| RAN3 | #125bis | Oct. 2024 | 1.5 | - Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements for MRO enhancements, Intra-NTN mobility, Network slicing and leftover parts. 2. Coordinate with other working groups, and reply and send the LS if needed 3. Update BL CRs if needed. |
| RAN2 | #128 | Nov. 2024 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #126 | Nov. 2024 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #129 | Feb. 2025 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #127 | Feb. 2025 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #129bis | Apr. 2025 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #127bis | Apr. 2025 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #130 | May 2025 | 0.5 | Finalize Stage-2 discussion |
| RAN3 | #128 | May 2025 | 1.5 | Finalize Stage-2 discussion |
| RAN2 | #131 | Aug. 2025 | 0.5 | Finalize Stage-3 discussion |
| RAN3 | #129 | Aug. 2025 | 1.5 | Finalize Stage-3 discussion |
| RAN | #109 | Sep. 2025 |  | Functional freeze |

Note that the detailed work plan for the meetings after May will be updated based on the progress.

3	Summary

Proposal 1: RAN3 working group is kindly asked to endorse the workplan.

4   References

- RP-234038: New WID: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4; TSG RAN Meeting #102, Edinburgh, Scotland, Dec 11-15, 2023

- RP-232744, Status of time budgets for RAN1/2/3/4 ongoing and new WIs/SIs after RAN #102, TSG RAN Meeting #102, Edinburgh, Scotland, Dec 11-15, 2023