3GPP TSG-RAN WG4 #112	R4-2411031

Maastricht, NL

Agenda item:	7.14.1

Source: 	Novamint, Ubiik, Semtech, Telit, Sequans Communications

Title: 	Work plan for LTE FDD new band in 1800–1830 MHz for Canada

Document for:	Approval

# Introduction

A spectrum-related work item [1] was agreed to specify a new LTE band in the 1800-1830 MHz frequency range.  This contribution provides a work plan to complete the technical work.

# Discussion

According to the WID [1], the work item to specify a new LTE band in the 1800-1830 MHz frequency range is scheduled to complete by RAN#107 (March 2025).  The objectives from the WID are copied below

Core part

Specify a new E-UTRA FDD operating band operating in the range 1800-1830 MHz, in a Release independent from Release 13, with the following characteristics:

  - UL: 1800 – 1810 MHz and DL: 1820 – 1830 MHz

  - Band numbering and RF characteristics

  - Support the following channelization: 10, 5, 3 and 1.4 MHz

  - Specify related UE RF core requirements (e.g. UE power class, Additional Maximum Power Reduction (A-MPR), Reference sensitivity, blocking performance)

  - Define PC3 UE power class

  - Consider UE categories M1&M2 and NB1&NB2

  - Specify related BS RF core requirements

  - Consider WA BS, MR BS and LA BS classes

  - Update RRM specification with new band

Note: 	Not impose new UE requirements with this new band as the protected band from the existing 3GPP bands (i.e., Table 6.6.3.2-1 in TS 36.101, and Table 6.5.3.2-1 in TS 38.101-1).

Performance part

Update the related 3GPP technical specifications with test requirements and BS conformance tests to take account of the new band.

The following RAN4 working group meetings are currently on the calendar until the completion of the work item:  RAN4 #112, RAN4 #112-bis, RAN4#113 and RAN4#114. Thus, there are three meetings to complete the technical work for the Core part (RAN4 #112, RAN4 #112-bis, RAN4#113) and two meetings to complete the technical work for the Performance part (RAN4#113, RAN4#114).

The following work plan is proposed

RAN4 #112 (2024-08-19 to 2024-08-23)

- Overview of current regulation

- Identify a band number

- Identify which Sections of the specifications listed in [1] need to be updated

- Agree on channel bandwidths and E-UTRA channel numbers

- Agree on related UE RF core requirements

- Agree on parameters to allow support of NB-IoT and eMTC in the new band

RAN4 #112-bis (2024-10-14 to 2024-10-18)

- Draft CR’s for Core part to be presented.

RAN4 #113 (2024-11-18 to 2024-11-22)

- Finalize and agree to CR’s on Core Part

- Draft CR’s for Performance part to be presented

RAN4 #114 (2025-02-17 to 2025-02-21)

- Finalize and agree to CR’s on Performance Part

# Conclusion

A work plan has been presented as a guideline for timely completion of the technical work to specify a new LTE band in the 1800-1830 MHz frequency range.  The completion of this WID is expected in RAN#107 (March 2025).

# Reference

- RP-241649, “New WID: Introduction of LTE FDD band in 1800 – 1830 MHz for Canada,” Novamint, Sequans, Semtech, Telit, Ubiik