3GPP TSG-RAN WG4 Meeting #112	R4-2411044

Maastricht, Netherlands, Aug 19 – Aug 23, 2024

Source:	Nokia

Title:	Work Plan for Spatial Channel Model Study Item

Agenda item:	8.14.1

Document for:	Approval

Introduction

During RAN#104 the study item on Spatial Channel Model was agreed, whereby the SI is due to start during RAN4#112, within this contribution we present a potential work plan to add structure to study item throughout Release 19.

Discussion

TU Allocation

To provide a reminder the following table is the time unit allocation provided to the Study Item agreed during RAN#104.

| Meeting No. | Date | TU allocation |
| --- | --- | --- |
| RAN4#112 | August 24 | 0.5 |
| RAN #105 (September 25) |  |  |
| RAN4#112-bis | October 24 | 0.5 |
| RAN4#113 | November 24 | 0.5 |
| RAN #106 (December 25) |  |  |
| RAN4#114 | Feb 25 | 0.5 |
| RAN #107 (March 25) |  |  |
| RAN4#114-bis | March 25 | 0.5 |
| RAN4#115 | May 25 | 0.5 |
| RAN #108 (June 25) |  |  |

As can be seen, the Study Item is due for completion by RAN#108, therefore it is imperative that a tight timescale and plan is drawn and adhered to by all delegates to ensure successful completion of the Study Item.

Such a plan requires to provide enough structure to drive timely delivery; but sufficient room for technical discussions on the best approach to introduce spatial channel modelling to RAN4. Therefore, we propose that a work plan is agreed during RAN4 #112 that all companies agree to stick to for successful and timely delivery of the SI.

A work plan is required, which should be agreed upon during RAN4#112.

Assumptions on Process for TR Generation

In order to develop a work plan, there are some key assumptions that RAN4 must make on the delivery of the final TR ahead of RAN #108, most notably that of the process for delivering the TR.

Furthermore, as this is a new TR; designated as TR 38.753, Nokia believes that it would be beneficial that a draft TR and work split be agreed in good time and that we follow a ‘draft pCR’ process, with submission of a formal Text Proposal to approve the first version of the TR during RAN #108.

The Spatial Channel Model TR has been allocated as TR 38.753

RAN4 shall follow the ‘draft pCR’ process with submission of a ‘big pCR’ during RAN4#115

Approach

In order to develop a reasonable work plan based off the SID, we believe that the following distinct phases should happen as part of the study item.

Identify Existing Limitations (Phase 1): RAN4 should start by collectively defining the limitations of the current channel models (TDL and TDL + antenna correlation) in relation to MIMO performance. This should include:

- How these models fail to capture spatial characteristics of real-world channels.

- How these limitations impact the accuracy of performance assessments for SU-MIMO and MU-MIMO scenarios.

- Specific examples of performance discrepancies observed in real-world deployments compared to simulations using current models.

In order to identify the existing limitations, relevant scenarios should be utilized, ideally with the input of Mobile Network Operators.

RAN4 shall identify relevant deployment scenarios which can highlight any existing limitations

Explore Modelling Approaches (Phase 2): RAN4 should then explore potential spatial channel modelling approaches:

- CDL-based: Focus on the tuned repeatable spatial channel model from TR38.827 as a starting point. Identify necessary modifications to make it suitable for demodulation performance requirements.

- TDL-based: Investigate if TDL-based approaches can be enhanced to incorporate spatial information. Consider potential limitations and trade-offs.

Develop Test Methodology (Phase 3): Once promising modelling approaches are identified, RAN4 should develop a test methodology for evaluating demodulation performance:

- Feasibility: Ensure the methodology is practical and achievable with reasonable test complexity.

- FR1 and FR2: Develop separate methodologies for both frequency ranges, prioritizing FR1 initially.

- Validate and Refine: RAN4 should conduct simulations to validate the chosen modeling approach and test methodology.

Document Conclusions (Phase 4): Finally, RAN4 should document the findings of the study in the TR (Technical Report). This document should include:

- A detailed description of the chosen spatial channel model.

- The test methodology and its validation results.

- Recommendations for developing RAN4 performance requirements.

Work plan

Based on the above assumptions and time unit constrictions, the following is a proposed outline work plan for activities that need to occur within this Study Item. The distinct phases are represented by the bold text.

RAN4 shall agree to the following work plan

| Meeting No. | Date | Details |
| --- | --- | --- |
| RAN4#112 | August 24 | Identify Existing Limitations (Phase 1): Scenario Discussed and early Alignment Initial Scenario Configuration Alignment Explore Modelling Approaches (Phase 2): Potential approaches to channel modelling discussed |
| RAN #105 (September 25) |  |  |
| RAN4#112-bis | October 24 | Identify Existing Limitations (Phase 1): Scenarios agreed Explore Modelling Approaches (Phase 2): Initial simulation parameter alignment Considered channel model alignment |
| RAN4#113 | November 24 | Explore Modelling Approaches (Phase 2): Simulation parameters agreed Develop Test Methodology (Phase 3): Testability Discussions Initial simulations Document Conclusions (Phase 4): Draft TR structure agreed Work split agreed |
| RAN #106 (December 25) |  |  |
| RAN4#114 | Feb 25 | Develop Test Methodology (Phase 3): Simulation Alignment Document Conclusions (Phase 4): Initial discussion on potential conclusions Draft TPs |
| RAN #107 (March 25) |  |  |
| RAN4#114-bis | March 25 | Develop Test Methodology (Phase 3): Further Simulation Alignment Document Conclusions (Phase 4): Draft conclusions Draft TPs |
| RAN4#115 | May 25 | Document Conclusions (Phase 4): big pCR |
| RAN #108 (June 25) |  |  |

Conclusion

The paper introduces the topic of Spatial Channel Modelling into RAN4 and presents some of the Nokia views on this topic for discussion during RAN4#112.

The following Observations and Proposals were made:

Observation 1: A work plan is required, which should be agreed upon during RAN4#112.

Observation 2: The Spatial Channel Model TR has been allocated as TR 38.753

Proposal 1: RAN4 shall follow the ‘draft pCR’ process with submission of a ‘big pCR’ during RAN4#115

Proposal 2: RAN4 shall identify relevant deployment scenarios which can highlight any existing limitations

Proposal 3: RAN4 shall agree to the following work plan

| Meeting No. | Date | Details |
| --- | --- | --- |
| RAN4#112 | August 24 | Identify Existing Limitations (Phase 1): Scenario Discussed and early Alignment Initial Scenario Configuration Alignment Explore Modelling Approaches (Phase 2): Potential approaches to channel modelling discussed |
| RAN #105 (September 25) |  |  |
| RAN4#112-bis | October 24 | Identify Existing Limitations (Phase 1): Scenarios agreed Explore Modelling Approaches (Phase 2): Initial simulation parameter alignment Considered channel model alignment |
| RAN4#113 | November 24 | Explore Modelling Approaches (Phase 2): Simulation parameters agreed Develop Test Methodology (Phase 3): Testability Discussions Initial simulations Document Conclusions (Phase 4): Draft TR structure agreed Work split agreed |
| RAN #106 (December 25) |  |  |
| RAN4#114 | Feb 25 | Develop Test Methodology (Phase 3): Simulation Alignment Document Conclusions (Phase 4): Initial discussion on potential conclusions Draft TPs |
| RAN #107 (March 25) |  |  |
| RAN4#114-bis | March 25 | Develop Test Methodology (Phase 3): Further Simulation Alignment Document Conclusions (Phase 4): Draft conclusions Draft TPs |
| RAN4#115 | May 25 | Document Conclusions (Phase 4): big pCR |
| RAN #108 (June 25) |  |  |

- References

- RP-241610; “Study on spatial channel model for demodulation performance requirements”, Nokia, BT Plc et al, RAN#104, Shanghai, June 2024.