## Sheet1
RAN5 5GS AP list
AP-5G# | WG | Area | Description | AP Owner(s) | Comments | Status | Start date | Target / End date
1 | RF+SIG | RAN1 | DCI formats and information about transport block size to be used for NR is missing in RAN1 specifications. This is basic information critical to be available in the RAN1 NR TSs after RAN1#91 (Nov-17) to progress of RAN5 work. Check with RAN1 when this information will be available. If needed, RAN5 chair to inform RAN1 chair before RAN1#91 (Nov-17) about the RAN5 needs. | Ericsson (Leif Mattisson), RAN5 chair (Jacob John) | RAN1 chair feedback: DCI format and TBS formula are progressing and aim is to have then ready by Dec 2017 (subject to further corrections) | Closed | 2017-11-02 | 2017-11-15
2 | RF+SIG | RAN1, RAN2 | L1\L2 layer parameters still not defined, this will impact overall SIG progress. Check with RAN1 & RAN2 when this will be included in RAN1 and RAN2 draft TSs. If needed, RAN5 chair to inform RAN1 and RAN2 chair before RAN1#91 and RAN2#100 (Nov-17) about the RAN5 needs. | Ericsson (Leif Mattisson), RAN5 chair (Jacob John) | RAN1/RAN2 chairs feedback: L1 and L2 parameters (and complete RRC for LTE/NR dual connectivity) should be available in RAN1 and RAN2 specifications by Dec 2017. Corrections are expected at the ASN.1 freeze in March 2018. | Closed | 2017-11-02 | 2017-11-15
3 | RF | RAN4 | To progress RAN5 RF for Option 3 at the RAN5 ad-hoc#1 (16-19 Jan 2018) it is necessary to clarify which specs (TS38.101-1/2/3) are capturing the requirements for NSA and it is critical that TSs or the associated TRs will become available after the RAN4#85 meeting in Reno. RAN4 needs to be informed about this before RAN4#85. If needed, RAN5 chair to inform RAN4 chair before RAN4#85 (Nov-17) about the RAN5 needs. | CMCC (Jinqiang Xing), Qualcomm (Pradeep Gowda), RAN5 chair (Jacob John) | RAN4 chair feedback: For the Jan ad-hoc RAN5 could start the work for NR FR1 (Below 6GHz) which is highly possible to be completed in RAN4 by Nov meeting. For FR2, some inter-WG working between RAN4 and RAN5 are needed to finalize the remaining core requirements for FR2 in Q1 2018. | Closed | 2017-11-02 | 2017-11-15
4 | SIG | RAN2 | Which encryption and integrity protection algorithms will be used for NR? Need to check with RAN2 when this will be decided. | Qualcomm (Yogesh Tugnawat) | RAN2 agreed that a PDCP associated with KeNB can be configured with one of the LTE algorithms only and a PDCP associated with S-KgNB can be configured with one of the NR algorithms only, regardless of PDCP version. | Closed | 2017-11-02 | 2017-11-11
5 | SIG | RAN2 | Is support of NR-PDCP on MCG split bearer mandatory or optional? If optional this will result in NR-PDCP test cases will be optional for NSA option 3. Need to be confirmed with RAN2. | Qualcomm (Yogesh Tugnawat) | Support of NR PDCP for split bearer is mandatory requirement as split bearer is always configured with NR PDCP. | Closed | 2017-11-02 | 2017-11-11
6 | SIG | RAN2 | Uplink Switching for Split Bearer options - Is it controlled by NW? | Qualcomm (Yogesh Tugnawat) | Yes, per current discussions in RAN2, UL switch is signaled by RRC. To be confirmed once there is agreement in RAN2. | Ongoing | 2017-11-02 | RAN5#77
7 | SIG | UE test functions | Update the Discussion paper for checking UE's IP stack, add some examples. | Qualcomm (Yogesh Tugnawat) | Proposal under discussion. Contact Yogesh for further details. | Ongoing | 2017-11-02 | RAN5#77
8 | RF+SIG | UE test functions | Rapporteurs need to collect requirements (and possible operation) for loopback modes based on their test case requirement and inform TS 38.509 rapporteur (Stoyan Baev, Samsung) | WP sub-area rapporteurs |  | Not started | 2017-11-02 | Option 3: RAN5#77
9 | SIG | EN-DC | RAN5 assumption is that all options for EN-DC needs to be considered (3, 3a, 3x). Further confirmation needed? | Qualcomm (Yogesh Tugnawat) |  | Ongoing | 2017-11-02 | RAN5#77
10 | SIG | EN-DC | Discuss complexities due to testing of several bearer options for EN-DC. | Qualcomm (Yogesh Tugnawat) | Discussion paper pålanned for RAN5#77 along with a RRC Model TC. | Ongoing | 2017-11-02 | RAN5#77
11 | SIG | UE test functions | UE beamlock function, will it be needed for signaling? RAN5 need to evaluate. | Ericsson (Leif Mattisson), SS vendors |  | Not started | 2017-11-02 | RAN5#78
12 | SIG | SIG OTA | Evaluate means for performing protocol testing for UEs only supporting NR mmWave bands. Must OTA chambers as used for RF/RRM for NR mmWave frequencies be used?; or can "simpler" means be used considering that protocol testing is functional? Discussions from OTA discussions in the RF group to be included in RF/SIG joint session. | Qualcomm (Pradeep Gowda), SS vendors |  | Not started | 2017-11-02 | RAN5#77
13 | RF | RF OTA | Ensure reliability of the LTE OTA link: 1. Define appropriate DL power, TM mode, MCS 2. No DL or UL grants after 5G-NR connection setup. Do we require active 5G-NR signaling over LTE link which would need LTE DL/UL Traffic? 3. Impact to OTA chamber dimensions due to OTA LTE 4. Impact of multipath due to reflections for OTA LTE | Qualcomm (Vijay Balasubramanian), SS vendors |  | Not started | 2017-11-02 | RAN5#77
14 | RF | RAN4 | UE beam lock function (UBF) for RF/RRM mmwOTA tests. Way fwd to be finalized by Ran5, but need RAN4 input on the requirements that will need UBF, to help RAN5 define the UBF aspects. LS input from RAN4 on the need for UBF to RAN5#77. RAN5 need to request further details from RAN4 in the response LS to RAN4 to be able to define the details in 38.509. | Qualcomm (Pradeep Gowda) |  | Not started | 2017-11-02 | RAN5#78