## Cover sheet
3GPP TSG-RAN WG5 Meeting #91-e | [10 empty] | R5-212559
Electronic Meeting, 17th May- 28th May 2021
Agenda Item: | 7.4.2
Source: | Rapporteurs (China Mobile, China Telecom, China Unicom)
Title: | WP - UE Conformance Test Aspects for Enhancement of Network Slicing
Work item code: | eNS-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 15% (+10%) | 0 | 6
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 14.7% (+9.7%) | 0 | 6
FR1 |  | 14.7% (+9.7%) | 0 | 6
FR2 |  | 14.7% (+9.7%) | 0 | 6
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 6 | 0% | 0 | 6 | 0% | 0 | 6
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-210370 | New WID on UE Conformance Test Aspects for Enhancement of Network Slicing
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance Test Aspects for Enhancement of Network Slicing | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | eNS-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-16 Enhancement of Network Slicing (UID-910099) | [12 empty] | vs Area
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 14.7% (+9.7%) | 14.7% (+9.7%)
[14 empty] | 10 | 10
[14 empty] | 7.8 | 7.8
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.7 | General and Signaling Test Environment for eNS testing | Add enhancement of network slicing changes to default messages | CMCC | RAN5#92-e (Aug-21) | R5-213423, R5-213424 | CMCC Luting Kong <kongluting@chinamobile.com> | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | <Clause> | Introduction of common implementation conformance statements for Rel-16 eNS |  | CMCC | RAN5#91-e (May-21) | R5-213642 | CMCC Luting Kong <kongluting@chinamobile.com> | 0.3 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Network slice-specific authentication and authorization
3 |  | 38.523-1 | 9.1.10 | Network slice-specific authentication and authorization | New sub-clause |  |  |  |  | 0
4 | Y | 38.523-1 | 9.1.10.1 | NSSAA / EAP message transport / Success | ****TP1: [TS 24,501: 5.5.1.2.2]**** WITH: UE in 5GMM-DEREGISTERED state and supports network slice-specific authentication and authorization WHEN: UE is switched on THEN: UE transmits REGISTRATION REQUEST message with NSSAA bit in the 5GMM capability IE set to "network slice-specific authentication and authorization supported" ****TP2: [TS 24,501: 5.5.1.2.4]**** WITH: UE in 5GMM-REGISTERED-INITIATED state WHEN: SS sends REGISTRATION ACCEPT message with pending NSSAI and "NSSAA to be performed" indicator set to indicate that the network slice-specific authentication and authorization procedure will be performed THEN: UE shall store the S-NSSAI(s) in the pending NSSAI. ****TP3: [TS 24,501:5.4.7.2.2]**** WITH: UE is in 5GMM-REGISTERED state WHEN: SS sends NETWORK SLICE-SPECIFIC AUTHENTICATION COMMAND message with EAP message IE set to EAP-request message THEN: UE sends NETWORK SLICE-SPECIFIC AUTHENTICATION COMPLETE message with EAP message IE SET to the EAP-response message. ****TP4: [TS 24,501:5.4.7.2.2]**** WITH: UE is in 5GMM-REGISTERED state WHEN: SS sends NETWORK SLICE-SPECIFIC AUTHENTICATION COMMAND message THEN: UE sends NETWORK SLICE-SPECIFIC AUTHENTICATION COMPLETE message and set the S-NSSAI IE of the NETWORK SLICE-SPECIFIC AUTHENTICATION COMPLETE message to the HPLMN S-NSSAI associated with the EAP-response message. ****TP5:[TS 24.501 5.4.4.3，TS 23.502 4.2.9.3] **** WITH: UE is in 5GMM-REGISTERED state WHEN: SS sends CONFIGURATION UPDATE COMMAND message with allowed NSSAI for which the network slice-specific authentication and authorization has been successfully performed THEN: UE considers the new allowed NSSAI as valid and store the allowed NSSAI | CMCC | RAN5#92-e (Aug-21) |  | CMCC Luting Kong <kongluting@chinamobile.com> | 1 | 0% | 0% |  | 0% | 0%
5 | Y | 38.523-1 | 9.1.10.2 | NSSAA / EAP message transport / Abnormal | ****TP1: [TS 24,501:5.4.7.2.4 a]**** WITH: UE in 5GMM-REGISTERED state and NSSAA is ongoing WHEN: UE fails on transmission of NETWORK SLICE-SPECIFIC AUTHENTICATION COMPLETE message due to TAI change from lower layers THEN: UE initiate the mobility registration update procedure ****TP2: [TS 24,501:5.4.7.2.4 c]**** WITH: UE in 5GMM-DEREGISTERED-INITIATED state WHEN: SS sends NETWORK SLICE-SPECIFIC AUTHENTICATION COMMAND message THEN: UE ignores the NETWORK SLICE-SPECIFIC AUTHENTICATION COMMAND message and proceed with the de-registration procedure | Lenovo/Motorola Mobility | RAN5#93-e (Dec-21) |  | Lenovo/Motorola Mobility Abdul Rasheed M D<rasheed@motorola.com> | 1 | 0% | 0% |  | 0% | 0%
6 | Y | 38.523-1 | 9.1.10.3 | NSSAA / Initial registration / Rejected NSSAI, pending NSSAI | ****TP1: [TS 24,501: 5.5.1.2.4]**** WITH: UE has sent REGISTRATION REQUEST message with NSSAA bit and Request NSSAI WHEN: SS sends REGISTRATION ACCEPT message contains rejected NSSAI with rejection cause of "S-NSSAI not available due to the failed or revoked network slice-specific authentication and authorization" THEN: UE stores the rejected S-NSSAI(s) in the rejected NSSAI and shall not attempt to use this S-NSSAI in the current PLMN over any access *****TP2: [TS 24,501: 5.5.1.2.4]***** WITH: UE receives rejected NSSAI in the REGISTRATION ACCEPT message with rejection cause of "S-NSSAI not available due to the failed or revoked network slice-specific authentication and authorization", WHEN: UE is switched off and switched on THEN: UE deletes the stored Rejected NSAAI for the current PLMN *****TP3: [TS 24,501: 5.5.1.2.4]***** WITH: UE receives rejected NSSAI in the REGISTRATION ACCEPT message with rejection cause of "S-NSSAI not available due to the failed or revoked network slice-specific authentication and authorization", WHEN: The UICC containing the USIM is removed THEN: UE deletes the stored Rejected NSAAI for the current PLMN ****TP4:[TS 24,501: 5.5.1.2.4]**** WITH: UE stores pending NSSAI WHEN: SS sends REGISTRATION ACCEPT message with the pending NSSAI is not included and "NSSAA to be performed" indicator is not set to "Network slice-specific authentication and authorization is to be performed" THEN:UE deletes the stored pending NSSAI for the current PLMN | Ericsson | RAN5#93-e (Dec-21) |  | Ericsson Calle Hagenfeldt<calle.hagenfeldt@ericsson.com> | 1 | 0% | 0% |  | 0% | 0%
7 | Y | 38.523-1 | 9.1.10.4 | NSSAA / Initial registration / Reject | ****TP1: [TS 24,501: 5.5.1.2.5]**** WITH: UE in 5GMM-REGISTERED-INITIATED state WHEN: UE receives a REGISTRATION REJECT with cause #62 "No network slices available" THEN: UE abort the initial registration procedure, set the 5GS update status to 5U2 NOT UPDATED, enter state 5GMM-DEREGISTERED.NORMAL-SERVICE or 5GMM-DEREGISTERED.PLMN-SEARCH and reset the registration attempt counter ****TP2: [TS 24,501: 5.5.1.2.5]**** WITH: UE in 5GMM-REGISTERED-INITIATED state WHEN: UE receives the rejected NSSAI in the REGISTRATION REJECT message with rejection cause of "S-NSSAI not available due to the failed or revoked network slice-specific authentication and authorization"， THEN: UE stores the rejected NSSAI and doesn't attempt to use this S-NSSAI in the current PLMN over any access | Ericsson | RAN5#93-e (Dec-21) |  | Ericsson Calle Hagenfeldt<calle.hagenfeldt@ericsson.com> | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 38.523-1 | 9.1.10.5 | NSSAA / UE configuration update / Allowed NSSAI | ****TP1: [TS 24,501: 5.5.1.2.4]**** WITH: UE has sent REGISTRATION REQUEST message with NSSAA bit and Request NSSAI WHEN: SS sends REGISTRATION ACCEPT message contains the allowed NSSAI THEN: UE stores the included allowed NSSAI together with the PLMN identity of the registered PLMN and the registration area ****TP2: [TS 24,501: 5.5.1.2.4]**** WITH: UE in 5GMM-REGISTERED state and configured with allowed NSSAI WHEN: UE receives CONFIGURATION UPDATE COMMAND message with allowed NSSAI which the network slice-specific authentication and authorization has been successfully performed THEN: UE considers the new allowed NSSAI as valid and considers the old allowed NSSAI as invalid | Lenovo/Motorola Mobility | RAN5#92-e (Aug-21) |  | Lenovo/Motorola Mobility Abdul Rasheed M D<rasheed@motorola.com> | 1 | 0% | 0% |  | 0% | 0%
9 | Y | 38.523-1 | 9.1.10.6 | NSSAA / UE configuration update / Rejected NSSAI | ****TP1: [TS 24,501:5.4.4.3]**** WITH: UE is in 5GMM-REGISTERED state and NSSAA failure WHEN: SS sends the rejected NSSAI in the CONFIGURATION UPDATE COMMAND message with rejection cause of "S-NSSAI not available due to the failed or revoked network slice-specific authentication and authorization" THEN: UE adds the rejected S-NSSAI(s) in the rejected NSSAI and shall not attempt to use this S-NSSAI in the current PLMN over any access ****TP2: [TS 24,501:5.4.4.3]**** WITH: UE receives the rejected NSSAI in the CONFIGURATION UPDATE COMMAND message with rejection cause of "S-NSSAI not available due to the failed or revoked network slice-specific authentication and authorization" WHEN: UE has been switched off, then switched on THEN: UE deletes the stored Rejected NSAAI for the current PLMN ****TP3: [TS 24,501:5.4.4.3]**** WITH: UE receives the rejected NSSAI in the CONFIGURATION UPDATE COMMAND message with rejection cause of "S-NSSAI not available due to the failed or revoked network slice-specific authentication and authorization" WHEN: The UICC containing the USIM is removed THEN: UE deletes the stored Rejected NSAAI for the current PLMN | CMCC | RAN5#92-e (Aug-21) |  | CMCC Luting Kong <kongluting@chinamobile.com> | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
10 |  | 38.523-2 | 4.1 | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 | CMCC | RAN5#92-e (Aug-21) |  | CMCC Luting Kong <kongluting@chinamobile.com> | 0.5 | 0% | 0% |  | 0% | 0%
11 |  | 38.523-2 | 4.2 | <Title> | Add Applicability Condition for new eNS test cases | CMCC | RAN5#92-e (Aug-21) |  | CMCC Luting Kong <kongluting@chinamobile.com> | 0.5 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
12 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.