## Cover sheet
3GPP TSG-RAN WG5 Meeting #91-e | [10 empty] | R5-213084
Electronic Meeting, 17th - 28th May 2021
Agenda Item: | 7.4.2
Source: | Ericsson
Title: | Work plan: UE Conformance Test Aspects – Rel14 Enhanced Full Dimension MIMO for LTE
Work item code: | LTE_eFDMIMO-UEConTest
Release: | Rel-14
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#86 meeting in December 2019 the Rel-15 RAN5 work item for UE Conformance Test Aspects – Even further enhanced MTC for LTE was approved At the RAN#83 meeting in March 2019 the Rel-14 RAN5 work item for UE Conformance Test Aspects - Elevation Beamforming/Full-Dimension MIMO for LTE was approved in [1]. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items for eFD-MIMO. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 10
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 5% | 0 | 10
FDD |  | 5% | 0 | 7
TDD |  | 5% | 0 | 4
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 0% |  |  | 0% |  |  | 0%
LTE RF/RRM
RF common parts | 36.521-1 | 0% |  |  | 0% |  |  | 0%
RF Demod test cases | 36.521-1 Demod | 0% | 0 | 10 | 0% | 0 | 7 | 0% | 0 | 4
Applicability RF, Demod/QSI and RRM test cases | 36.521-2 | 0% |  |  | 0% |  |  | 0%
Test Tolerances analysis receiver test cases | 36.904 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-190509 | New WID on UE Conformance Test Aspects - Enhancements on Full-Dimension (FD) MIMO for LTE; Supporting companies: Ericsson, SRTC, T-Mobile US, Telecom Italia, Qualcomm
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Rel14 Enhanced Full Dimension MIMO for LTE | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_eFDMIMO-UEConTest
WP Scope: |  | RF perfromance test cases for Rel-14 Enhanced Full Dimension MIMO for LTE | [12 empty] | vs Area
WP Resp: |  | Mikael Zirén, Ericsson |  |  | mikael.ziren@ericsson.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD
[14 empty] | 5% | 5%
[14 empty] | 16 | 13
[14 empty] | 10.9 | 7.9
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
TBD |  | 36.508 | Annex A | Connection diagrams | Required connection diagrams are handled under each test case. This task represent the overall competion of connection diagrams. |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
TBD |  | 36.521-1 | Annex A | RMC | Define Reference Measurement Channels |  | TBD |  |  | 0.3 | 0% | 0% |  | 0% | 0%
TBD |  | 36.521-1 | Annex B | Propagation Conditions | Add new Beamforming models |  | TBD |  |  | 0.3 | 0% | 0% |  | 0% | 0%
|  | 36.904 | Annex F | Test Tolerances | Required Test Tolerance analysis for Annex F are handled under each impacted test case. | Each company introducing a new TC
TBD |  | 36.521-1 | Annex G | Statistical test time | Required Test Tolerance analysis for Annex F are handled under each impacted test case. | Each company introducing a new TC
TS 36.521-1: Demod/QSI reporting test cases
Demodulation of PDSCH (User-Specific Reference Symbols)
TBD |  | 36.521-1 Demod | 8.1.2 | Applicability of requirements |  |  | TBD |  |  | 0.3 | 0% | 0% |  | 0% | 0%
TBD |  | 36.521-1 Demod | 8.3.1.1H | FDD Single-layer Spatial Multiplexing (With Enhanced DMRS table configured) | Add new sub tests Add TT analysis in TR 36.904 Add TT in Annex F |  | TBD |  |  | 0.3 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 8.3.1.4 | FDD Performance Requirements for semiOpenLoop transmission | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 36.521-1 Demod | 8.3.1.1H | TDD Single-layer Spatial Multiplexing (With Enhanced DMRS table configured) | Add new sub tests Add TT analysis in TR 36.904 Add TT in Annex F |  | TBD |  |  | 0.3 | 0% | 0% |  |  | 0%
TBD | Y | 36.521-1 Demod | 8.3.2.5 | Performance Requirements for semiOpenLoop transmission | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
Reporting of Precoding Matrix Indicator (PMI)
TBD |  | 36.521-1 Demod | 9.4.1.3.1 | FDD Minimum requirement PUSCH 3-1 (CSI Reference Symbol) | Add new sub tests Add TT analysis in TR 36.904 Add TT in Annex F |  | TBD |  |  | 0.3 | 0% | 0% |  | 0%
TBD |  | 36.521-1 Demod | 9.4.1.3.2 | TDD Minimum requirement PUSCH 3-1 (CSI Reference Symbol) | Add new sub tests Add TT analysis in TR 36.904 Add TT in Annex F |  | TBD |  |  | 0.3 | 0% | 0% |  |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.1.3.5 | FDD (with Class A 24Tx codebook) | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.1.3.6 | TDD (with Class A 24Tx codebook) | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TBD |  | 36.521-1 Demod | 9.4.1.4.3 | Minimum requirement PUCCH 1-1 (CSI Reference Symbol) / FDD (with Class B alternative codebook for one CSI-RS resource configured) | Add new sub tests Add TT analysis in TR 36.904 Add TT in Annex F |  | TBD |  |  | 0.3 | 0% | 0% |  | 0%
TBD |  | 36.521-1 Demod | 9.4.1.4.4 | Minimum requirement PUCCH 1-1 (CSI Reference Symbol) / TDD (with Class B alternative codebook for one CSI-RS resource configured) | Add new sub tests Add TT analysis in TR 36.904 Add TT in Annex F |  | TBD |  |  | 0.3 | 0% | 0% |  |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.2.3.7 | FDD (with Class A 32Tx codebook) | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.2.3.8 | TDD (with Class A 32Tx codebook) | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.2.3.9 | FDD (with Class A 16Tx advanced codebook) | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.4.2.3.10 | TDD (with Class A 16Tx advanced codebook) | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
Reporting of Hybrid Channel state information
TBD | Y | 36.521-1 Demod | 9.11.1.1 | FDD Minimum requirement (with eMIMO-Type configured as Class B with more then one CSI-RS resource configured and eMIMO-Type2 as Class B with one CSI-RS resource configured) | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 36.521-1 Demod | 9.11.1.2 | TDD Minimum requirement (with eMIMO-Type configured as Class B with more then one CSI-RS resource configured and eMIMO-Type2 as Class B with one CSI-RS resource configured) | Add new test case including required TT in Annex F based on TT analysis in TR.36.904. If needed add connection diagram in 36.508 Annex A. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 36.521-2 | Table 4.1-1 | Applicability of RF conformance test cases | Add test case applicability statements for the new test cases introduced in 36.521-1. |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TR 36.904: Test Tolerances analysis receiver test cases
TBD |  | 36.904 |  | Test Tolerance analysis for each test case addition in Annex F | Required Test Tolerance analysis for Annex F are handled under each impacted test case. This task represent the overall completion of all TT analysis. | Each company introducing a new TC | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.