## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (NOV-21)
3GPP TSG-RAN5#93-e R5-216628
Electronic Meeting, 8 – 19 Nov 2021
DRAFT

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 Rel-15 5GS work item delivery phase.
Content
Progress since previous report
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) targets
Planning for next delivery
  SA NR (SA Option 2)
  EN-DC (NSA Option 3)
  NE-DC (NSA Option 4)

## Slide 3: Progress SINCE PREVIOUS REPORT
Status vs connectivity option:
  SA NR (SA Option 2): 91% completed
  EN-DC (NSA Option 3): 95% completed
  NE-DC (NSA Option 4): 84% completed
Current target completion is moved 3 months to RAN5#94-e (Mar-22).
For further details including list of completed test cases see RAN5 workplan in R5-216625

## Slide 4
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT)

## Slide 5
All FR2 test cases may not be feasible to complete by RAN5#94-e.
RF/Performance/RRM test cases:
  FR1
    RF: Complete remaining one (1) FR1 test cases (TS 38.521-1).
  FR2 & FR1+FR2:
    RF: Complete remaining 172 FR2 test cases (TS 38.521-1).
    RF performance: Complete remaining one (1) FR2 test case (TS 38.521-4).
    RRM: Complete remaining 46 FR2 and 3 FR1+FR2 test cases (TS 38.533).
RAN Protocol test cases (TS 38.523-1):
  Idle mode: Complete remaining 36 FR2 test cases.
  RRC: Complete remaining 47 FR2 and 6 FR1+FR2 test cases.
  Multilayer/Services: Complete remaining 6 FR2 test cases.
IMS Protocol test cases:
  Complete remaining 9 IMS test cases for FR1 and FR2 (TS 34.229-5).
Plan for next delivery:
SA NR (SA Option 2) - Phase 14 - Target RAN5#94-e MAR-22

## Slide 6
Plan for next deliverY:
EN-DC (NSA Option 3) - Phase 15 content - Target RAN5#94-e MAR-22
All FR2 test cases may not be feasible to complete by RAN5#94-e.
RF/Performance/RRM test cases
  FR1:
    RF: Complete remaining 21 FR1 (anchor-agnostic) test cases (TS 38.521-3).
    RF performance: Complete remaining one (1) FR1 test case (TS 38.521-4).
  FR2 & FR1+FR2:
    RF: Complete remaining 50 FR2 test cases (TS 38.521-3).
      Progress depending on progress of associated NR SA FR2 test cases.
    RRM: Complete remaining 37 FR2 and one (1) FR1+FR2 test cases (TS 38.533).
RAN Protocol test cases:
  RRC: Complete remaining 4 FR1 and 4 FR2 test cases (TS 38.523-1).

## Slide 7
Plan for next deliverY:
NE-DC (NSA Option 4) - Phase 2 content - Target RAN5#94-e MAR-22
Scope: Inter-band two band NE-DC configurations with 1CC FR1 NR and 1CC E-UTRA.
All NE-DC test cases may not be feasible to complete by RAN5#94-e.
RF/Performance/RRM test cases
  RF: Complete remaining 8 FR1 test cases (TS 38.521-3).
  RF performance (TS 38.521-4):
    Complete remaining one (1) SDR test case
  RRM:
    No test case definitions in RAN4 TS 38.133 prior to RAN5#93-e, therefore no test cases in R5 WP (TS 38.533).
  RAN Protocol:
    RRC: Complete remaining 31 FR1 test cases (TS 38.523-1).