## Cover sheet
3GPP TSG-RAN WG5 Meeting #98 | [10 empty] | R5-230441
Athens, Greece, 27th February – 3rd March 2023
Agenda Item: | 7.4.2
Source: | NTT DOCOMO, INC
Title: | WP - UE Conformance - Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode
Work item code: | eCPSOR_CON-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
This work item covers the protocol conformance testing for Rel-17 5G Control Plane Steering of Roaming for UE in Connected mode At the RAN#96-emeeting in Sep 2022,Rel-17 RAN5 work item for UE Conformance - Enhancement for the 5G Control Plane Steering of Roaming for UE [1] was approved. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% | 7 | 7 | Maintenance CR related to SOR-CMCI is discussed in CT1#139, so addition of new test cases may be required in next RAN5#98.
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% | 1 | 1
Common ICS | 38.508-2
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% | 7 | 7
Applicability Protocol test cases | 38.523-2 | 100% | 2 | 2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-222255 | UE Conformance - Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - Enhancement for the 5G Control Plane Steering of Roaming for UE in Connected mode | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | eCPSOR_CON-UEConTest
WP Scope: |  | UE Conformance Test Aspects for Rel-17 5G Control Plane Steering of Roaming for UE in Connected mode(UID=970073) | [12 empty] | vs Area
WP Resp: |  | Masahiro Takano, NTT DOCOMO,INC |  |  | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 13.5% (+13.5%) | 13.5% (+13.5%)
[14 empty] | 11 (+11) | 11 (+11)
[14 empty] | 8.4 (+8.4) | 8.4 (+8.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
970073 |  | 38.508-1 | 4.7.2 | Addition of parameter related to SOR-CMCI for DL NAS transport and UL NAS transport message in 38.508-1 | Add changes to default messages(DL/ULNAS transport) | NTT DOCOMO, INC. |  | R5-227593 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | 1 | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
970073 | Y | 38.523-1 | 6.3.2.1 | Addition of new test case 6.3.2.1 for DNN in SOR-CMCI | UE sends an SOR transparent container with ACK in UL NAS TRANSPORT message and UE sends DEREGISTRATION REQUEST message after Tsor-cm timer expires and selects higher priority PLMN after DEREGISTRATION procedure is completed sucessfully | NTT DOCOMO, INC. |  | R5-227594 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | 1 | 100% | 100%
970073 | Y | 38.523-1 | 6.3.2.2 | Addition of new test case 6.3.2.2 for MMTEL voice call in SOR-CMCI | UE sends an SOR transparent container with ACK in UL NAS TRANSPORT message and UE sends DEREGISTRATION REQUEST message after Tsor-cm timer expires and selects higher priority PLMN after DEREGISTRATION procedure is completed sucessfully | NTT DOCOMO, INC. |  | R5-227595 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | 1 | 100% | 100%
970073 | Y | 38.523-1 | 6.3.2.3 | Addition of new test case 6.3.2.3 for match all in SOR-CMCI | UE sends an SOR transparent container with ACK in UL NAS TRANSPORT message and UE sends DEREGISTRATION REQUEST message after Tsor-cm timer expires and selects higher priority PLMN after DEREGISTRATION procedure is completed sucessfully | NTT DOCOMO, INC. |  | R5-227504 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | 1 | 100% | 100%
970073 | Y | 38.523-1 | 6.3.2.4 | Addition of new test case 6.3.2.4 for updating Tsor-cm timer in SOR-CMCI | UE receives SOR Transparent container included in DL NAS TRANSPORT message with Tsor-cm timer value is other than infinity and is smaller than the current value of the running Tsor-cm timer, and, UE sends DEREGISTRATION REQUEST message after Tsor-cm timer expires, and, selects higher priority PLMN after DEREGISTRATION procedure is completed sucessfully | NTT DOCOMO, INC. |  | R5-227505 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | 1 | 100% | 100%
970073 | Y | 38.523-1 | 6.3.2.5 | Addition of new test case 6.3.2.5 for storing SOR-CMCI in the USIM after power off-on the UE | UE sends DEREGISTRATION REQUEST message after Tsor-cm timer expires, and, selects higher priority PLMN after DEREGISTRATION procedure is completed sucessfully | NTT DOCOMO, INC. |  | R5-227506 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | 1 | 100% | 100%
970073 | Y | 38.523-1 | 6.3.2.x | Correction of Pre-test conditions on TC 6.3.2.x | TC 6.3.2.x are need to modified in terms of editorial mistakes and optimizing the number of bands that can be used to run the test case. | NTT DOCOMO, INC. |  | R5-230442 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com |  | 100% | 100%
970073 | Y | 38.523-1 | 6.3.2.6 | Addition of new test case 6.3.2.6 for Emergency call in SOR-CMCI | UE sends an SOR transparent container with ACK in UL NAS TRANSPORT message and UE sends RRCSetupRequest message after releasing Emergency call with expiring Tsor-cm timer and selects higher priority PLMN procedure is completed sucessfully | NTT DOCOMO, INC. |  | R5-231900 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
|  | 38.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
970073 |  | 38.523-2 | 4.1 | Addition of applicability for new test case from 6.3.2.1 to 6.3.2.5 | add applicability to test case from 6.3.2.1 to 6.3.2.5 | NTT DOCOMO, INC. |  | R5-227596 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | 1 | 100% | 100%
970073 |  | 38.523-2 | 4.2 | Addition of applicability for new test case from 6.3.2.1 to 6.3.2.5 | add applicability to test case from 6.3.2.1 to 6.3.2.5 | NTT DOCOMO, INC. |  | R5-227596 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com | 1 | 100% | 100%
970073 |  | 38.523-2 | 4.2 | Addition of applicability for new test case 6.3.2.6 | add applicability to test case6.3.2.6 | NTT DOCOMO, INC. |  | R5-230444 | masahiro[dot]takano[dot]ru[at]nttdocomo[dot]com |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.