## Cover sheet
3GPP TSG RAN WG5#104 | [10 empty] | R5-244788
<Maastricht, NL, 19th Aug - 23rd Aug, 2024>
Agenda Item: | 7.5.2
Source: | China Unicom
Title: | UE Conformance – Support of reduced capability NR devices
Work item code: | NR_redcap_plus_ARCH-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
The objective of the UE Conformance – Support of reduced capability NR devices work item is to define the UE conformance requirements corresponding to WID on Support of reduced capability NR devices, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the RedCap UE work item in Rel-17. At the RAN#95 meeting the Rel-17 RAN5 work item for UE Conformance – Support of reduced capability NR devices (NR_redcap_plus_ARCH-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+0%) | 150 (+16.5) | 155
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 99.9% (+0.4%) | 150 (+16.5) | 155
FR1 |  | 99.9% (-0%) | 119.5 | 123.5
FR2 |  | 99.9% (+1.1%) | 42.5 (+16.5) | 43.5
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  | 100%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 100% |  |  | 100%
FR1 RF Tx test cases | 38.521-1 Tx | 100% | 5 | 5 | 100% | 5 | 5
FR1 RF Rx test cases | 38.521-1 Rx | 100% | 5 | 5 | 100% | 5 | 5
FR2 RF common parts | 38.521-2 | 100% | [5 empty] | 100%
FR2 RF Tx test cases | 38.521-2 Tx | 100% | [5 empty] | 100%
FR2 RF Rx test cases | 38.521-2 Rx | 100% | [5 empty] | 100%
RF Demod/QSI test cases | 38.521-4 | 99.7% (+0%) | 21 | 23 | 99.7% (+0%) | 21 | 23
RRM test cases | 38.533 | 99.8% (+1.5%) | 107 (+16.5) | 110 | 99.9% (-0%) | 76.5 | 78.5 | 99.7% (+4.1%) | 30.5 (+16.5) | 31.5
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100% |  |  | 100%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 95% |  |  | 95%
Test Point analysis receiver and transmitter test cases | 38.905 | 100% |  |  | 100% |  |  | 100%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% | 12 | 12 | 100% | 12 | 12 | 100% | 12 | 12
Applicability Protocol test cases | 38.523-2 | 100% |  |  | 100% |  |  | 100%
Test suites (TTCN) | 38.523-3 | 100% |  |  | 100% |  |  | 100%
5 References
[1] RP-220830 | New WID on UE Conformance – Support of reduced capability NR devices for RAN#95e
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Support of reduced capability NR devices | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_redcap_plus_ARCH-UEConTest
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item Support of reduced capability NR devices comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID | [12 empty] | vs Area
WP Resp: |  | Yu Shi(China Unicom),Yang, Zhaobing (Huawei) ,Calle Hagenfeldt (Ericsson),Yogesh Tugnawat (Qualcomm) |  |  | shiyu19@chinaunicom.cn;yangzhaobing@hisilicon.com;calle.hagenfeldt@ericsson.com;yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 99.9% (-0%) | 99.9% (+1.1%)
[14 empty] | 269 | 145
[14 empty] | 214.2 | 118.5
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | common test environment for RedCap | Definition of common test environment for RedCap | Huawei | RAN5#96 (Aug-22) | R5-223410 R5-222650 R5-223784 R5-224725 R5-225342 R5-225343 R5-225682 R5-225766 R5-227518 R5-227587 R5-230457 R5-230103 R5-231586 R5-233406 R5-235249 R5-235781 R5-235841 R5-235781 R5-235823 R5-237816 R5-236933 R5-236302 R5-236412 R5-236413 R5-243750 |  | 3 | 100% | 100% |  | 100% | 100%
2 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Huawei | RAN5#96 (Aug-22) | R5-226110 |  | 3 | 100% | 100% |  | 100% | 100%
3 |  | 38.508-1 | 6 | Test environments for Signalling test | Necessary changes to Signalling test environments | Huawei | RAN5#96 (Aug-22) | R5-226110 R5-236410 R5-236411 |  | 3 | 100% | 100% |  | 100% | 100%
4 |  | 38.508-1 | 7 | Test environments for RRM tests | Necessary changes to RRM test environments | Huawei | RAN5#97(Nov-22) | R5-226110 R5-237021r1 R5-240676 |  | 3 | 100% | 100% |  | 100% | 100%
5 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams | Ericsson | RAN5#99 (May-23) | R5-226684 |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
6 |  | 38.508-2 | A.4 | ICS proforma tables | Introduction of common implementation conformance statement (ICS) for RedCap | Huawei | RAN5#99 (May-23) | R5-222827 R5-236678 R5-225767 R5-237088 R5-227894 R5-244222 R5-227708 R5-245497 R5-227521 R5-227588 R5-232929 R5-233034 |  | 3 | 100% | 100% |  | 100% | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
7 |  | 38.521-1 | 3 | Definitions, symbols and abbreviations | definitions, symbols and abbreaviations respectively for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223790 R5-230888 |  | 2 | 100% | 100% |  | 100%
8 |  | 38.521-1 | 4 | General | Define categories of test requirements for R17 reduced capability NR devices | China Unicom | RAN5#96 (Aug-22) | R5-223790 R5-226765 |  | 2 | 100% | 100% |  | 100%
9 |  | 38.521-1 | 5 | Operating bands and Channel arrangement | Define the frequency bands and channel arragement for R17 reduced capability NR devices | China Unicom | RAN5#96 (Aug-22) | R5-223790 R5-231858 R5-231640 |  | 2 | 100% | 100% |  | 100%
10 |  | 38.521-1 | Annex |  | Check if necesarry to update Annex | ZTE | RAN5#100 (Aug-23) | R5-240826 |  | 1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
Transmitter characteristics (Clause 6)
11 | Y | 38.521-1 Tx | 6.2I.1 | Maximum output power for RedCap | Adding TC of UE maximum output power for RedCap | Huawei | RAN5#96 (Aug-22) | R5-223785 R5-227116 R5-231255 R5-234119 R5-234169 |  | 5 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
Receiver characteristics(Clause 7)
12 |  | 38.521-1 Rx | 7.1I | General | Adding general info introudction for RedCap | China Unicom | RAN5#95e (May-22) | R5-223198 |  | 1 | 100% | 100% |  | 100%
13 |  | 38.521-1 Rx | 7.2 | Diversity characteristics | Update of diveristy characteristics intrdocution for RedCap | China Unicom | RAN5#95e (May-22) | R5-223198 R5-227935 R5-236936 R5-243309 |  | 5 | 100% | 100% |  | 100%
14 |  | 38.521-1 | 7.3I | Reference sensitivity for RedCap | sub-clause
15 |  | 38.521-1 Rx | 7.3I.1 | General | Adding general info introudction for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223789 R5-225683 R5-226595 R5-227935 |  | 5 | 100% | 100% |  | 100%
16 | Y | 38.521-1 Rx | 7.3I.2 | Reference sensitivity power level for RedCap | TC of reference sensitivity power level for RedCap | China Unicom | RAN5#96 (Aug-22) | R5-223789 R5-224245 R5-225683 R5-226595 R5-227935 R5-230998 R5-234907 R5-234169 R5-236935 R5-241369 |  | 5 | 100% | 100% |  | 100%
TS 38.521-2: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
17 |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | definitions, symbols and abbreaviations respectively for RedCap | China Unicom | RAN5#98 (Feb-23) | R5-227943 R5-231285 R5-233206 |  | 1 | 100% | 100% |  |  | 100%
18 |  | 38.521-2 | 5 | Operating bands and Channel arrangement | Define the frequency bands and channel arragement for R17 reduced capability NR devices | China Unicom | RAN5#98 (Feb-23) |  |  | 1 | 100% | 100% |  |  | 100%
19 |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for PC7 |  |  | R5-234825 R5-234169 |  | 1 | 100% | 100% |  |  | 100%
TS 38.521-2: FR2 RF test cases - Tx
Transmitter characteristics (Clause 6)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
20 |  | 38.521-2 Tx | 6.1 | General | adding PC7 common uplink configuration | Qualcomm | RAN5#97(Nov-22) | R5-227777 |  | 1 | 100% | 100% |  |  | 100%
21 |  | 38.521-2 Tx | 6.2.1.0 | General | adding Release-17 FR2 PC7 UE Type | Qualcomm | RAN5#97(Nov-22) | R5-227777 R5-233718 |  | 1 | 100% | 100% |  |  | 100%
22 |  | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | adding RF requirement for Release-17 FR2 PC7 UE | Qualcomm | RAN5#98 (Feb-23) | R5-231873 R5-233554 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
23 |  | 38.521-2 Tx | 6.2.1.1_1 | UE maximum output power - EIRP and TRP (Rel16 and forward) | adding RF requirement for Release-17 FR2 PC7 UE with enhanced beam correspondence side condition | Qualcomm | RAN5#98 (Feb-23) | R5-231873 R5-233554 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
24 |  | 38.521-2 Tx | 6.2.1.2 | UE maximum output power - Spherical coverage | adding UE spherical coverage for power class 7 | Qualcomm | RAN5#98 (Feb-23) | R5-231873 R5-233718 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
25 |  | 38.521-2 Tx | 6.2.1.2_1 | UE maximum output power - Spherical coverage (Rel16 and forward) | adding UE spherical coverage for power class 7 UE with enhanced beam correspondence side condition | Qualcomm | RAN5#99 (May-23) | R5-231873 R5-233554 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
26 |  | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | adding Release-17 FR2 PC7 UE MPR | ZTE | RAN5#100 (Aug-23) | R5-237662 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
27 |  | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | adding Release-17 FR2 PC7 UE MPR for NS_202 and NS_203 | ZTE | RAN5#100 (Aug-23) | R5-237660 R5-241781 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
28 |  | 38.521-2 Tx | 6.3.1 | Minimum output power | adding Release-17 FR2 PC7 Minimum output power | ZTE | RAN5#100 (Aug-23) | R5-237661 R5-240838 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
29 |  | 38.521-2 Tx | 6.4.2.2 | Carrier leakage | adding Release-17 FR2 PC7 Carrier leakage | Nokia | RAN5#100 (Aug-23) | R5-233552 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
30 |  | 38.521-2 Tx | 6.4.2.3 | In-band emissions | adding Release-17 FR2 PC7 In-band emissions | Nokia | RAN5#100 (Aug-23) | R5-233553 |  | 1 | 100% | 100% |  |  | 100%
31 |  | 38.521-2 Tx | 6.6.1 | Beam correspondence - EIRP | adding Release-17 FR2 PC7 Beam correspondence | Huawei | RAN5#100 (Aug-23) | R5-233554 |  | 1 | 100% | 100% |  |  | 100%
32 |  | 38.521-2 Tx | 6.6.2 | Enhanced Beam correspondence – EIRP | adding Release-17 FR2 PC7 Beam correspondence | Huawei | RAN5#100 (Aug-23) | R5-233554 |  | 1 | 100% | 100% |  |  | 100%
33 |  | 38.521-2 Tx | Multi places | Multi sections | Checking all test cases and adding PC7 to configuration tables where 'inner full configuration' is used for testing | Qualcomm | RAN5#99 (May-23) | R5-233206 R5-232618 | Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
TS 38.521-2: FR2 RF test cases - Rx
Receiver characteristics(Clause 7)
34 |  | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | adding Release-17 FR2 PC7 Reference sensitivity power level | Qualcomm | RAN5#99 (May-23) | R5-232617 |  | 1 | 100% | 100% |  |  | 100%
35 |  | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | adding Release-17 FR2 PC7 EIS spherical coverage | Qualcomm | RAN5#99 (May-23) | R5-233719 | MU and TT for PC3 is complete. Due to lack of deployment interest, MU and TT for PC7 for RedCap UE which is still missing is out of scope of this WI | 1 | 100% | 100% |  |  | 100%
TS 38.521-4: Demod/QSI reporting test cases
36 |  | 38.521-4 | 3 | Definitions, symbols and abbreviations | definitions, symbols and abbreaviations respectively for RedCap | Ericsson | RAN5#99 (May-23) | R5-226690 |  | 1 | 100% | 100% |  | 100%
37 |  | 38.521-4 | 5.1.1.11 | Applicability of requirements for RedCap | Add new table for Requirements applicability for RedCap | Ericsson | RAN5#99 (May-23) | R5-227806 R5-241143 |  | 1 | 100% | 100% |  | 100%
38 |  | 38.521-4 | 5.2.1 | 1RX requirements (Void) | Remove void | Ericsson | RAN5#99 (May-23) |  |  | 0 | 100% | 100% |  | 100%
39 |  | 38.521-4 | 5.2.1.1 | FDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
40 | Y | 38.521-4 | 5.2.1.1.1 | 1Rx FDD FR1 PDSCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-226687 R5-231697 R5-230682 R5-230683 R5-232569r1 R5-235686 R5-241113 R5-244829 | SNR in test requirements table is within square brackets. | 1 | 100% | 100% |  | 100%
41 |  | 38.521-4 | 5.2.1.2 | TDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
42 | Y | 38.521-4 | 5.2.1.2.1 | 1Rx TDD FR1 PDSCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-234548 R5-244829 R5-241113 |  | 1 | 100% | 100% |  | 100%
43 | Y | 38.521-4 | 5.2.2.1.17 | 2Rx FDD FR1 PDSCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-230702 R5-235689 |  | 1 | 100% | 100% |  | 100%
44 | Y | 38.521-4 | 5.2.2.2.18 | 2Rx TDD FR1 PDSCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-230703 R5-233010r2 R5-235689 |  | 1 | 100% | 100% |  | 100%
45 |  | 38.521-4 | 5.3.1 | 1RX requirements (Void) | Remove void | Ericsson | RAN5#99 (May-23) |  |  | 0
46 |  | 38.521-4 | 5.3.1.1 | FDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
47 | Y | 38.521-4 | 5.3.1.1.1 | 1Rx FDD FR1 PDCCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-234550 R5-241113 |  | 1 | 100% | 100% |  | 100%
48 |  | 38.521-4 | 5.3.1.2 | TDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
49 | Y | 38.521-4 | 5.3.1.2.1 | 1Rx TDD FR1 PDCCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-230706 R5-235690 R5-235687 R5-241113 |  | 1 | 100% | 100% |  | 100%
50 | Y | 38.521-4 | 5.3.2.1.4 | 2Rx FDD FR1 PDCCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-233598 R5-235689 R5-235690 |  | 1 | 100% | 100% |  | 100%
51 | Y | 38.521-4 | 5.3.2.2.4 | 2Rx TDD FR1 PDCCH performance for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-232568r2 R5-235689 R5-235690 R5-240827 |  | 1 | 100% | 100% |  | 100%
52 | Y | 38.521-4 | 5.5.3 | FR1 Sustained downlink data rate performance for RedCap | New test case | Qualcomm | RAN5#99 (May-23) | R5-237289r2 |  | 1 | 100% | 100% |  | 100%
53 |  | 38.521-4 | 6.1.1 | Applicability of requirements | Updates as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-226688 R5-230724 |  | 1 | 100% | 100% |  | 100%
54 |  | 38.521-4 | 6.1.1.6 | Applicability of requirements for RedCap | New clause | Ericsson | RAN5#99 (May-23) | R5-226688 R5-230724 R5-232570 |  | 1 | 100% | 100% |  | 100%
55 |  | 38.521-4 | 6.2.1 | 1RX requirements (Void) | Remove void | Ericsson | RAN5#99 (May-23) |  |  | 0
56 |  | 38.521-4 | 6.2.1.1 | FDD | New caluse | Ericsson | RAN5#99 (May-23) |  |  | 0
57 |  | 38.521-4 | 6.2.1.1.1 | CQI reporting definition under AWGN conditions | New caluse | Ericsson | RAN5#99 (May-23) | R5-227807 |  | 1 | 100% | 100% |  | 100%
58 | Y | 38.521-4 | 6.2.1.1.1.1 | 1Rx FDD FR1 periodic CQI reporting under AWGN conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-227807 R5-232571 R5-241175 |  | 1 | 100% | 100% |  | 100%
59 |  | 38.521-4 | 6.2.1.1.2 | CQI reporting definition under fading conditions | New caluse |  | RAN5#99 (May-23)
60 | Y | 38.521-4 | 6.2.1.1.2.1 | 1Rx FDD FR1 periodic wideband CQI reporting under fading conditions for RedCap | New test case | Qualcomm | RAN5#99 (May-23) | R5-241142 |  | 1 | 100% | 100% |  | 100%
61 |  | 38.521-4 | 6.2.1.2 | TDD | New caluse | Ericsson | RAN5#99 (May-23) | R5-232572
62 |  | 38.521-4 | 6.2.1.2.1 | CQI reporting definition under AWGN conditions | New caluse | Ericsson | RAN5#99 (May-23) | R5-232572 |  | 1 | 100% | 100% |  | 100%
63 | Y | 38.521-4 | 6.2.1.2.1.1 | 1Rx TDD FR1 periodic CQI reporting under AWGN conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-232572 R5-241175 |  | 1 | 100% | 100% |  | 100%
64 |  | 38.521-4 | 6.2.1.2.2 | CQI reporting definition under fading conditions | New caluse | Ericsson | RAN5#99 (May-23) | R5-232573 |  | 1 | 100% | 100% |  | 100%
65 | Y | 38.521-4 | 6.2.1.2.2.1 | 1Rx TDD FR1 periodic wideband CQI reporting under fading conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-232573 R5-243110 |  | 1 | 100% | 100% |  | 100%
66 | Y | 38.521-4 | 6.2.2.1.1.4 | 2Rx FDD FR1 periodic CQI reporting under AWGN conditions for RedCap | New test case | Qualcomm | RAN5#99 (May-23) | R5-227809 R5-230057 R5-230707 R5-234274r1 R5-234916 |  | 1 | 100% | 100% |  | 100%
67 | Y | 38.521-4 | 6.2.2.1.2.4 | 2Rx FDD FR1 periodic wideband CQI reporting under fading conditions for RedCap | New test case | Qualcomm | RAN5#99 (May-23) | R5-227810 R5-230707 R5-231305 R5-234274r1 R5-234916 R5-236513 |  | 1 | 100% | 100% |  | 100%
68 | Y | 38.521-4 | 6.2.2.2.1.5 | 2Rx TDD FR1 periodic CQI reporting under AWGN conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-235688 R5-237212 R5-241175 |  | 1 | 100% | 100% |  | 100%
69 | Y | 38.521-4 | 6.2.2.2.2.4 | 2Rx TDD FR1 periodic wideband CQI reporting under fading conditions for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-234824 R5-237291 |  | 1 | 100% | 100% |  | 100%
70 |  | 38.521-4 | 6.3.1.1 | FDD | New clause |  |  |  |  | 0
71 | Y | 38.521-4 | 6.3.1.1.1 | 1Rx FDD Single PMI with 4TX TypeI-SinglePanel Codebook for RedCap | New test case | Huawei, Hisilicon | RAN5#102 (Feb-24) | R5-241960 | Edior's Note: Connection diagram is still TBD | 1 | 95% | 95% |  | 95%
72 |  | 38.521-4 | 6.3.1.2 | TDD | New clause |  |  |  |  | 0
73 | Y | 38.521-4 | 6.3.1.2.1 | 1Rx TDD Single PMI with 4TX TypeI-SinglePanel Codebook for RedCap | New test case | Huawei, Hisilicon | RAN5#102 (Feb-24) | R5-241817 | Edior's Note: Connection diagram is still TBD | 1 | 95% | 95% |  | 95%
74 | Y | 38.521-4 | 6.3.2.2.7 | 2Rx TDD Single PMI with 4TX TypeI-SinglePanel Codebook for RedCap | New test case | Huawei, Hisilicon | RAN5#102 (Feb-24) | R5-241961 |  | 1 | 100% | 100% |  | 100%
75 | Y | 38.521-4 | 6.4.2.1.1 | 2Rx FDD FR1 RI reporting for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-236511 R5-243695 |  | 1 | 100% | 100% |  | 100%
76 | Y | 38.521-4 | 6.4.2.2.1 | 2Rx TDD FR1 RI reporting for RedCap | New test case | Ericsson | RAN5#99 (May-23) | R5-236512 |  | 1 | 100% | 100% |  | 100%
77 |  | 38.521-4 | 7.1.1 | Applicability of requirements | Updates as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-230724 R5-234279 |  | 1 | 100% | 100% |  | 100%
78 |  | 38.521-4 | 7.1.1.7 | Applicability of requirements for RedCap | New clause | Ericsson | RAN5#99 (May-23) | R5-230724 R5-234279 |  | 0.1 | 100% | 100% |  | 100%
79 | Y | 38.521-4 | 7.5I.1 | FR2 Sustained downlink data rate performance for single carrier for RedCap | Update table 7.5.1.3-1 as per 38.101-4 | Qualcomm | RAN5#99 (May-23) | R5-241141 |  | 1 | 100% | 100% |  | 100%
80 |  | 38.521-4 | 8.1.1 | Applicability of requirements | Updates as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-230724 R5-234279 |  | 1 | 100% | 100% |  | 100%
81 |  | 38.521-4 | 8.1.1.6 | Applicability of requirements for RedCap | New clause | Ericsson | RAN5#99 (May-23) | R5-230724 R5-234279 |  | 0.1 | 100% | 100% |  | 100%
82 |  | 38.521-4 | Annex A | Measurement channels | Table A.4-1 as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-226690 R5-235691 R5-236515 |  | 1 | 100% | 100% |  | 100%
83 |  | 38.521-4 | Annex B | Propagation conditions | B.1.0 as per 38.101-4 | Ericsson | RAN5#99 (May-23) | R5-226690 |  | 1 | 100% | 100% |  | 100%
84 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances for FR1 | MU and TT for newly introduced RedCap Demod and CQI test cases | Ericsson | RAN5#99 (May-23) | R5-234825 R5-236514 R5-240864 R5-243310 |  | 1 | 100% | 100% |  | 100%
85 |  | 38.521-4 | Annex G | Minimum test time | To add minimum test time for RedCap Demod Test | Ericsson | RAN5#99 (May-23) | R5-226682 R5-230683 R5-233714 R5-233599 R5-232577 R5-237288 |  | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
86 |  | 38.522 | 4 | Test case conditions and selection criteria | Add test case applicability statements for the new test cases introduced for 38.521-1. | All test case owners | RAN5#100 (Aug-23) | R5-234667 R5-234673 R5-237778 R5-241849 R5-240831 R5-241140 R5-241962 R5-241379 R5-241848 | R5#103： R5-243910 R5-243915 R5-242984 R5-243396 | 1 | 100% | 100% |  | 100%
87 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1. | All test case owners | RAN5#100 (Aug-23) | R5-223791 R5-227117 R5-227874 R5-231813 R5-231814 R5-233715 |  | 1 | 100% | 100% |  | 100%
88 |  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-2. | All test case owners | RAN5#100 (Aug-23) |  | No new TCs introduced in FR2 | 0 | 100% | 100% |  |  | 100%
89 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4. | All test case owners | RAN5#100 (Aug-23) | R5-226702 R5-230679 R5-232578 R5-234826 R5-236516 R5-240831 R5-241140 R5-241379 R5-241848 |  | 1 | 100% | 100% |  | 100%
90 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. | All test case owners | RAN5#100 (Aug-23) | R5-226112，R5-230458 R5-232458，R5-232928 R5-235799，R5-234667 R5-234690，R5-236679r2 R5-240831，R5-241962 R5-241302，R5-241848 R5-241849 |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  | R5#103： R5-242904 R5-243746 R5-243344 R5-243907 R5-242878 R5-243918 R5-242880 R5-242881 R5-242986 R5-242987 R5-243025 R5-243095 R5-243712 R5-243341 R5-243342 R5-243384 R5-243903 R5-243919 R5-242882 R5-242883 R5-242884 R5-242885 R5-243774 R5-242887 R5-242892 R5-242893 R5-243775 R5-242895 R5-243776 R5-243777 R5-243778 R5-243779 R5-243780 R5-243781 R5-243782 R5-243783 R5-243713 R5-243343 R5-243904 R5-243388 |  | TBD
91 |  | 38.533 | 16 | NR standalone tests in FR1 for RedCap | New clause header |  | TBD |  |  | 0
92 |  | 38.533 | 16.1 | RRC_IDLE state mobility for RedCap | New sub-clause header |  |  |  |  | 0
93 |  | 38.533 | 16.1.1 | NR cell re-selection for RedCap | New sub-clause header |  |  |  |  | 0
94 | Y | 38.533 | 16.1.1.1 | NR SA FR1 Cell reselection for 1 Rx UE | Test in A.16.1.1.1 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227828 R5-231732 R5-233610 R5-233016r1 R5-234919 R5-234920r1 R5-234921 R5-237789 R5-241114 |  | 0.5 | 100% | 100% |  | 100%
95 | Y | 38.533 | 16.1.1.2 | NR SA FR1 Cell reselection for 2 Rx UE | Test in A.16.1.1.2 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227211 R5-231760 R5-233016r1 R5-234920r1 R5-234921 R5-241114 |  | 0.5 | 100% | 100% |  | 100%
96 | Y | 38.533 | 16.1.1.3 | NR SA FR1-FR1 Cell reselection for 1 Rx UE | Test in A.16.1.1.3 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227212 R5-231733 R5-234921 R5-235725 R5-241114 |  | 0.5 | 100% | 100% |  | 100%
97 | Y | 38.533 | 16.1.1.4 | NR SA FR1-FR1 Cell reselection for 2 Rx UE | Test in A.16.1.1.4 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227213 R5-231761 R5-234921 R5-241114 |  | 0.5 | 100% | 100% |  | 100%
98 | Y | 38.533 | 16.1.1.5 | NR SA FR1 Cell reselection for UE fulfilling stationary relaxed measurement criterion for 1 Rx UE | Test in A.16.1.1.5 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227214 R5-231734 R5-235696 R5-234921 R5-235726 R5-241114,R5-241299 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
99 | Y | 38.533 | 16.1.1.6 | NR SA FR1 Cell reselection for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.16.1.1.6 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227215 R5-231746 R5-235696 R5-234921 R5-241114,R5-241299 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
100 | Y | 38.533 | 16.1.1.7 | NR SA FR1-FR1 Cell reselection for UE fulfilling stationary relaxed measurement criterion for 1 Rx UE | Test in A.16.1.1.7 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227216 R5-231735 R5-235696 R5-234921 R5-235727 R5-241114,R5-241299 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
101 | Y | 38.533 | 16.1.1.8 | NR SA FR1-FR1 Cell reselection for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.16.1.1.8 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-227217 R5-231747 R5-235696 R5-234921 R5-241114,R5-241299 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
102 |  |  | 16.1.2 | NR - E-UTRA cell re-selection for RedCap | New sub-clause header |  | TBD | R5-227829 |  | 0
103 | Y | 38.533 | 16.1.2.1 | NR SA FR1 - E-UTRA Cell reselection to higher priority E-UTRA for 1 Rx UE | Test in A.16.1.2.1 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231123 R5-233616 R5-234000 R5-235728 R5-241114 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
104 | Y | 38.533 | 16.1.2.2 | NR SA FR1 - E-UTRA Cell reselection to higher priority E-UTRA for 2 Rx UE | Test in A.16.1.2.2 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231124 R5-233616 R5-234000 R5-241114 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
105 | Y | 38.533 | 16.1.2.3 | NR SA FR1 - E-UTRA Cell reselection to lower priority E-UTRA for 1 Rx UE | Test in A.16.1.2.3 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231125 R5-233616 R5-234000 R5-235729 R5-241114 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
106 | Y | 38.533 | 16.1.2.4 | NR SA FR1 - E-UTRA Cell reselection to lower priority E-UTRA for 2 Rx UE | Test in A.16.1.2.4 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231126 R5-233616 R5-234000 R5-241114 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
107 | Y | 38.533 | 16.1.2.5 | NR SA FR1 - E-UTRA Cell reselection to lower priority E-UTRA for UE fulfilling stationary relaxed measurement criterion for 1 Rx UE | Test in A.16.1.2.5 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231127 R5-233616 R5-235696 R5-234983r2 R5-241114,R5-241299 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
108 | Y | 38.533 | 16.1.2.6 | NR SA FR1 - E-UTRA Cell reselection to lower priority E-UTRA for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.16.1.2.6 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231128 R5-233616 R5-235696 R5-237020 R5-241114,R5-241299 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
109 |  |  | 16.2 | RRC_INACTIVE state mobility for RedCap | New sub-clause header
110 |  |  | 16.2.1 | Configured Grant based Small Data Transmissions for RedCap | New sub-clause header
111 | Y | 38.533 | 16.2.1.1 | NR SA FR1 CG-SDT for 1Rx UE | Test in A.16.2.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-237705，R5-240705 |  | 0.5 | 100% | 100% |  | 100%
112 | Y | 38.533 | 16.2.1.2 | NR SA FR1 CG-SDT for 2Rx UE | Test in A.16.2.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-237706，R5-240706 |  | 0.5 | 100% | 100% |  | 100%
113 |  |  | 16.3 | RRC_CONNECTED state mobility for RedCap | New sub-clause header |  |  | R5-226113
114 |  |  | 16.3.1 | Handover for RedCap | New sub-clause header |  |  | R5-226113
115 | Y | 38.533 | 16.3.1.1 | NR SA FR1 handover with known target cell for 1 Rx UE | Test in A.16.3.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230459 R5-234397 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
116 | Y | 38.533 | 16.3.1.2 | NR SA FR1 handover with known target cell for 2 Rx UE | Test in A.16.3.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230460 R5-235701 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
117 | Y | 38.533 | 16.3.1.3 | NR SA FR1 handover with unknown target cell for 1 Rx UE | Test in A.16.3.1.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230461 R5-232459 R5-234398 R5-240699 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
118 | Y | 38.533 | 16.3.1.4 | NR SA FR1 handover with unknown target cell for 2 Rx UE | Test in A.16.3.1.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230462 R5-232459 R5-234399 R5-240699 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
119 | Y | 38.533 | 16.3.1.5 | NR SA FR1-FR1 handover with unknown target cell for 1 Rx UE | Test in A.16.3.1.5 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230463 R5-232459 R5-234400 R5-240699 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
120 | Y | 38.533 | 16.3.1.6 | NR SA FR1-FR1 handover with unknown target cell for 2 Rx UE | Test in A.16.3.1.6 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230464 R5-232459 R5-240699 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
121 | Y | 38.533 | 16.3.1.7 | NR SA FR1 - E-UTRA handover with known target cell for 1Rx UE | Test in A.16.3.1.7 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226114 R5-236719r2 R5-237161r1 |  | 0.5 | 100% | 100% |  | 100%
122 | Y | 38.533 | 16.3.1.8 | NR SA FR1 - E-UTRA handover with known target cell for 2Rx UE | Test in A.16.3.1.8 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228013 R5-237161r1 R5-241298 |  | 0.5 | 100% | 100% |  | 100%
123 | Y | 38.533 | 16.3.1.9 | NR SA FR1 - E-UTRA handover with unknown target cell for 1 Rx UE | Test in A.16.3.1.9 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226116 R5-237786 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
124 | Y | 38.533 | 16.3.1.10 | NR SA FR1 - E-UTRA handover with unknown target cell for 2 Rx UE | Test in A.16.3.1.10 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228014 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
125 |  |  | 16.3.2 | RRC Connection Mobility Control for RedCap | New sub-clause header |  |  | R5-226118
126 |  |  | 16.3.2.1 | RRC re-establishment for RedCap | New sub-clause header |  |  | R5-226118
127 | Y | 38.533 | 16.3.2.1.1 | NR SA FR1 RRC re-establishment for 1 Rx UE | Test in A.16.3.2.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226119 R5-236721 R5-236736 R5-241300 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
128 | Y | 38.533 | 16.3.2.1.2 | NR SA FR1 RRC re-establishment for 2 Rx UE | Test in A.16.3.2.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226120 R5-232172 R5-236736 R5-241300 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
129 | Y | 38.533 | 16.3.2.1.3 | NR SA FR1-FR1 RRC re-establishment for 1 Rx UE | Test in A.16.3.2.1.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226121 R5-236722 R5-236736 R5-241300 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
130 | Y | 38.533 | 16.3.2.1.4 | NR SA FR1-FR1 RRC re-establishment for 2 Rx UE | Test in A.16.3.2.1.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226122 R5-232172 R5-235701 R5-236736 R5-241300 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
131 | Y | 38.533 | 16.3.2.1.5 | NR SA FR1 RRC re-establishment without serving cell timing for 1 Rx UE | Test in A.16.3.2.1.5 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226123 R5-235701 R5-237787 R5-241300 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
132 | Y | 38.533 | 16.3.2.1.6 | NR SA FR1 RRC re-establishment without serving cell timing for 2 Rx UE | Test in A.16.3.2.1.6 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226124 R5-232172 R5-235701 R5-236736 R5-241300 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
133 |  | 38.533 | 16.3.2.2 | Random Access for RedCap |  |  | TBD | R5-226125
134 | Y | 38.533 | 16.3.2.2.1 | NR SA FR1 4-step RA type contention based random access test in FR1 for NR standalone for 1 Rx UE | Test in A.16.3.2.2.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226126 R5-236724 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
135 | Y | 38.533 | 16.3.2.2.2 | NR SA FR1 4-step RA type contention based random access test in FR1 for NR standalone for 2 Rx UE | Test in A.16.3.2.2.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226127 R5-232172 R5-235700 R5-240707 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
136 | Y | 38.533 | 16.3.2.2.3 | NR SA FR1 4-step RA type non-contention based random access test in FR1 for NR standalone for 1 Rx UE | Test in A.16.3.2.2.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226128 R5-236725 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
137 | Y | 38.533 | 16.3.2.2.4 | NR SA FR1 4-step RA type non-contention based random access test in FR1 for NR standalone for 2 Rx UE | Test in A.16.3.2.2.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226129 R5-232172 R5-235700 R5-240707 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
138 | Y | 38.533 | 16.3.2.2.5 | NR SA FR1 2-step RA type contention based random access test in FR1 for NR standalone for 1 Rx UE | Test in A.16.3.2.2.5 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228015 R5-236726 R5-237104 R5-237105r1 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
139 | Y | 38.533 | 16.3.2.2.6 | NR SA FR1 2-step RA type contention based random access test in FR1 for NR standalone for 2 Rx UE | Test in A.16.3.2.2.6 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228016 R5-232172 R5-237103 R5-237104 R5-237105r1 R5-240707 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
140 | Y | 38.533 | 16.3.2.2.7 | NR SA FR1 2-step RA type non-contention based test in FR1 for NR standalone for 1 RX UE | Test in A.16.3.2.2.7 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228017 R5-236727 R5-237104 R5-237105r1 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
141 | Y | 38.533 | 16.3.2.2.8 | NR SA FR1 2-step RA type non-contention based test in FR1 for NR standalone for 2 RX UE | Test in A.16.3.2.2.8 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228018 R5-232172 R5-237104 R5-237105r1 R5-240707,R5-241227 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
142 |  |  | 16.3.2.3 | RRC Connection Release with Redirection for RedCap | New sub-clause header |  |  | R5-226134
143 | Y | 38.533 | 16.3.2.3.1 | NR SA FR1-FR1 RRC connection release with redirection for 1 Rx UE | Test in A.16.3.2.3.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226135 R5-236728 R5-236736 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
144 | Y | 38.533 | 16.3.2.3.2 | NR SA FR1-FR1 RRC connection release with redirection for 2 Rx UE | Test in A.16.3.2.3.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228019 R5-232172 R5-236736 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
145 | Y | 38.533 | 16.3.2.3.3 | NR SA FR1 - E-UTRA RRC connection release with redirection for 1 Rx UE | Test in A.16.3.2.3.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228020 R5-237788 R5-236736 R5-241115 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
146 | Y | 38.533 | 16.3.2.3.4 | NR SA FR1 - E-UTRA RRC connection release with redirection for 2 Rx UE | Test in A.16.3.2.3.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228021 R5-232172 R5-236736 R5-241115 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
147 |  |  | 16.4 | Timing for RedCap | New sub-clause header |  |  | R5-226139
148 |  |  | 16.4.1 | UE transmit timing for RedCap | New sub-clause header |  |  | R5-226139
149 | Y | 38.533 | 16.4.1.1 | NR SA FR1 NR UE transmit timing accuracy for 1Rx UE | Test in A.16.4.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228022 R5-234999 R5-237220 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
150 | Y | 38.533 | 16.4.1.2 | NR SA FR1 NR UE transmit timing accuracy for 2Rx UE | Test in A.16.4.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-228023 R5-234999 R5-241964 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
151 |  |  | 16.4.2 | UE timer accuracy for RedCap | New sub-clause header
152 |  |  | 16.4.3 | Timing advance for RedCap | New sub-clause header
153 | Y | 38.533 | 16.4.3.1 | NR SA FR1 timing advance adjustment accuracy for 1 Rx UE | Test in A.16.4.3.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230465 R5-234999 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
154 | Y | 38.533 | 16.4.3.2 | NR SA FR1 timing advance adjustment accuracy for 2 Rx UE | Test in A.16.4.3.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230466 R5-234999 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
155 |  |  | 16.5 | Signalling characteristics for RedCap | New sub-clause header |  |  | R5-226142
156 |  |  | 16.5.1 | Radio link Monitoring for RedCap | New sub-clause header |  |  | R5-226142
157 | Y | 38.533 | 16.5.1.1 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with SSB-based RLM RS in non-DRX mode for 1 Rx UE | Test in A.16.5.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226143 R5-234401 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
158 | Y | 38.533 | 16.5.1.2 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with SSB-based RLM RS in non-DRX mode for 2 Rx UE | Test in A.16.5.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226144 R5-235702 R5-241964 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
159 | Y | 38.533 | 16.5.1.3 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with SSB-based RLM RS in non-DRX mode for 1 Rx UE | Test in A.16.5.1.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226145 R5-234402 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
160 | Y | 38.533 | 16.5.1.4 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with SSB-based RLM RS in non-DRX mode for 2 Rx UE | Test in A.16.5.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226146 R5-235702 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
161 | Y | 38.533 | 16.5.1.5 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with SSB-based RLM RS in DRX mode for 1 Rx UE | Test in A.16.5.1.5 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233612 R5-233998 R5-234664 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
162 | Y | 38.533 | 16.5.1.6 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with SSB-based RLM RS in DRX mode for 2 Rx UE | Test in A.16.5.1.6 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233612 R5-233998 R5-234664 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
163 | Y | 38.533 | 16.5.1.7 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with SSB-based RLM RS in DRX mode for 1 Rx UE | Test in A.16.5.1.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226147 R5-234404 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
164 | Y | 38.533 | 16.5.1.8 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with SSB-based RLM RS in DRX mode for 2 Rx UE | Test in A.16.5.1.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226148 R5-235702 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
165 | Y | 38.533 | 16.5.1.9 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with CSI-RS-based RLM in non-DRX mode for 1 Rx UE | Test in A.16.5.1.9 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230467 R5-234405 R5-241965 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
166 | Y | 38.533 | 16.5.1.10 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with CSI-RS-based RLM in non-DRX mode for 2 Rx UE | Test in A.16.5.1.10 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230468 R5-236825 R5-241965 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
167 | Y | 38.533 | 16.5.1.11 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with CSI-RS-based RLM in non-DRX mode for 1 Rx UE | Test in A.16.5.1.11 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230469 R5-234406 R5-241965 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
168 | Y | 38.533 | 16.5.1.12 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with CSI-RS-based RLM in non-DRX mode for 2 Rx UE | Test in A.16.5.1.12 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230470 R5-235702 R5-236825 R5-241965 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
169 | Y | 38.533 | 16.5.1.13 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with CSI-RS-based RLM in DRX mode for 1 Rx UE | Test in A.16.5.1.13 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230471 R5-234407 R5-241965 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
170 | Y | 38.533 | 16.5.1.14 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for FR1 PCell configured with CSI-RS-based RLM in DRX mode for 2 Rx UE | Test in A.16.5.1.14 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231759 R5-236825 R5-241965 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
171 | Y | 38.533 | 16.5.1.15 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with CSI-RS-based RLM in DRX mode for 1 Rx UE | Test in A.16.5.1.15 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230473 R5-234408 R5-241965 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
172 | Y | 38.533 | 16.5.1.16 | NR SA FR1 Radio Link Monitoring In-sync Test for FR1 PCell configured with CSI-RS-based RLM in DRX mode for 2 Rx UE | Test in A.16.5.1.16 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230474 R5-235702 R5-235121r1 R5-235251 R5-236825 R5-241965 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
173 |  |  | 16.5.2 | Beam Failure Detection and Link recovery procedures for RedCap | New sub-clause header |  |  | R5-226149
174 | Y | 38.533 | 16.5.2.1 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with SSB-based BFD and LR in non-DRX mode for 1 Rx UE | Test in A.16.5.5.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226150 R5-232460 R5-236730 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
175 | Y | 38.533 | 16.5.2.2 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with SSB-based BFD and LR in non-DRX mode for 2 Rx UE | Test in A.16.5.5.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-228024 R5-232460 R5-237709 R5-240695 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
176 | Y | 38.533 | 16.5.2.3 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with SSB-based BFD and LR in DRX mode for 1 Rx UE | Test in A.16.5.5.3 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233613 R5-233998 R5-234664 R5-236736 R5-241115 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
177 | Y | 38.533 | 16.5.2.4 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with SSB-based BFD and LR in DRX mode for 2 Rx UE | Test in A.16.5.5.4 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233613 R5-234664 R5-237710 R5-236736 R5-241116,R5-241115 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
178 | Y | 38.533 | 16.5.2.5 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with CSI-RS-based BFD and LR in non-DRX mode for 1 Rx UE | Test in A.16.5.5.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230475 R5-236731 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
179 | Y | 38.533 | 16.5.2.6 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with CSI-RS-based BFD and LR in non-DRX mode for 2 Rx UE | Test in A.16.5.5.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230476 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
180 | Y | 38.533 | 16.5.2.7 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with CSI-RS-based BFD and LR in DRX mode for 1 Rx UE | Test in A.16.5.5.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230477 R5-236732 R5-245958 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
181 | Y | 38.533 | 16.5.2.8 | NR SA FR1 Beam Failure Detection and Link Recovery Test for FR1 PCell configured with CSI-RS-based BFD and LR in DRX mode for 2 Rx UE | Test in A.16.5.5.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230478 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
182 |  | 38.533 | 16.5.3 | Active BWP switch | New sub-clause header
183 |  | 38.533 | 16.5.3.1 | DCI-based and timer-based active BWP switch for RedCap | New sub-clause header
184 | Y | 38.533 | 16.5.3.1.1 | NR SA FR1 NR SA FR1 DL active BWP switch with non-DRX in SA for 1 Rx UE | Test in A.16.5.3.1.1 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233614 R5-234664 R5-234999 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
185 | Y | 38.533 | 16.5.3.1.2 | NR SA FR1 NR SA FR1 DL active BWP switch with non-DRX in SA for 2 Rx UE | Test in A.16.5.3.1.2 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233614 R5-234664 R5-234999 R5-236826 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
186 |  |  | 16.5.3.2 | RRC-based Active BWP Switch for RedCap | New sub-clause header
187 | Y | 38.533 | 16.5.3.2.1 | NR SA FR1 NR SA FR1 DL active BWP switch of Cell with non-DRX in SA for 1 Rx UE | Test in A.16.5.3.2.1 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233615 R5-233889 R5-233998 R5-234664 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
188 | Y | 38.533 | 16.5.3.2.2 | NR SA FR1 NR SA FR1 DL active BWP switch of Cell with non-DRX in SA for 2 Rx UE | Test in A.16.5.3.2.2 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-233615 R5-233889 R5-233998 R5-234664 R5-236826 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
189 |  |  | 16.5.4 | UE specific CBW change for RedCap | New sub-clause header
190 | Y | 38.533 | 16.5.4.1 | NR SA FR1 UE specific CBW change on PCell in FR1 in non-DRX for 1 Rx UE | Test in A.16.5.8.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230479 R5-240696 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
191 | Y | 38.533 | 16.5.4.2 | NR SA FR1 UE specific CBW change on PCell in FR1 in non-DRX for 2 Rx UE | Test in A.16.5.8.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230480 R5-240696 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
192 |  |  | 16.6 | Measurement procedure for RedCap | New sub-clause header |  |  | R5-226152
193 |  |  | 16.6.1 | Intra-frequency Measurements for RedCap | New sub-clause header |  |  | R5-226152
194 | Y | 38.533 | 16.6.1.1 | NR SA FR1 Event triggered reporting tests without gap under non-DRX for 1 Rx UE | Test in A.16.6.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230481 R5-232462 R5-234409 R5-235696 R5-236734，R5-240699 R5-244110 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
195 | Y | 38.533 | 16.6.1.2 | NR SA FR1 Event triggered reporting tests without gap under non-DRX for 2 Rx UE | Test in A.16.6.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230482 R5-232462 R5-236734，R5-240699 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
196 | Y | 38.533 | 16.6.1.3 | NR SA FR1 Event triggered reporting tests without gap under DRX for 1 Rx UE | Test in A.16.6.1.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226153 R5-232461 R5-233999 R5-234410 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
197 | Y | 38.533 | 16.6.1.4 | NR SA FR1 Event triggered reporting tests without gap under DRX for 2 Rx UE | Test in A.16.6.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226154 R5-232172 R5-232461 R5-233999 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
198 | Y | 38.533 | 16.6.1.5 | NR SA FR1 Event triggered reporting tests with per-UE gaps under non-DRX for 1 Rx UE | Test in A.16.6.1.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230483 R5-232461 R5-233999 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
199 | Y | 38.533 | 16.6.1.6 | NR SA FR1 Event triggered reporting tests with per-UE gaps under non-DRX for 2 Rx UE | Test in A.16.6.1.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230484 R5-232461 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
200 | Y | 38.533 | 16.6.1.7 | NR SA FR1 Event triggered reporting tests with per-UE gaps under DRX for 1 Rx UE | Test in A.16.6.1.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226155 R5-232461 R5-235695 R5-233999 R5-234412 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
201 | Y | 38.533 | 16.6.1.8 | NR SA FR1 Event triggered reporting tests with per-UE gaps under DRX for 2 Rx UE | Test in A.16.6.1.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226156 R5-232171 R5-232172 R5-232461 R5-233999 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
202 | Y | 38.533 | 16.6.1.9 | NR SA FR1 Event triggered reporting tests without gap under non-DRX with SSB index reading for 1 Rx UE | Test in A.16.6.1.9 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230485 R5-232462 R5-234413 R5-236734，R5-240699 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
203 | Y | 38.533 | 16.6.1.10 | NR SA FR1 Event triggered reporting tests without gap under non-DRX with SSB index reading for 2 Rx UE | Test in A.16.6.1.10 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230486 R5-232462 R5-236734，R5-240699 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
204 | Y | 38.533 | 16.6.1.11 | NR SA FR1 Event triggered reporting tests with per-UE gaps under non-DRX with SSB index reading for 1 Rx UE | Test in A.16.6.1.11 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226157 R5-232461 R5-235695 R5-234414 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
205 | Y | 38.533 | 16.6.1.12 | NR SA FR1 Event triggered reporting tests with per-UE gaps under non-DRX with SSB index reading for 2 Rx UE | Test in A.16.6.1.12 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226158 R5-232171 R5-232172 R5-232461 R5-234924 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
206 |  |  | 16.6.2 | Inter-frequency Measurements for RedCap | New sub-clause header
207 | Y | 38.533 | 16.6.2.1 | NR SA FR1-FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used for 1 Rx UE | Test in A.16.6.2.1 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234984r2 R5-237001r1 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
208 | Y | 38.533 | 16.6.2.2 | NR SA FR1-FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used for 2 Rx UE | Test in A.16.6.2.2 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234985r1 R5-237002r1 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
209 | Y | 38.533 | 16.6.2.3 | NR SA FR1-FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used for 1 Rx UE | Test in A.16.6.2.3 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234986r1 R5-237003r1 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
210 | Y | 38.533 | 16.6.2.4 | NR SA FR1-FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used for 2 Rx UE | Test in A.16.6.2.4 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234987r1 R5-237004 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
211 | Y | 38.533 | 16.6.2.5 | NR SA FR1-FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is not used for 1 Rx UE | Test in A.16.6.2.5 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-237005 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
212 | Y | 38.533 | 16.6.2.6 | NR SA FR1-FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is not used for 2 Rx UE | Test in A.16.6.2.6 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-237006 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
213 | Y | 38.533 | 16.6.2.7 | NR SA FR1-FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is used for 1 Rx UE | Test in A.16.6.2.7 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234990r1 R5-237007 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
214 | Y | 38.533 | 16.6.2.8 | NR SA FR1-FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is used for 2 Rx UE | Test in A.16.6.2.8 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234991r1 R5-237008 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
215 | Y | 38.533 | 16.6.2.9 | NR SA FR1-FR1 Event triggered reporting tests with additional mandatory gap pattern for 1 Rx UE | Test in A.16.6.2.9 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234992r1 R5-237009 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
216 | Y | 38.533 | 16.6.2.10 | NR SA FR1-FR1 Event triggered reporting tests with additional mandatory gap pattern for 2 Rx UE | Test in A.16.6.2.10 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234993r1 R5-237010r1 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
217 | Y | 38.533 | 16.6.2.11 | NR SA FR1-FR1 Event triggered reporting tests for FR1 when DRX is used for 1 Rx UE | Test in A.16.6.2.11 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234994r1 R5-237011 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
218 | Y | 38.533 | 16.6.2.12 | NR SA FR1-FR1 Event triggered reporting tests for FR1 when DRX is used for 2 Rx UE | Test in A.16.6.2.12 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-234995r1 R5-237012r1 R5-240694r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
219 |  |  | 16.6.3 | Inter-RAT Measurements for RedCap | New sub-clause header
220 | Y | 38.533 | 16.6.3.1 | NR - E-UTRA event-triggered reporting in non-DRX for 1 Rx UE | Test in A.16.6.3.1 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-240794r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
221 | Y | 38.533 | 16.6.3.2 | NR - E-UTRA event-triggered reporting in non-DRX for 2 Rx UE | Test in A.16.6.3.2 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-240795r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
222 | Y | 38.533 | 16.6.3.3 | NR - E-UTRA event-triggered reporting in DRX for 1 Rx UE | Test in A.16.6.3.3 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-240796r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
223 | Y | 38.533 | 16.6.3.4 | NR - E-UTRA event-triggered reporting in DRX for 2 Rx UE | Test in A.16.6.3.4 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-240797r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
224 |  | 38.533 | 16.6.4 | L1-RSRP measurement for beam reporting for RedCap | New sub-clause header |  |  | R5-226159 |  | 0
225 | Y | 38.533 | 16.6.4.1 | NR SA FR1 SSB based L1-RSRP measurement when DRX is not used for 1 Rx UE | Test in A.16.6.4.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226160 R5-234415 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
226 | Y | 38.533 | 16.6.4.2 | NR SA FR1 SSB based L1-RSRP measurement when DRX is not used for 2 Rx UE | Test in A.16.6.4.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-228025 R5-235698 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
227 | Y | 38.533 | 16.6.4.3 | NR SA FR1 SSB based L1-RSRP measurement when DRX is used for 1 Rx UE | Test in A.16.6.4.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226162 R5-234416 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
228 | Y | 38.533 | 16.6.4.4 | NR SA FR1 SSB based L1-RSRP measurement when DRX is used for 2 Rx UE | Test in A.16.6.4.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-228026 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
229 | Y | 38.533 | 16.6.4.5 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is not used for 1 Rx UE | Test in A.16.6.4.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230487 R5-234417 R5-245957 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
230 | Y | 38.533 | 16.6.4.6 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is not used for 2 Rx UE | Test in A.16.6.4.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230488 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
231 | Y | 38.533 | 16.6.4.7 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is used for 1 Rx UE | Test in A.16.6.4.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230489 R5-234418 R5-245957 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
232 | Y | 38.533 | 16.6.4.8 | NR SA FR1 CSI-RS based L1-RSRP measurement when DRX is used for 2 Rx UE | Test in A.16.6.4.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230490 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
233 |  | 38.533 | 16.6.5 | NR measurements with autonomous gaps for RedCap | New sub-clause header
234 | Y | 38.533 | 16.6.5.1 | NR SA FR1 CGI identification of NR neighbour cell for 1 Rx UE | Test in A.16.6.7.1 in TS 38.133 | Nokia | RAN5#101 (Nov-23) | R5-234356 R5-237785 R5-236735r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
235 | Y | 38.533 | 16.6.5.2 | NR SA FR1 CGI identification of NR neighbour cell for 2 Rx UE | Test in A.16.6.7.2 in TS 38.133 | Nokia | RAN5#101 (Nov-23) | R5-234357 R5-236219r1 R5-236735r1 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
236 | Y | 38.533 | 16.6.5.3 | NR SA FR1 - E-UTRA CGI Identification of E-UTRA neighbour cell for 1 Rx UE | Test in A.16.6.7.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-236682 R5-240204r2 R5-241886 |  | 0.5 | 100% | 100% |  | 100%
237 | Y | 38.533 | 16.6.5.4 | NR SA FR1 - E-UTRA CGI Identification of E-UTRA neighbour cell for 2 Rx UE | Test in A.16.6.7.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-236683r1 R5-240204r2 R5-240709 R5-244293 |  | 0.5 | 100% | 100% |  | 100%
238 |  |  | 16.7 | Measurement Performance requirements for RedCap | New sub-clause header
239 |  |  | 16.7.1 | SS-RSRP for RedCap | New sub-clause header
240 | Y | 38.533 | 16.7.1.1.1 | Intra-frequency measurements for RedCap for 1Rx UE | Test in A.16.7.1.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-237101 R5-237711 R5-241213 | Appicability missing | 0.5 | 100% | 100% |  | 100%
241 | Y | 38.533 | 16.7.1.1.2 | NR SA FR1 SS-RSRP absolute measurement accuracy for 1 Rx UE | Test in A.16.7.1.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-237101 R5-237711 R5-241214 | Appicability missing | 0.5 | 100% | 100% |  | 100%
|  | 38.533 | 16.7.1.2 | Intra-frequency measurements for RedCap for 2Rx UE | New sub-clause header
242 | Y | 38.533 | 16.7.1.2.1 | NR SA FR1 SS-RSRP absolute measurement accuracy for 2 Rx UE | Test in A.16.7.1.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-237101 R5-237711 R5-241215 | Appicability missing | 0.5 | 100% | 100% |  | 100%
243 | Y | 38.533 | 16.7.1.2.2 | NR SA FR1 SS-RSRP relative measurement accuracy for 2 Rx UE | Test in A.16.7.1.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-237101 R5-237711 R5-241216 | Appicability missing | 0.5 | 100% | 100% |  | 100%
|  | 38.533 | 16.7.1.3 | Inter-frequency measurements for RedCap for 1 Rx UE | New sub-clause header
244 | Y | 38.533 | 16.7.1.3.1 | NR SA FR1-FR1 SS-RSRP absolute measurement accuracy for 1 Rx UE | Test in A.16.7.1.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-241219 | TT analysis is missing Appicability missing | 0.5 | 100% | 100% |  | 100%
245 | Y | 38.533 | 16.7.1.3.2 | NR SA FR1-FR1 SS-RSRP relative measurement accuracy for 1 Rx UE | Test in A.16.7.1.3 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-241219 | TT analysis is missing Appicability missing | 0.5 | 100% | 100% |  | 100%
|  | 39.533 | 16.7.1.4 | Inter-frequency measurements for RedCap for 2 Rx UE | New sub-clause header
246 | Y | 38.533 | 16.7.1.4.1 | NR SA FR1-FR1 SS-RSRP absolute measurement accuracy for 2 Rx UE | Test in A.16.7.1.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-241220 | TT analysis is missing Appicability missing | 0.5 | 100% | 100% |  | 100%
247 | Y | 38.533 | 16.7.1.4.2 | NR SA FR1-FR1 SS-RSRP relative measurement accuracy for 2 Rx UE | Test in A.16.7.1.4 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-241220 | TT analysis is missing Appicability missing | 0.5 | 100% | 100% |  | 100%
|  |  | 16.7.2 | SS-RSRQ for RedCap | New sub-clause header
249 | Y | 38.533 | 16.7.2.1 | NR SA FR1 SS-RSRQ absolute measurement accuracy for 1 Rx UE | Test in A.16.7.2.1 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-241217 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
250 | Y | 38.533 | 16.7.2.2 | NR SA FR1 SS-RSRQ absolute measurement accuracy for 2 Rx UE | Test in A.16.7.2.2 in TS 38.133 | Rohde & Schwarz | RAN5#101 (Nov-23) | R5-241218 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
|  |  | 16.7.2.3 | Inter-frequency measurement accuracy for 1 Rx UE | New sub-clause header
251 | Y | 38.533 | 16.7.2.3.1 | NR SA FR1-FR1 SS-RSRQ absolute measurement accuracy for 1 Rx UE | Test in A.16.7.2.3 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237707 R5-240710 |  | 0.5 | 100% | 100% |  | 100%
252 | Y | 38.533 | 16.7.2.3.2 | NR SA FR1-FR1 SS-RSRQ relative measurement accuracy for 1 Rx UE | Test in A.16.7.2.3 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237708 R5-240711r2 |  | 0.5 | 100% | 100% |  | 100%
|  |  | 16.7.2.4 | Inter-frequency measurement accuracy for 2 Rx UE | New sub-clause header
253 | Y | 38.533 | 16.7.2.4.1 | NR SA FR1-FR1 SS-RSRQ absolute measurement accuracy for 2 Rx UE | Test in A.16.7.2.4 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237742 R5-240712r1 |  | 0.5 | 100% | 100% |  | 100%
254 | Y | 38.533 | 16.7.2.4.2 | NR SA FR1-FR1 SS-RSRQ relative measurement accuracy for 2 Rx UE | Test in A.16.7.2.4 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237743 R5-240713r1 |  | 0.5 | 100% | 100% |  | 100%
255 |  |  | 16.7.3 | SS-SINR for RedCap | New sub-clause header
256 | Y | 38.533 | 16.7.3.1 | NR SA FR1 SS-SINR absolute measurement accuracy for 1 Rx UE | Test in A.16.7.3.1 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237744 R5-240714 |  | 0.5 | 100% | 100% |  | 100%
257 | Y | 38.533 | 16.7.3.2 | NR SA FR1 SS-SINR absolute measurement accuracy for 2 Rx UE | Test in A.16.7.3.2 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237745 R5-240715 |  | 0.5 | 100% | 100% |  | 100%
|  |  | 16.7.3.3 | Inter-frequency measurement accuracy for 1 Rx UE | New sub-clause header
258 | Y | 38.533 | 16.7.3.3.1 | NR SA FR1-FR1 SS-SINR absolute measurement accuracy for 1 Rx UE | Test in A.16.7.3.3 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237746 R5-240716 |  | 0.5 | 100% | 100% |  | 100%
259 | Y | 38.533 | 16.7.3.3.2 | NR SA FR1-FR1 SS-SINR relative measurement accuracy for 1 Rx UE | Test in A.16.7.3.3 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237747 R5-240717 |  | 0.5 | 100% | 100% |  | 100%
|  |  | 16.7.3.4 | Inter-frequency measurement accuracy for 2 Rx UE | New sub-clause header
260 | Y | 38.533 | 16.7.3.4.1 | NR SA FR1-FR1 SS-SINR absolute measurement accuracy for 2 Rx UE | Test in A.16.7.3.4 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237748 R5-240718 |  | 0.5 | 100% | 100% |  | 100%
261 | Y | 38.533 | 16.7.3.4.2 | NR SA FR1-FR1 SS-SINR relative measurement accuracy for 2 Rx UE | Test in A.16.7.3.4 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237749 R5-241963 |  | 0.5 | 100% | 100% |  | 100%
262 |  |  | 16.7.4 | L1-RSRP measurement for beam reporting for RedCap | New sub-clause header
|  |  | 16.7.4.1 | SSB based L1-RSRP measurements for 1 Rx UE | New sub-clause header
263 | Y | 38.533 | 16.7.4.1.1 | NR SA FR1 SSB based L1-RSRP absolute measurement accuracy for 1 Rx UE | Test in A.16.7.4.1 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236694r1 R5-240720 |  | 0.5 | 100% | 100% |  | 100%
264 | Y | 38.533 | 16.7.4.1.2 | NR SA FR1 SSB based L1-RSRP relative measurement accuracy for 1 Rx UE | Test in A.16.7.4.1 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236695r1 R5-240721 |  | 0.5 | 100% | 100% |  | 100%
|  |  | 16.7.4.2 | SSB based L1-RSRP measurements for 2 Rx UE | New sub-clause header
265 | Y | 38.533 | 16.7.4.2.1 | NR SA FR1 SSB based L1-RSRP absolute measurement accuracy for 2 Rx UE | Test in A.16.7.4.2 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236696r1 R5-240722 |  | 0.5 | 100% | 100% |  | 100%
266 | Y | 38.533 | 16.7.4.2.2 | NR SA FR1 SSB based L1-RSRP relative measurement accuracy for 2 Rx UE | Test in A.16.7.4.2 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236697r1 R5-240723 |  | 0.5 | 100% | 100% |  | 100%
|  |  | 16.7.4.3 | CSI-RS based L1-RSRP measurements for 1 Rx UE | New sub-clause header
267 | Y | 38.533 | 16.7.4.3.1 | NR SA FR1 CSI-RS based L1-RSRP absolute measurement accuracy for 1 Rx UE | Test in A.16.7.4.3 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-2366981r1 R5-240724 R5-245959 |  | 0.5 | 100% | 100% |  | 100%
268 | Y | 38.533 | 16.7.4.3.2 | NR SA FR1 CSI-RS based L1-RSRP relative measurement accuracy for 1 Rx UE | Test in A.16.7.4.3 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236699r1 R5-240725 R5-245960 |  | 0.5 | 100% | 100% |  | 100%
|  |  | 16.7.3.4 | CSI-RS based L1-RSRP measurements for 2 Rx UE | New sub-clause header
269 | Y | 38.533 | 16.7.4.4.1 | NR SA FR1 CSI-RS based L1-RSRP absolute measurement accuracy for 2 Rx UE | Test in A.16.7.4.4 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236700r1 R5-240726 |  | 0.5 | 100% | 100% |  | 100%
270 | Y | 38.533 | 16.7.4.4.2 | NR SA FR1 CSI-RS based L1-RSRP relative measurement accuracy for 2 Rx UE | Test in A.16.7.4.4 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236701r1 R5-240727 |  | 0.5 | 100% | 100% |  | 100%
271 |  |  | 16.7.5 | E-UTRAN RSRP for RedCap | New sub-clause header
272 | Y | 38.533 | 16.7.5.1 | NR SA FR1 - E-UTRA RSRP absolute measurement accuracy for 1 Rx UE | Test in A.16.7.5.1 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237750 R5-240728 |  | 0.5 | 100% | 100% |  | 100%
273 | Y | 38.533 | 16.7.5.2 | NR SA FR1 - E-UTRA RSRP absolute measurement accuracy for 2 Rx UE | Test in A.16.7.5.2 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237751 R5-240729 |  | 0.5 | 100% | 100% |  | 100%
274 |  |  | 16.7.6 | E-UTRAN RSRQ for RedCap | New sub-clause header
275 | Y | 38.533 | 16.7.6.1 | NR SA FR1 - E-UTRA RSRQ absolute measurement accuracy for 1 Rx UE | Test in A.16.7.6.1 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236704 R5-240730 |  | 0.5 | 100% | 100% |  | 100%
276 | Y | 38.533 | 16.7.6.2 | NR SA FR1 - E-UTRA RSRQ absolute measurement accuracy for 2 Rx UE | Test in A.16.7.6.2 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236705 R5-240731 |  | 0.5 | 100% | 100% |  | 100%
277 |  |  | 17 | NR standalone tests in FR2 for RedCap | New clause header
278 |  |  | 17.1 | RRC_IDLE state mobility for RedCap | New sub-clause header
279 |  |  | 17.1.1 | NR cell re-selection for RedCap | New sub-clause header
280 | Y | 38.533 | 17.1.1.1 | NR SA FR2 Cell reselection for 2 Rx UE | Test in A.17.1.1.1 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231130 R5-232923 R5-235696 R5-236997 | RAN4 Phase 1 | 0.5 | 100% | 100% |  |  | 100%
281 | Y | 38.533 | 17.1.1.2 | NR SA FR2-FR2 Cell reselection for 2 Rx UE | Test in A.17.1.1.2 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231131 R5-232924 R5-235696 R5-236998 | RAN4 Phase 1 | 0.5 | 100% | 100% |  |  | 100%
282 | Y | 38.533 | 17.1.1.3 | NR SA FR2 Cell reselection for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.17.1.1.3 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231132 R5-232925 R5-236999 | RAN4 Phase 1 | 0.5 | 100% | 100% |  |  | 100%
283 | Y | 38.533 | 17.1.1.4 | NR SA FR2-FR2 Cell reselection for UE fulfilling stationary relaxed measurement criterion for 2 Rx UE | Test in A.17.1.1.4 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231133 R5-232926 R5-237000 | RAN4 Phase 1 | 0.5 | 100% | 100% |  |  | 100%
284 |  |  | 17.2 | RRC_INACTIVE state mobility for RedCap | New sub-clause header
285 |  |  | 17.2.1 | Configured Grant based Small Data Transmissions for RedCap | New sub-clause header
286 | Y | 38.533 | 17.2.1.1 | NR SA FR2 TA validation for CG-SDT for 2 Rx UE | Test in A.17.2.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-237752 |  | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
287 |  |  | 17.3 | RRC_CONNECTED state mobility for RedCap | New sub-clause header
288 |  |  | 17.3.1 | Handover for RedCap | New sub-clause header
289 | Y | 38.533 | 17.3.1.1 | NR SA FR2 handover with unknown target cell for 2 Rx UE | Test in A.17.3.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-237753 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
290 | Y | 38.533 | 17.3.1.2 | NR SA FR2-FR2 handover with unknown target cell for 2 Rx UE | Test in A.17.3.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-237754 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
291 |  |  | 17.3.2 | RRC Connection Mobility Control for RedCap | New sub-clause header |  |  | R5-226164
292 |  |  | 17.3.2.1 | RRC Re-establishment for RedCap | New sub-clause header |  |  | R5-226164
293 | Y | 38.533 | 17.3.2.1.1 | NR SA FR2 RRC Re-establishment for 2 Rx UE | Test in A.17.3.2.1.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226165 | RAN4 Phase 1 | 0.5 | 100% | 100% |  |  | 100%
294 | Y | 38.533 | 17.3.2.1.2 | NR SA FR2-FR2 RRC re-establishment for 2 Rx UE | Test in A.17.3.2.1.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226166 | RAN4 Phase 1 | 0.5 | 100% | 100% |  |  | 100%
295 | Y | 38.533 | 17.3.2.1.3 | NR SA FR2 RRC re-establishment without serving cell timing for 2 Rx UE | Test in A.17.3.2.1.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226167 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
296 |  |  | 17.3.2.2 | Random Access for RedCap | New sub-clause header
297 | Y | 38.533 | 17.3.2.2.1 | NR SA FR2 4-step RA type contention based random access test in FR2 for NR Standalone | Test in A.17.3.2.2.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230491 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
298 | Y | 38.533 | 17.3.2.2.2 | NR SA FR2 4-step RA type non-contention based random access test in FR2 for NR Standalone | Test in A.17.3.2.2.2 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230492 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
299 | Y | 38.533 | 17.3.2.2.3 | NR SA FR2 2-step RA type contention based random access test in FR2 for NR Standalone | Test in A.17.3.2.2.3 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230493 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
300 | Y | 38.533 | 17.3.2.2.4 | NR SA FR2 2-step RA type non-contention based random access test in FR2 for NR Standalone | Test in A.17.3.2.2.4 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-230494 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
301 |  |  | 17.3.2.3 | SA: RRC Connection Release with Redirection for RedCap | New sub-clause header
302 | Y | 38.533 | 17.3.2.3.1 | NR SA FR2-FR2 Redirection from NR in FR2 to NR in FR2 | Test in A.17.3.2.3.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-236709 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
303 |  |  | 17.4 | Timing for RedCap | New sub-clause header
304 |  |  | 17.4.1 | UE transmit timing for RedCap | New sub-clause header
305 | Y | 38.533 | 17.4.1.1 | NR SA FR2 NR UE Transmit Timing Test for FR2 | Test in A.17.4.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-237755 R5-240697 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
306 |  |  | 17.4.2 | UE timer accuracy for RedCap | New sub-clause header
307 |  |  | 17.4.3 | Timing advance for RedCap | New sub-clause header
308 | Y | 38.533 | 17.4.3.1 | NR SA FR2 SA FR2 timing advance adjustment accuracy | Test in A.17.4.3.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-236711 | RAN4 Phase 1 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
309 |  |  | 17.5 | Signaling characteristics for RedCap | New sub-clause header
310 |  |  | 17.5.1 | Radio link Monitoring for RedCap | New sub-clause header |  |  | R5-226168
311 | Y | 38.533 | 17.5.1.1 | NR SA FR2 Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with SSB-based RLM RS in non-DRX mode | Test in A.17.5.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226169 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
312 | Y | 38.533 | 17.5.1.2 | NR SA FR2 Radio Link Monitoring In-sync Test for FR2 PCell configured with SSB-based RLM RS in non-DRX mode | Test in A.17.5.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226170 R5-232463 R5-234386 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
313 | Y | 38.533 | 17.5.1.3 | NR SA FR2 Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with SSB-based RLM RS in DRX mode | Test in A.17.5.1.3 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-241296 | TT analysis is missing | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
314 | Y | 38.533 | 17.5.1.4 | NR SA FR2 Radio Link Monitoring In-sync Test for FR2 PCell configured with SSB-based RLM RS in DRX mode | Test in A.17.5.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226171 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
315 | Y | 38.533 | 17.5.1.5 | NR SA FR2 Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with CSI-RS-based RLM in non-DRX mode | Test in A.17.5.1.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-236712 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
316 | Y | 38.533 | 17.5.1.6 | NR SA FR2 Radio Link Monitoring In-sync Test for FR2 PCell configured with CSI-RS-based RLM in non-DRX mode | Test in A.17.5.1.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-236713 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
317 | Y | 38.533 | 17.5.1.7 | NR SA FR2 Radio Link Monitoring Out-of-sync Test for FR2 PCell configured with CSI-RS-based RLM in DRX mode | Test in A.17.5.1.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-237756 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
318 | Y | 38.533 | 17.5.1.8 | NR SA FR2 Radio Link Monitoring In-sync Test for FR2 PCell configured with CSI-RS-based RLM in DRX mode | Test in A.17.5.1.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-236715 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
319 | Y | 38.533 | 17.5.1.9 | NR SA FR2 UE Radio Link Monitoring Scheduling Restrictions on FR2 | Test in A.17.5.1.9 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230495 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
320 |  |  | 17.5.2 | Beam Failure Detection and Link recovery procedures for RedCap | New sub-clause header
321 | Y | 38.533 | 17.5.2.1 | NR SA FR2 Beam Failure Detection and Link Recovery Test for FR2 PCell configured with SSB-based BFD and LR in non-DRX mode | Test in A.17.5.2.1 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-241297 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 95%
322 | Y | 38.533 | 17.5.2.2 | NR SA FR2 Beam Failure Detection and Link Recovery Test for FR2 PCell configured with SSB-based BFD and LR in DRX mode | Test in A.17.5.2.2 in TS 38.133 | Qualcomm | RAN5#101 (Nov-23) | R5-241297 | RAN4 Phase 2 TT analysis is still missing | 0.5 | 100% | 100% |  |  | 95%
323 | Y | 38.533 | 17.5.2.3 | NR SA FR2 Beam Failure Detection and Link Recovery Test for FR2 PCell configured with CSI-RS-based BFD and LR in non-DRX mode | Test in A.17.5.2.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231721 R5-233654 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
324 | Y | 38.533 | 17.5.2.4 | NR SA FR2 Beam Failure Detection and Link Recovery Test for FR2 PCell configured with CSI-RS-based BFD and LR in DRX mode | Test in A.17.5.2.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231722 R5-233655 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
325 | Y | 38.533 | 17.5.2.5 | NR SA FR2 Scheduling availability restriction during Beam Failure Detection and Link Recovery for FR2 PCell configured with SSB-based BFD and LR in non-DRX mode | Test in A.17.5.2.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231723 R5-233656 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
326 |  |  | 17.5.3 | Active BWP switch for RedCap | New sub-clause header
327 |  |  | 17.5.3.1 | DCI-based and Timer-based Active BWP Switch | New sub-clause header
328 | Y | 38.533 | 17.5.3.1.1 | NR SA FR2 DCI-based and Timer-based DL active BWP switch for 2 Rx UE | Test in A.17.5.3.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240681 |  | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
329 |  |  | 17.5.3.2 | NR SA FR2 DL active BWP switch with non-DRX in SA | New sub-clause header
330 | Y | 38.533 | 17.5.3.2.1 | NR SA FR2 RRC-based DL active BWP switch for 2 Rx UE | Test in A.17.5.3.2.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240682 |  | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
331 |  |  | 17.5.4 | Active TCI state switch delay for RedCap | New sub-clause header
332 |  |  | 17.5.4.1 | MAC-CE based active TCI state switch for RedCap | New sub-clause header
333 | Y | 38.533 | 17.5.4.1.1 | NR SA FR2 NR PCell FR2 active TCI state switch for a known TCI state | Test in A.17.5.4.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-237757 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
334 |  |  | 17.5.4.2 | RRC based active TCI state switch for RedCap | New sub-clause header
335 | Y | 38.533 | 17.5.4.2.1 | NR SA FR2 NR PCell FR2 active TCI state switch for a known TCI state | Test in A.17.5.4.2.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-237758 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
336 |  |  | 17.5.5 | Uplink spatial relation switch delay | New sub-clause header
337 |  |  | 17.5.5.1 | MAC-CE based Spatial Relation switch | New sub-clause header
338 | Y | 38.533 | 17.5.5.1.1 | NR SA FR2 NR PCell FR2 spatial relation associated with known DL-RS | Test in A.17.5.5.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240683 |  | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
339 |  |  | 17.5.5.2 | RRC based spatial relation switch for RedCap | New sub-clause header
340 | Y | 38.533 | 17.5.5.2.1 | NR SA FR2 NR PCell FR2 spatial relation switch associated with a known DL-RS | Test in A.17.5.5.2.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240684 |  | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
341 |  |  | 17.5.6 | UE specific CBW change for RedCap | New sub-clause header
342 | Y | 38.533 | 17.5.6.1 | NR SA FR2 NR SA FR2 UE specific CBW change of PCell with non-DRX in SA | Test in A.17.5.6.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240685 |  | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
343 |  |  | 17.6 | Measurement procedure for RedCap | New sub-clause header |  |  | R5-226172
344 |  |  | 17.6.1 | Intra-frequency Measurements for RedCap | New sub-clause header |  |  | R5-226172
345 | Y | 38.533 | 17.6.1.1 | NR SA FR2 Event triggered reporting test without gap under non-DRX | Test in A.17.6.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-226173 R5-232467 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
346 | Y | 38.533 | 17.6.1.2 | NR SA FR2 Event triggered reporting test without gap under DRX | Test in A.17.6.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-233657 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
347 | Y | 38.533 | 17.6.1.3 | NR SA FR2 Event triggered reporting test with per-UE gaps under non-DRX | Test in A.17.6.1.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230499 R5-232469 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
348 | Y | 38.533 | 17.6.1.4 | NR SA FR2 Event triggered reporting test with per-UE gaps under DRX | Test in A.17.6.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230500 R5-232469 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
349 |  |  | 17.6.2 | Inter-frequency Measurements for RedCap | New sub-clause header
350 | Y | 38.533 | 17.6.2.1 | NR SA FR2-FR2 Event triggered reporting tests For FR2 without SSB time index detection when DRX is not used (PCell in FR2) | Test in A.17.6.2.1 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-240798 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
351 | Y | 38.533 | 17.6.2.2 | NR SA FR2-FR2 Event triggered reporting tests For FR2 without SSB time index detection when DRX is used (PCell in FR2) | Test in A.17.6.2.2 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-240799 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
352 | Y | 38.533 | 17.6.2.3 | NR SA FR2-FR2 Event triggered reporting tests For FR2 with SSB time index detection when DRX is not used (PCell in FR2) | Test in A.17.6.2.3 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-240800 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
353 | Y | 38.533 | 17.6.2.4 | NR SA FR2-FR2 Event triggered reporting tests For FR2 with SSB time index detection when DRX is used (PCell in FR2) | Test in A.17.6.2.4 in TS 38.133 | Ericsson | RAN5#101 (Nov-23) | R5-240801 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
354 |  |  | 17.6.3 | L1-RSRP measurement for beam reporting for RedCap | New sub-clause header
355 | Y | 38.533 | 17.6.3.1 | NR SA FR2 SSB based L1-RSRP measurement when DRX is not used | Test in A.17.6.3.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-231724 R5-233647 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
356 | Y | 38.533 | 17.6.3.2 | NR SA FR2 SSB based L1-RSRP measurement when DRX is used | Test in A.17.6.3.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230502 R5-232472 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
357 | Y | 38.533 | 17.6.3.3 | NR SA FR2 CSI-RS based L1-RSRP measurement when DRX is not used | Test in A.17.6.3.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230503 R5-232473 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
358 | Y | 38.533 | 17.6.3.4 | NR SA FR2 CSI-RS based L1-RSRP measurement when DRX is used | Test in A.17.6.3.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230504 R5-232474 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
359 |  |  | 17.6.4 | NR Measurements with autonomous gaps for RedCap | New sub-clause header
360 | Y | 38.533 | 17.6.4.1 | NR SA FR2 Interfrequency CGI reporting in autonomous gaps test (PCell in FR2) | Test in A.17.6.4.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-237759 R5-240698 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
361 |  |  | 17.7 | Measurement Performance requirements for RedCap | New sub-clause header
362 |  |  | 17.7.1 | SS-RSRP | New sub-clause header
363 | Y | 38.533 | 17.7.1.1 | NR SA FR2 Intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Test in A.17.7.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240686 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
364 | Y | 38.533 | 17.7.1.2 | NR SA FR2-FR2 Inter-frequency case measurement accuracy with FR2 serving cell and FR2 target cell | Test in A.17.7.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240687 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
365 |  |  | 17.7.2 | SS-RSRQ | New sub-clause header
366 | Y | 38.533 | 17.7.2.1 | NR SA FR2 Intra-frequency measurement accuracy with FR2 serving cell and FR2 target cell | Test in A.17.7.2.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240688 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
367 | Y | 38.533 | 17.7.2.2 | NR SA FR2-FR2 Inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell | Test in A.17.7.2.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240689 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
368 |  |  | 17.7.3 | L1-RSRP measurement for beam reporting for RedCap | New sub-clause header
369 | Y | 38.533 | 17.7.3.1 | NR SA FR2 SSB based L1-RSRP measurement | Test in A.17.7.3.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240690 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
370 | Y | 38.533 | 17.7.3.2 | NR SA FR2 CSI-RS based L1-RSRP measurement on resource set with repetition off | Test in A.17.7.3.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-240691 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
371 |  | 38.533 | 17.7.4 | SS-SINR measurement for RedCap | New sub-clause header
372 | Y | 38.533 | 17.7.4.1 | NR SA FR2 intra-frequency case measurement accuracy with FR2 serving cell and FR2 target cell for 2Rx UE | Test in A.17.7.4.1 in TS 38.133 | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-240692 | RAN4 Phase 2 | 0.5 | 100% (+5%) | 100% (+5%) |  |  | 100%
373 | Y | 38.533 | 17.7.4.2 | NR SA FR2-FR2 Inter-frequency measurement accuracy with FR2 serving cell and FR2 TDD target cell | Test in A.17.7.4.2 in TS 38.133 | Huawei | RAN5#103 (Nov-23) | R5-243783 | RAN4 Phase 2 | 0.5 | 100% (+100%) | 100% (+100%) |  |  | 100%
374 |  |  | 18 | E-UTRA standalone tests for NR RRM for RedCap | New clause header
375 |  |  | 18.1 | RRC_IDLE state mobility for RedCap | New sub-clause header
376 |  |  | 18.1.1 | Inter-RAT NR Cell re-selection for RedCap | New sub-clause header
377 | Y | 38.533 | 18.1.1.1 | E-UTRA - NR SA FR1 E-UTRA Cell reselection to higher priority NR target Cell in FR1 | Test in A.18.1.1.1 in TS 38.133 | Ericsson | RAN5#99 (May-23) | R5-231134 R5-235696 | RAN4 Phase 1 TT analysis is still missing | 0.5 | 100% | 100% |  | 100%
378 |  |  | 18.2 | RRC_CONNECTED state mobility for RedCap | New sub-clause header |  |  | R5-226174
379 |  |  | 18.2.1 | Handover for RedCap | New sub-clause header |  |  | R5-226174 | RAN4 Phase 1
380 | Y | 38.533 | 18.2.1.1 | E-UTRA - NR SA FR1 E-UTRAN - NR handover in FR1 | Test in A.18.2.1.1 in TS 38.133 | Huawei |  | R5-226175 |  | 0.5 | 100% | 100% |  | 100%
381 |  |  | 18.2.2 | RRC connection release with redirection for RedCap | New sub-clause header |  |  | R5-226176
382 | Y | 38.533 | 18.2.2.1 | E-UTRA - NR SA FR1 Redirection from E-UTRA to NR SA FR1 for redcap UE | Test in A.18.2.2.1 in TS 38.133 | Huawei | RAN5#99 (May-23) | R5-226177 R5-232475 | RAN4 Phase 1 | 0.5 | 100% | 100% |  | 100%
383 |  |  | 18.3 | Measurement procedure for RedCap | New sub-clause header
384 |  |  | 18.3.1 | E-UTRA - NR Measurements for RedCap | New sub-clause header
385 | Y | 38.533 | 18.3.1.1 | E-UTRA - NR SA FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is not used | Test in A.18.3.1.1 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230505 R5-234671 R5-241228,R5-241264 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
386 | Y | 38.533 | 18.3.1.2 | E-UTRA - NR SA FR1 Event triggered reporting tests for FR1 without SSB time index detection when DRX is used | Test in A.18.3.1.2 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230506 R5-234671 R5-241228,R5-241264 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
387 | Y | 38.533 | 18.3.1.3 | E-UTRA - NR SA FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is not used | Test in A.18.3.1.3 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230507 R5-234671 R5-241228,R5-241264 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
388 | Y | 38.533 | 18.3.1.4 | E-UTRA - NR SA FR1 Event triggered reporting tests for FR1 with SSB time index detection when DRX is used | Test in A.18.3.1.4 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230508 R5-234671 R5-241228,R5-241264 | RAN4 Phase 2 | 0.5 | 100% | 100% |  | 100%
389 | Y | 38.533 | 18.3.1.5 | E-UTRA - NR SA FR2 Event triggered reporting tests for FR2 without SSB time index detection when DRX is not used | Test in A.18.3.1.5 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230509 R5-232476r1 R5-241228,R5-241264 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
390 | Y | 38.533 | 18.3.1.6 | E-UTRA - NR SA FR2 Event triggered reporting tests for FR2 without SSB time index detection when DRX is used | Test in A.18.3.1.6 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230510 R5-232477r1 R5-241228,R5-241264 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
391 | Y | 38.533 | 18.3.1.7 | E-UTRA - NR SA FR2 Event triggered reporting tests for FR2 with SSB time index detection when DRX is not used | Test in A.18.3.1.7 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230511 R5-232478r1 R5-241228,R5-241264 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
392 | Y | 38.533 | 18.3.1.8 | E-UTRA - NR SA FR2 Event triggered reporting tests for FR2 with SSB time index detection when DRX is used | Test in A.18.3.1.8 in TS 38.133 | Huawei | RAN5#101 (Nov-23) | R5-230512 R5-232479r2 R5-241228 | RAN4 Phase 2 | 0.5 | 100% | 100% |  |  | 100%
393 |  | 38.533 | Clause 1-3 and Annex | Adding definition, RMC, side condition, cell mapping, uncertainty and test method for RedCap RRM test cases | Adding definition, RMC, side condition, cell mapping, uncertainty and test method for RedCap RRM test cases | Huawei | RAN5#97(Nov-22) | R5-226178,R5-227827 R5-226180,R5-226181 R5-227845,R5-226183 R5-230513,R5-230514 R5-230515,R5-231135 R5-232480,R5-233611 R5-232482,R5-233617 R5-235724,R5-234662 R5-234925r1,R5-235697 R5-234997,R5-235730 R5-235699,R5-237785 R5-236219r1,R5-237790 R5-237023,R5-236736 R5-236737,R5-236738 R5-240676r1, R5-240449 R5-240693r1,R5-241878 R5-240790,R5-240802 R5-241211 R5-245956 R5-245278 R5-245319 |  | 0.5 | 90% (+5%) | 90% (+5%) |  |  | 90%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
394 |  | 38.903 | 8 and attachment | Grouping and TT analysis of test cases defined in TS 38.533 | TT analysis grouping for RRM test cases |  | TBD | R5-227846,R5-227847,R5-227848 R5-227849,R5-227850,R5-227851 R5-227852,R5-227853,R5-227854 R5-226428,R5-227855,R5-227856 R5-227857,R5-227858,R5-227859 R5-226434,R5-226435,R5-226436 R5-226437,R5-226438,R5-226439 R5-227860,R5-231762,R5-230517 R5-230518,R5-230519,R5-230520 R5-230521,R5-230522,R5-230523 R5-230524,R5-230525,R5-231763 R5-231138,R5-231139,R5-231140 R5-231141,R5-231142,R5-232483 R5-232484,R5-232485,R5-232486 R5-232487,R5-232488,R5-233299 R5-235731,R5-234421,R5-234422 R5-234423,R5-234424,R5-235732 R5-234663,R5-234665,R5-234666 R5-234668,R5-234669,R5-234670 R5-234965r1,R5-234966,R5-234967 R5-234968r1,R5-234969,R5-234970 R5-236221,R5-236739r2,R5-236740 R5-236741,R5-236742,R5-236743 R5-236744r1,R5-236745,R5-236746 R5-236747,R5-237791,R5-236989 R5-237792,R5-240733,R5-240734 R5-240735,R5-240736,R5-240737 R5-240738,R5-240739,R5-240740r1 R5-240741,R5-240742,R5-240743 R5-241887,R5-241888,R5-241889 R5-240747,R5-240748,R5-240749 R5-241890,R5-241891,R5-240752 R5-240753,R5-240754,R5-240755 R5-240787,R5-240788,R5-240789 R5-241221,R5-241222,R5-241223 R5-241224,R5-241225,R5-241226 R5-241892 R5-243747 R5-242907 R5-242908 R5-245964 R5-245965 R5-245966 R5-245967 R5-244641 R5-244642 R5-245257 R5-245258 R5-245305 R5-245306 R5-245384 R5-245385 R5-245386 |  | 1 | 95% | 95% |  | 95%
395 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | MU analysis for Power class 7 |  | TBD |  |  | 0 | 100% | 100% |  |  | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
396 |  | 38.905 | 4 | Test coverage analysis | Add header, general text and table to list test point analysis for RedCap | Huawei | RAN5#98 (Feb-23) | R5-222903 |  | 1 | 100% | 100% |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
397 | Y | 38.523-1 | 6.1.2.26 | Cell Selection / Redcap | **** TP1: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except cell Barred status "true" for Redcap THEN: the UE considers the cell as barred and no camping on this cell can take place **** TP2: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except intraFreqReselectionRedCap in SIB1 is absent THEN: the UE considers the cell as barred and no camping on this cell can take place **** TP3: [Ref: 38.304 clause 5.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: a cell fulfils the requirements for a suitable cell except cell Barred status not "true" for Redcap THEN: the UE considers the cell suitable and camps on it | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-225346 R5-227156 R5-231531 R5-232981 |  | 1 | 100% | 100% |  | 100% | 100%
398 | Y | 38.523-1 | 6.1.2.27 | Cell reselection / inter-freguency / Redcap | **** TP1: [Ref: 38.331 clause 6.3.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: the serving cell broadcasts SIB4 with system information indication of frequencies which accept RedCap UEs THEN: the UE reselects the inter-frequency neighbor cell depending on SIB4 indication | Qualcomm | RAN5#96 (Aug-22) | R5-227536 R5-230435 R5-231532 R5-240441 |  | 1 | 100% | 100% |  | 100% | 100%
Layer 2
399 | Y | 38.523-1 | 7.1.1.1.15 | Random access procedure / RedCap UE / SI request | **** TP1: [Ref: ] WITH: UE in RRC_Idle State and initialUplinkBWP-RedCap and si-RequestConfigRedCap is configured in SIB1 of Serving Cell WHEN: one System information,which si-BroadcastStatus is set to notBroadcasting, is updated THEN: UE transmitted PRACH preamble for System information request using the PRACH preamble(s) and PRACH resource(s) in si-RequestConfigRedcap and retransmitted PRACH preamble when ra-ResponseWindow has expired **** TP2: [Ref: ] WITH: UE in RRC_Idle State and transmitted PRACH preamble for System information request WHEN: UE received a RAR message addressed to RA-RNTI and including matching RAPID only THEN: UE considers the RACH procedure to be successfully completed and informs the upper layer | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-232940 |  | 1 | 100% | 100% |  | 100% | 100%
400 | Y | 38.523-1 | 7.1.1.1.16 | Random access procedure / Redcap UE identification / Msg3-based / CCCH1 | **** TP1: [Ref: 38.321 clause 5.1 and 6.2.1] WITH: UE surpporting Redcap and in NR RRC_Inactive state WHEN: UE starts Random Access procedure THEN: the UE uses the Redcap specific LCID in Mag3 | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-225345 |  | 1 | 100% | 100% |  | 100% | 100%
401 | Y | 38.523-1 | 7.1.1.1.17 | Random access procedure / Redcap UE identification / Msg1-based | **** TP1: [Ref: 38.321 clause 5.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: UE starts Random Access procedure THEN: the UE uses the Redcap specific random access resource in Msg1 **** TP2: [Ref: 38.321 clause 6.2.1] WITH: UE supporting RedCap and in NR RRC_IDLE state WHEN: UE starts Random Access procedure THEN: the UE uses the RedCap specific LCID in Msg3 | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-225347 R5-227533 R5-231529 |  | 1 | 100% | 100% |  | 100% | 100%
402 | Y | 38.523-1 | 7.1.1.8.3 | Separate BWP / IDLE / Redcap | **** TP1: [Ref: 38.321 clause 5.15.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: initialDownlinkBWP-RedCap is configured THEN: the UE shall monitor the PDCCH on the BWP configured by initialDownlinkBWP-RedCap **** TP2: [Ref: 38.321 clause 5.15.1] WITH: UE surpporting Redcap and in NR RRC_IDLE state WHEN: initialUplinkBWP-RedCap is configured and the UE needs to perform the Random Access procedure THEN: the UE shall perform the Random Access procedure by using the BWP configured by initialUplinkBWP-RedCap | Huawei, Hisilicon | RAN5#96 (Aug-22) | R5-225344 R5-227530 R5-231530 |  | 1 | 100% | 100% |  | 100% | 100%
403 | Y | 38.523-1 | 7.1.1.8.4 | Separate BWP / RedCap-specific initial DL BWP without CORESET#0 / NCD-SSB | **** TP1 WITH: UE supporting RedCap and in NR RRC_IDLE state WHEN: initialDownlinkBWP-RedCap does not contain the entire CORESET#0 THEN: UE uses this BWP for receiving DL messages during initial access and after initial access **** TP2 WITH: UE in NR RRC_CONNECTED and the active BWP is RedCap-specific initial downlink BWP and this BWP does not include CD-SSB and the entire CORESET#0 WHEN: NCD-SSB is configured for a RedCap UE in RRCSetup THEN: UE replies RRCSetupComplete **** TP3 WITH: UE in NR RRC_CONNECTED and the active BWP is RedCap-specific initial downlink BWP and this BWP does not include CD-SSB and the entire CORESET#0 WHEN: SS sends RRCRelease to trigger UE move to RRC_IDLE THEN: UE shall monitor paging in the initial DL BWP that includes CORESET#0 | Huawei, Hisilicon | RAN5#100 (Aug-23) | R5-235315 R5-236414 R5-240151 |  | 1 | 100% | 100% |  | 100% | 100%
RRC
404 |  | 38.523-1 | 8.1.3.1.24 | Void | Void | Huawei, Hisilicon | RAN5#97(Nov-22) |  | no need to provide test coverage in SIG since RRM will cover this | 0
405 | Y | 38.523-1 | 8.1.5.10.4 | UE Assistance Information / RRM measurement relaxation / RedCap | **** TP1: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is fulfilled and the UE does not transmit a UEAssistanceInformation message with rrm-MeasRelaxationFulfilment as true since it was configured to provide indications of RRM measurement relaxation criterion fulfilment THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is fulfilled **** TP2: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is not fulfilled and the last UEAssistanceInformation message indicated fulfilment of the criterion with rrm-MeasRelaxationFulfilment as true THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is not fulfilled **** TP3: [Ref: 38.304 clause 5.2.4.9, 38.331 clause 5.7.4] WITH: UE surpporting Redcap and in NR RRC_Connected state and configured RRM measurement relaxation Stationary criterion WHEN: the criterion is fulfilled and the last UEAssistanceInformation message indicated the criterion is not fulfilled with rrm-MeasRelaxationFulfilment as false THEN: the UE initiates transmission of the UEAssistanceInformation message to indicate that the criterion for RRM measurement relaxation for connected mode is fulfilled | Ericsson | RAN5#96 (Aug-22) | R5-225348 R5-227589 R5-231587 R5-236104 |  | 1 | 100% | 100% |  | 100% | 100%
NAS
406 | Y | 38.523-1 | 8.1.5.2.3 | eDRX / IDLE / Paging for notification of BCCH modification | **** TP1: [Ref: ] WITH: UE in NR RRC_IDLE state using eDRX cycle longer than the BCCH modification period WHEN: UE receives a Short Message and the systemInfoModification-eDRX bit is set to indicate BCCH modification THEN: UE applies the SI acquisition procedure to update the new system information **** TP2: [Ref: ] WITH: UE in NR RRC_IDLE state using eDRX cycle shorter than the BCCH modification period WHEN: UE receives a Short Message and the systemInfoModification bit is set to indicate BCCH modification THEN: UE applies the SI acquisition procedure to update the new system information | Qualcomm | RAN5#100 (Aug-23) | R5-235343 R5-236415 R5-236587r1 |  | 1 | 100% | 100% |  | 100% | 100%
407 |  | 38.523-1 | 11.7 | eDRX | Sub-clause heading |  |  |  |  | 1 | 100% | 100% |  | 100% | 100%
408 | Y | 38.523-1 | 11.7.1 | eDRX / IDLE | **** TP1: [Ref: 24.501 clause 5.3.16] WITH : UE having sent an REGISTRATION REQUEST message with extended DRX parameters IE WHEN : the UE receives the extended DRX parameters in the REGISTRATION ACCEPT message THEN: the UE sends a REGISTRATION COMPLETE message **** TP2: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_IDLE state and configured eDRX (eDRX cycle >= 10.24s) WHEN: network sends Paging message within a Paging Time Window(PTW) THEN: UE establishes RRC connection **** TP3: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_IDLE state and configured eDRX (eDRX cycle <= 10.24s) WHEN: network sends Paging message within a paging occassion THEN: UE establishes RRC connection **** TP4: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_IDLE state and configured eDRX WHEN: network changes SIB1 to exclude eDRX-AllowedIdle IE THEN: UE applies the new system information about eDRX not allowed and stops using extended DRX for CN paging in RRC_IDLE state | Qualcomm | RAN5#96 (Aug-22) | R5-227522 R5-231534 R5-233411 R5-235344 R5-240657 | Optional supported by UE | 1 | 100% | 100% |  | 100% | 100%
409 | Y | 38.523-1 | 11.7.2 | eDRX / Inactive / RAN-initiated paging | **** TP1: [Ref: 24.501 clause 5.3.16] WITH: UE having sent an REGISTRATION REQUEST message with extended DRX parameters IE WHEN: the UE receives the extended DRX parameters in the REGISTRATION ACCEPT message THEN: the UE sends a REGISTRATION COMPLETE message **** TP2: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_Inactive state and configured eDRX and RAN Extended Paging Cycle equals to the IDLE mode eDRX cycle WHEN:the network sends a RAN-initiated Paging message within a paging occassion THEN:the UE resumes RRC connection **** TP3: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_Inactive state and configured eDRX and RAN Extended Paging Cycle shorter than the IDLE mode eDRX cycle WHEN: the network sends a RAN-initiated Paging message within a paging occassion THEN:the UE applies the value of ran-ExtendedPagingCycle for RAN-initiated paging and resumes RRC connection **** TP4: [Ref: 24.501 clause 5.3.16] WITH: UE in NR RRC_ INACTIVE state and configured eDRX WHEN: network changes SIB1 to exclude eDRX-AllowedInactive IE THEN: UE applies the new system information and stops using extended DRX for RAN paging in RRC_INACTIVE state | Ericsson | RAN5#96 (Aug-22) | R5-225173 R5-227590 R5-231535 R5-233412 R5-235345 R5-240473 | Optional supported by UE | 1 | 100% | 100% |  | 100% | 100%
410 | Y | 38.523-1 | 11.7.3 | eDRX / Inactive / CN-initiated paging / eDRX Allowed / Not Allowed | **** TP1: [Ref: ] WITH: UE in NR RRC_Inactive state and configured eDRX WHEN: the network sends a CN-initiated Paging message within a paging occassion THEN: the UE goes to RRC_IDLE state and establishes an RRC connection **** TP2: [Ref: ] WITH: UE in NR RRC_ INACTIVE state and configured eDRX WHEN: network changes SIB1 to exclude eDRX-AllowedIdle and eDRX-AllowedInactive IEs THEN: UE applies the new system information and stops using extended DRX for CN-initiated paging in RRC_INACTIVE state | Mediatek | RAN5#100 (Aug-23) | R5-235346 R5-236166 R5-240511 R5-241377 |  | 1 | 100% | 100% |  | 100% | 100%
Legacy testcases adjustment
|  | 38.523-1 | multiple places | Place holder for Legacy R16/R17 test case updates | Update the legacy R16/R17 TCs to support RedCap UE | intersted parties | RAN5#97(Nov-22) | R5#103： R5-242274 R5-242275 R5-242276 R5-242277 R5-242278 R5-242326 R5-243595 R5-242177 R5-243484 | Legacy R16/R17 TCs updates for RedCap UE is out of scope of this WI. It will be tracked in the TEI maintainance WIs | 0
411 |  | 38.523-1 | 6 | Idle mode and RRC Inactive state operations | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) |  |  | 1 | 100% | 100% |  | 100% | 100%
412 |  | 38.523-1 | 7 | Layer 2 | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) |  |  | 1 | 100% | 100% |  | 100% | 100%
413 |  | 38.523-1 | 7.1.1.1.1 | Correct selection of RACH parameters / Random access preamble and PRACH resource explicitly signalled to the UE by RRC / contention free random access procedure | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-232938 |  | 1 | 100% | 100% |  | 100% | 100%
414 |  | 38.523-1 | 7.1.1.1.1a | Correct selection of RACH parameters / Random access preamble and PRACH resource explicitly signalled to the UE by PDCCH Order / contention free random access procedure | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-232938 |  | 1 | 100% | 100% |  | 100% | 100%
415 |  | 38.523-1 | 7.1.1.1.2 | Random access procedure / Successful / C-RNTI Based / Preamble selected by MAC itself | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-233408 |  | 1 | 100% | 100% |  | 100% | 100%
416 |  | 38.523-1 | 7.1.1.1.8 | Correct selection of RACH parameters / 2-step RACH/MSGA and PRACH resource explicitly signalled to the UE by RRC / contention free random access procedure | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-232938 R5-240284 |  | 1 | 100% | 100% |  | 100% | 100%
417 |  | 38.523-1 | 7.1.1.1.9 | Random access procedure / Successful / 2-step RACH/C-RNTI Based / Preamble selected by MAC itself | Update the legacy test cases to support RedCap UE HD-FDD mode | Mediatek | RAN5#102 (Feb-24) | R5-240285 |  | 0.5 | 100% | 100% |  | 100% | 100%
418 |  | 38.523-1 | 7.1.1.3.4 | Correct handling of MAC control information / Buffer status / UL data arrive in the UE Tx buffer / Regular BSR | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227162 |  | 1 | 100% | 100% |  | 100% | 100%
419 |  | 38.523-1 | 7.1.1.3.12 | Correct Handling of UL HARQ process / PUSCH Repetition Type B | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99 (May-23) | R5-233409 |  | 1 | 100% | 100% |  | 100% | 100%
420 |  | 38.523-1 | 7.1.1.4.1.1 | DL-SCH transport block size selection / DCI format 1_0 | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227163 |  | 1 | 100% | 100% |  | 100% | 100%
421 |  | 38.523-1 | 7.1.1.4.1.5 | DL-SCH transport block size selection / DCI format 1_2 | Update the legacy test cases to support RedCap UE | Mediatek | RAN5#102 (Feb-24) | R5-240286 |  | 0.5 | 100% | 100% |  | 100% | 100%
422 |  | 38.523-1 | 7.1.1.4.2.1 | UL-SCH transport block size selection / DCI format 0_0 / Transform precoding disabled | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227166 |  | 1 | 100% | 100% |  | 100% | 100%
423 |  | 38.523-1 | 7.1.1.4.2.3 | UL-SCH transport block size selection / DCI format 0_1 / RA type 0/RA Type 1 / Transform precoding disabled | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227167 |  | 1 | 100% | 100% |  | 100% | 100%
424 |  | 38.523-1 | 7.1.1.4.2.4 | UL-SCH transport block size selection / DCI format 0_1 / RA type 0/RA Type 1 / 256QAM / Transform precoding disabled | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227168 |  | 1 | 100% | 100% |  | 100% | 100%
425 |  | 38.523-1 | 7.1.1.4.2.5 | UL-SCH transport block size selection / DCI format 0_0 / Transform precoding disabled | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227169 |  | 1 | 100% | 100% |  | 100% | 100%
426 |  | 38.523-1 | 7.1.1.4.2.6 | UL-SCH Transport Block Size selection / DCI format 0_2 | Update the legacy test cases to support RedCap UE | Mediatek | RAN5#102 (Feb-24) | R5-240287 |  | 0.5 | 100% | 100% |  | 100% | 100%
427 |  | 38.523-1 | 7.1.1.5.0 | DRX Common Definitions | Update the legacy MAC CDRX TC to support RedCap UE HD-FDD mode | Huawei, Hisilicon | RAN5#100 (Aug-23) | R5-234454 |  | 1 | 100% | 100% |  | 100% | 100%
428 |  | 38.523-1 | 7.1.1.9.1 | MAC Reset | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227170 |  | 1 | 100% | 100% |  | 100% | 100%
429 |  | 38.523-1 | 7.1.2.3.3 | AM RLC / 12-bit SN / Correct use of sequence numbering | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227523 |  | 1 | 100% | 100% |  | 100% | 100%
430 |  | 38.523-1 | 7.1.2.3.5 | AM RLC / 12-bit SN / Control of transmit window/Control of receive window | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227528 |  | 1 | 100% | 100% |  | 100% | 100%
431 |  | 38.523-1 | 7.1.2.3.6 | AM RLC / Polling for status | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-226947 R5-233410 |  | 1 | 100% | 100% |  | 100% | 100%
432 |  | 38.523-1 | 7.1.2.3.7 | AM RLC / Receiver status triggers | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227164 |  | 1 | 100% | 100% |  | 100% | 100%
433 |  | 38.523-1 | 7.1.2.3.8 | AM RLC / Reconfiguration of RLC parameters by upper layers | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-226948 |  | 1 | 100% | 100% |  | 100% | 100%
434 |  | 38.523-1 | 7.1.2.3.9 | AM RLC / Re-ordering of RLC PDU segments | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227529 |  | 1 | 100% | 100% |  | 100% | 100%
435 |  | 38.523-1 | 7.1.2.3.10 | AM RLC / Re-transmission of RLC PDU with and without re-segmentation | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227601 |  | 1 | 100% | 100% |  | 100% | 100%
436 |  | 38.523-1 | 7.1.3.4.1 | PDCP handover / Lossless handover / PDCP sequence number maintenance/PDCP status report to convey the information on missing or acknowledged PDCP SDUs at handover/ In-order delivery and duplicate elimination in the downlink | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | R5-227535 |  | 1 | 100% | 100% |  | 100% | 100%
437 |  | 38.523-1 | 7.1.3.5.4 | PDCP handover / Lossless handover / PDCP sequence number maintenance/PDCP status report to convey the information on missing or acknowledged PDCP SDUs at handover/ In-order delivery and duplicate elimination in the downlink | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#98(Mar-23) | R5-231533 |  | 1 | 100% | 100% |  | 100% | 100%
438 |  | 38.523-1 | 8 | RRC | Update the legacy test cases to support RedCap UE | Qualcomm | RAN5#97(Nov-22) |  |  | 1 | 100% | 100% |  | 100% | 100%
439 |  | 38.523-1 | 8.1.5.1.1 | UE capability transfer / Success | Update the legacy test cases to support RedCap UE | Qualcomm | RAN5#97(Nov-22) | R5-227571 R5-233070 |  | 1 | 100% | 100% |  | 100% | 100%
440 |  | 38.523-1 | 8.1.5.2.2 | SI change / Notification of BCCH modification / Short message for SI update in NR RRC_CONNECTED state | Update the legacy test cases to support RedCap UE and HD-FDD mode | Qualcomm | RAN5#97(Nov-22) | R5-227531 R5-233408 |  | 1 | 100% | 100% |  | 100% | 100%
441 |  | 38.523-1 | 8.1.5.8.1 | SI change / Notification of BCCH modification / Short message for SI update in NR RRC_CONNECTED state | Update the legacy test cases to support RedCap UE HD-FDD mode | Huawei，hisilicon | RAN5#99(May-23) | R5-233071 |  | 1 | 100% | 100% |  | 100% | 100%
442 |  | 38.523-1 | 9 | Mobility management | Update the legacy test cases to support RedCap UE |  | RAN5#97(Nov-22) | No Document needed |  | 1 | 100% | 100% |  | 100% | 100%
443 |  | 38.523-1 | 10 | Session management | Update the legacy test cases to support RedCap UE |  | RAN5#97(Nov-22) | No Document needed |  | 1 | 100% | 100% |  | 100% | 100%
444 |  | 38.523-1 | 11 | Multi-layer and Services | Update the legacy test cases to support RedCap UE | Huawei, Hisilicon | RAN5#97(Nov-22) | No Document needed |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
445 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add applicability for NR Redcap |  |  | R5-227591 R5-245539 R5-227541 R5-245542 R5-227602 R5-227537 R5-231536 R5-232943 R5-234006 R5-234007 R5-235347 R5-235316 R5-237089 | Test applicability of Legacy R16/R17 features for RedCap UE is out of scope of this WI, and will be tracked in the TEI maintainace WIs | 1 | 100% | 100% |  | 100% | 100%
446 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add applicability for NR Redcap |  |  | R5-225350 R5-225174 R5-227591 R5-227541 R5-227602 R5-231588 R5-231536 R5-232943 R5-234006 R5-237089 | Test applicability of Legacy R16/R17 features for RedCap UE is out of scope of this WI, and will be tracked in the TEI maintainace WIs | 1 | 100% | 100% |  | 100% | 100%
TS 34.229-2: ICS for IMS test cases
447 |  | 34.229-2 | 4.2 | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | <Describe task> | Qualcomm | RAN5#102 (Feb-24) | R5-236559 R5-241411r1 |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
448 |  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD | 100% | 100% |  | 100% | 100%
449 |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | RAN5#102 (Feb-24) | R5-230104 R5-232191 R5-236303 |  | 1 | 100% | 100% |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.

## CRs agreed after R5#104
WG Tdoc | Title | Conclusion | Source | Spec | Version | WIC
R5-244222 | Removal of band n104 from Table A.4.3.9-4e | agreed | MediaTek Inc. | 38.508-2 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244829 | Correction to CSI-ResourcePeriodicityAndOffset in 5.2.1.1.1 and 5.2.1.2.1 | agreed | Anritsu | 38.521-4 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245872 | Addition of DL RMC for R.PDSCH.2-3.5 TDD and R.PDSCH.2-4.3 TDD | P.AGREED | Anritsu | 38.521-4 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245956 | Correction to Annex F for RedCap RRM test cases | P.AGREED | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245278 | Annex E.14 correction for new RedCap test cases | agreed | Rohde & Schwarz | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245319 | Annex F correction for RedCap test cases including Test Tolerance | agreed | Rohde & Schwarz | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244107r1 | Correction to RedCap RRM - SS-SINR accuracy requirement for 1RX | DEFERRED | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244110 | Correction to RedCap RRM - 16.6.1.1 test case | agreed | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244293 | Editorial correction of Redcap inter-RAT CGI test case 16.6.5.4 | agreed | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245957 | Correction to Redcap RRM TC 16.6.4.5 and 16.6.4.7_CSI-RS L1 RSRP 1Rx with TT | P.AGREED | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245958 | Correction of Redcap CSI-RS based BFD and LR 16.5.2.5 and 16.5.2.7 test case with Test Tolerance | P.AGREED | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245959 | Correction of 16.7.4.3.1 Redcap CSI-RS based L1-RSRP accuracy for 1RX test case with Test Tolerance | P.AGREED | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245960 | Correction of 16.7.4.3.2 Redcap CSI-RS based L1-RSRP accuracy for 1RX test case with Test Tolerance | P.AGREED | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244318 | Correction of Redcap RRM-16.7.4.0.3 and 16.7.4.0.4 CSI-RS L1-RSRP accuracy requirements | agreed | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244334 | Editorial correction of 1Rx RedCap RRM - L1-RSRP measurement for beam reporting | agreed | MediaTek Inc. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244349 | Correction on test requirements in Redcap RLM test cases | agreed | Mediatek India Technology Pvt. | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244632 | Correction to RedCap RRM test case 16.1.1.7 | DEFERRED | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244633 | Correction to RedCap BFR test cases | DEFERRED | Huawei, HiSilicon, Starpoint | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244832 | Correction to message exception in 16.5.3.1.1 and 16.5.3.2.1 | agreed | Anritsu | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244833 | Correction to antenna configuration in 16.6.2.9 | DEFERRED | Anritsu | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245908 | Correction to title of 16.7.1.x | P.AGREED | Anritsu | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244835 | Addition of clarification notes in 16.7.2.1 and 16.7.2.2 | agreed | Anritsu | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244836 | Correction to test requirement in 16.7.4.1.1 | agreed | Anritsu | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245909 | Correction to test requirements in FR1 L1-RSRP absolute measurement for RedCap | P.AGREED | Anritsu | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245910 | Correction to test requirement in 16.3.1.1 | P.AGREED | Anritsu | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245911 | Correction to test parameters in 16.3.2.3.1 | P.AGREED | Anritsu | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245037r1 | Correction to Antenna config in TC 16.6.2.9 | DEFERRED | Qualcomm Korea | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245961 | Correction to cell2 SS-RSRP for test 1 in TC 16.7.3.1 | P.AGREED | Qualcomm Korea | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245962 | Update to NR2L FR1 measurement accuracy TC 16.7.5.2 | P.AGREED | Qualcomm Korea | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245267 | Correction of SS-RSRP RedCap test case 16.7.1.4.2 including Test Tolerance | agreed | Rohde & Schwarz | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245268 | Correction of SS-RSRP RedCap test case 16.7.1.4.1 including Test Tolerance | agreed | Rohde & Schwarz | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245269 | Correction of SS-RSRP RedCap test case 16.7.1.3.2 including Test Tolerance | agreed | Rohde & Schwarz | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245963 | Correction of SS-RSRP RedCap test case 16.7.1.3.1 including Test Tolerance | P.AGREED | Rohde & Schwarz | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245316 | Update in 16.7.1.1.1 to align Noc level to TT analysis | agreed | Keysight Technologies | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245318 | Update in 16.7.2.2 to align Noc level | agreed | Keysight Technologies | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245367r1 | Update to RedCap 1Rx event-triggered test cases 16.6.3.1 and 16.6.3.3 including TT | DEFERRED | QUALCOMM Europe Inc. - Spain | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245368 | Update to RedCap 2Rx event-triggered test cases 16.6.3.2 and 16.6.3.4 including TT | agreed | QUALCOMM Europe Inc. - Spain | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245369 | Update to Annex F for RedCap event-triggered test cases 16.6.3.x | agreed | QUALCOMM Europe Inc. - Spain | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245370 | Correction to RedCap BFR 1Rx test cases 16.5.2.1 and 16.5.2.3 | DEFERRED | QUALCOMM Europe Inc. - Spain | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245905 | Update of test titles for RedCap UE | P.AGREED | China Unicom | 38.533 | 18.3.0 | TEI7_Test, NR_redcap_plus_ARCH-UEConTest
R5-244634 | Correction to RedCap RRM test case 17.5.1.3 with TT | agreed | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244635 | Correction to RedCap RRM test case 17.5.1.5 with TT | DEFERRED | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244636 | Correction to RedCap RRM test case 17.5.1.6 with TT | DEFERRED | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244637 | Correction to RedCap RRM test case 17.5.1.7 with TT | DEFERRED | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244638 | Correction to RedCap RRM test case 17.5.1.8 with TT | DEFERRED | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244639 | Correction to RedCap RRM test case 17.5.3.1.1 with TT | agreed | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244640 | Correction to RedCap RRM test case 17.5.3.2.1 with TT | agreed | Huawei, HiSilicon | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245365 | Update to RedCap SA FR2 SSB BFR test cases 17.5.2.1 and 17.5.2.2 including TT | agreed | QUALCOMM Europe Inc. - Spain | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245366 | Update to SDT test 17.2.1.1 including TT | DEFERRED | QUALCOMM Europe Inc. - Spain | 38.533 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245964 | Update of TT analysis for RedCap RRM TC 16.6.4.5 and 16.6.4.7 | P.AGREED | MediaTek Inc. | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245965 | Update of Test Tolerance analyses for RedCap RRM test cases 16.5.2.5 and 16.5.2.7 | P.AGREED | MediaTek Inc. | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245966 | Update of Test Tolerance analyses for RedCap RRM test cases 16.7.4.3.1 | P.AGREED | MediaTek Inc. | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245967 | Update of Test Tolerance analyses for RedCap RRM test cases 16.7.4.3.2 | P.AGREED | MediaTek Inc. | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244641 | TT analysis for RedCap RLM test cases | agreed | Huawei, HiSilicon | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-244642 | TT analysis for RedCap BWP switching test cases | agreed | Huawei, HiSilicon | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245257 | Test Tolerance for SS-RSRP RedCap test case 16.7.1.4.2 | agreed | Rohde & Schwarz | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245258 | Test Tolerance for SS-RSRP RedCap test case 16.7.1.4.1 | agreed | Rohde & Schwarz | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245305 | Test Tolerance for SS-RSRP RedCap test case 16.7.1.3.2 | agreed | Rohde & Schwarz | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245306 | Test Tolerance for SS-RSRP RedCap test case 16.7.1.3.1 | agreed | Rohde & Schwarz | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245384 | Addition of TTs for RedCap SA FR2 SSB BFR test cases 17.5.2.1 and 17.5.2.2 | agreed | QUALCOMM Europe Inc. - Spain | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245385 | Update to TT analysis for RedCap 1Rx event-triggered test cases 16.6.3.1 and 16.6.3.3 | agreed | QUALCOMM Europe Inc. - Spain | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245386 | Update to TT analysis for RedCap 2Rx event-triggered test cases 16.6.3.2 and 16.6.3.4 | agreed | QUALCOMM Europe Inc. - Spain | 38.903 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245497 | Add new PICS for R17 eDRX in RRC_INACTIVE | P.AGREED | Huawei, HiSilicon | 38.508-2 | 18.3.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245539 | Correct test applicabliity for R17 eDRX test case | P.AGREED | Huawei, HiSilicon | 38.523-2 | 17.7.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest
R5-245542 | Correction to Annexure A text | P.AGREED | Keysight Technologies UK | 38.523-2 | 17.7.0 | TEI17_Test, NR_redcap_plus_ARCH-UEConTest