## 2024
Version: 08-August-2024
3GPP RAN5 TTCN Delivery Schedule 2024
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk03 |  |  | 2024-01-19 |  | GCF CAG#77 (24-25 Jan)
wk09 |  |  | 2024-03-01 |  | PTCRB PVG#104 (5-7 Mar)
wk12 | 2024-03-22 | 2024-03-18 | 2024-03-22 | TTCN-3
wk16 |  |  | 2024-04-19 |  | GCF CAG#78 (23-24 Apr)
wk19 |  |  | 2024-05-10 |  | PTCRB PVG#105 (14-16 May)
wk22 |  |  | 2024-05-31 |  | GCF CAG#78bis (4 Jun)
wk24 | 2024-06-14 | 2024-06-10 | 2024-06-14 | TTCN-3
wk29 |  |  | 2024-07-19 |  | GCF CAG#79 (23-24 Jul)
wk32 | 2024-08-09 | 2024-07-31 |  | TTCN-3 Rel-18 Baseline upgrade | Move to Rel-18 Jun'24 baseline
wk32 |  |  | 2024-08-09 |  | PTCRB PVG#106 (13-15 Aug)
wk37 | 2024-09-13 | 2024-09-09 | 2024-09-13 | TTCN-3
wk41 |  |  | 2024-10-11 |  | GCF CAG#80 (15-16 Oct)
wk44 |  |  | 2024-11-01 |  | PTCRB PVG#107 (5-7 Nov)
wk49 | 2024-12-06 | 2024-12-02 |  | TTCN2 (FDD)
wk50 | 2024-12-13 | 2024-12-09 | 2024-12-13 | TTCN-3
3GPP RAN5 TTCN Workshop Schedule 2024
Workshop number | Week number | Date | Type | Place | Comment
#64 | wk06 | 2024-02-08 | eMeeting | online | Thursday
#65 | wk16 | 2024-04-18 | eMeeting | online | Thursday
#66 | wk27 | 2024-07-04 | eMeeting | online | Thursday
#67 | wk43 | 2024-10-22 | eMeeting | online | Tuesday
Notes:
1. One TTCN2 full delivery (FDD) and five TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 18 required in 2024:
Rel-18 Stage3 freeze declared by 3GPP in March 2024.
Rel-18 ASN.1 freeze declared by 3GPP in June 2024.