| Radiocommunication Study Groups |  |
| --- | --- |
| Source: Document 5D/TEMP/735 | Document IMT-2020/21-E |
|  | 23 July 2019 |
|  | English only |
| Working Party 5D |  |
| Detailed schedule for finalization of the first release of new Recommendation ITU-R M.[IMT-2020.SPECS] |  |
| Detailed specifications of the terrestrial radio interfaces of International Mobile Telecommunications-2020 (IMT-2020) |  |

This document provides the detailed schedule of critical items and milestones for the first release of draft new Recommendation ITU-R M.[IMT-2020.SPECS]. It is organized based on the normal IMT process flows and is presented in the typical format familiar to the External Organizations engaged in the IMT process for development of the Detailed Specifications of the Terrestrial Radio Interfaces of International Mobile Telecommunications.

These details address necessary items to be recognized and provided in due time by the relevant parties for the conclusion of Step 8. The schedule outlines the specific actions and hard deadlines for both Working Party 5D (WP 5D) and the relevant External Organizations, particularly the RIT/SRIT Proponents, GCS Proponents, and Transposing Organizations.

Background

The following dates are established for the specific actions and items needed for the process and, in particular, the completion of the first release Recommendation ITU-R M.[IMT-2020.SPECS] as identified in Table 1 below under Items 5 through 14. Additional details such as those related to the provision of Form A and Certifications B and C, Global Core Specification (GCS) and Directly Incorporated Specification (DIS) materials and other information may be communicated in the future to the relevant parties associated with the new technology proposals.

Table 1

Specific Actions and Items Needed for Completion of the First Release of Recommendation ITU-R M.[IMT-2020.SPECS]

Note: IMT-2020 Process Steps and Critical Milestone Dates from Document IMT-2020/2(Rev.1) (27 Feb 2017) Figure 1

This Table of the normal IMT-2020 process flow and interactions between ITU-R and external organizations incorporates the amended dates with the introduction of WP 5D Meeting #36 bis.

Dates that have been revised based on Meeting #36bis are indicated as   new date   .

Dates no longer valid are marked by strike through.

In light blue shading

Rows in the Table are to be addressed by the indicated External Organizations.

Critical Actions that are hard deadlines requiring action by External Organizations to provide materials to WP 5D are indicated by: date

| Item | Process Step | Action by | Date | Action | Notes |
| --- | --- | --- | --- | --- | --- |
| Item 0 | IMT-2020 Process Step 1 & Critical Milestone (0) | WP 5D | March 2016 commencing from WP 5D #24 23 Feb– 2 Mar 2016 & ending at WP 5D #32 Meeting ‘Y’ | Step 1 Invitation to Propose RITs Step 2 Development of Candidate RITs/SRITs |  |
| Item 1 | IMT-2020 Process Step 2 | RIT/SRIT Proponents | March 2016 commencing from WP 5D #24 23 Feb– 2 Mar 2016 & ending at WP 5D #32 Meeting ‘Y’ | Step 2 Development of Candidate RITs/SRITs |  |
| Item 2 | IMT-2020 Process Step 3 & Critical Milestone (1) | RIT/SRIT Proponents | 2 July 2019 (7 days before 9 -17 July 2019 – WP 5D #32) | Step 3 - Cut-off date for submission of candidate RIT and SRIT proposals (final) Final date for submission by RIT/SRIT Proponents |  |
| Item 3 | IMT-2020 Process Step 3 | WP 5D | July 2019 (from WP 5D #32) | Completion of Doc. IMT-2020/YYY Input Submissions Summary Circular Letter announcing receipt by WP 5D of a complete candidate technology submission and an invitation for submission of Evaluation Reports. |  |
| Item 4 |  | Independent Evaluation Groups | March 2016 – end of 2017 | Opportunity for registration of Evaluation Groups |  |
| Item 5 | IMT-2020 Process Step 4 & Critical Milestone (2) | Independent Evaluation Groups (Evaluation Reports) RIT/SRIT Proponents (Form A) | 12 February 2020 (7 days before 19-26 February 2020 – WP 5D #34) | Completion of Step 4 Evaluation of candidate RITs or SRITs by Independent Evaluation Groups Cut-off date for submission of evaluation reports (final) to ITU Final date for submission of mandatory Form A by RIT/SRIT Proponents |  |
| Item 6 | Process Step 4 | WP 5D | 19-26 February 2020 WP 5D #34 | Completion of Doc. IMT-2020/ZZZ Evaluation Reports Summary |  |
| Item 7 | IMT 2020 Process Step 8 | GCS Proponents | 17 June 2020 (7 days before 24 June – 1 July 2020 - WP 5D #35) | Step 8 Development of the specific sections in DNR ITU-R M.[IMT-2020.SPECS] for the Radio Interface Technology with no transposition references. Final date for submission of Global Core Specification - GCS (final) Final date for submission of mandatory Certification B by GCS Proponent. Final date for submission of mandatory Overview section by GCS Proponent. Satisfactory completion of mandatory new relevant business matters and satisfactory mandatory new statement of compliance with ITU policy on IPR by each GCS Proponent is essential & necessary for ITU-R accepting the GCS from the Transposing Organizations. | Note: This GCS (final) “locks down” the content of the detailed specifications in Recommendation and is the master list of the expected transposition references in a 1 to 1 correspondence (GCS <> Reference) to be subsequently received from each Transposing Organizations |
| Item 8 | IMT-2020 Process Step 5 Step 6 Step 7 & Critical Milestone (3) | WP 5D | 24 June – 1 July 2020 WP 5D #35 | Completion of Step 5 Review and coordination of outside evaluation activities Completion of Step 6 Review to assess compliance with minimum requirements Completion of Step 7 Consideration of evaluation results, consensus building and decision |  |
| Item 9 | IMT 2020 Process Step 8 (continuing) | WP 5D | 24 June – 1 July 2020 WP 5D # 35 | WP 5D performs a review of the submitted material and reaches its conclusion on the acceptability of the proposed material for inclusion in the DNR. WP 5D finalizes and provisionally agrees the specific technology WP 5D in draft new Rec. ITU-R M.[IMT-2020.SPECS] (not necessarily including the detailed transposition references). WP 5D liaison of the WP 5D provisionally agreed draft new Rec. ITU-R M.[IMT-2020.SPECS] to the relevant GCS Proponents and Transposing Organizations for their use in developing their inputs of the detailed references. Note: In any event, the WP 5D meeting #35 will “lock down” the entirety of the WP 5D provisionally agreed draft new Rec. ITU-R M.[IMT-2020.SPECS] for all technologies (not necessarily including the detailed transposition references). | 4 June – 1 July 2020 (WP 5D #35) |
| Item 10 | IMT-2020 Process Step 8 (continuing) (end) Critical Milestone (4) | WP 5D | 7-14 October 2020 (WP 5D #36) | WP 5D performs a quality and completeness check of the provisionally agreed final draft new Rec. ITU-R M.[IMT-2020.SPECS] without the hyperlinks. and forwards to Study Group 5 for action/approval Follow-up communications may be initiated to the GCS Proponents and/or Transposing Organizations, if necessary. | WP 5D will not, in this meeting, complete Step 8 as previously planned. The completion is shifted to WP 5D Meeting #36bis . See Item 12 |
| Item 11 | IMT 2020 Process Step 8 (continuing) | Transposing Organizations | 8 October 2020 8 October 2020 7 September 2020 approximately 4 to 6 weeks prior to the Subsequent Meeting | Delivery to ITU-R of transposition references (final) by each Transposing Organization for incorporation into the WP 5D provisionally agreed draft new Rec. ITU-R M.[IMT-2020.SPECS] Delivery to ITU-R of mandatory Certification C by each Transposing Organization. Satisfactory completion of mandatory new relevant business matters and satisfactory mandatory new statement of compliance with ITU policy on IPR by each Transposing Organization is essential & necessary for ITU-R accepting the transposition references from the Transposing Organizations. | 8 October 2020 (revised due date to send to Radio Communication Bureau from the Transposing Organizations for BR to compile all references (final) and all sections (final) into the completed draft deliverable for the draft new Recommendation) |
| Item 12 | IMT 2020 Process Step 8 (continuing) | Radiocommunication Bureau (BR) | ~ 10 November 2020 Prior to the Subsequent meeting | The Radiocommunication Bureau is requested to provide to WP 5D a ‘complete’ document that incorporates the transposition references |  |
| Item 13 | IMT-2020 Process Step 8 (end) Critical Milestone (4) | WP 5D | 17-19 November 2020 (WP 5D #36bis) | WP 5D performs the final review including quality checks and completeness of the final draft new Rec. ITU-R M.[IMT-2020.SPECS] with all hyperlinks and related materials and forwards to Study Group 5 for action. | New WP 5D Meeting #36bis Held in Geneva in conjunction with Study Group 5 “Block Meetings” of WP 5A, WP 5B & WP 5C. |
| Item 14 |  | Radiocommunication Bureau | before 23 November 2020 | Submission by Counsellor for SG 5 of completed draft new Recommendation including all URL references to SG 5, based on currently anticipated SG 5 meeting schedule. |  |
| Item 15 |  | Study Group 5 | Anticipated to be 23-24 November 2020 | Study Group 5 considers agreement of the draft new Recommendation ITU-R M.[IMT-2020.SPECS] for forwarding to Member States for adoption and approval. | The Study Group 5 meeting as planned would commence in Geneva on Monday of the week following the WP 5D #36bis meeting. |

Calendar 1; Summary of Actions for Completion of the First Release of Recommendation ITU-R M.[IMT-2020.SPECS] Organized in a Calendar View

| Part 1: Milestone Summary for ITU-R WP 5D and Radiocommunication Bureau (BR) for First Release of Recommendation ITU-R M.[IMT-2020.SPECS] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | WP 5D #32 |  |  | WP 5D #33 |  | WP 5D #34 |  | WP 5D #35 | WP 5D #36 |  |  | WP 5D #36bis |
| DATE |  |  | 9-17 July 2019 |  |  | 10-13 December 2019 |  | 19-26 February 2020 |  | 24 June – 1 July 2020 | 7-14 October 2020 |  | ~10 November 2020 | 17-19 November 2020 |
| IMT-2020 Process Step |  |  | Complete Step 3 |  |  |  |  | Complete Step 4 |  | Complete Steps 5 -7 Continue Step 8 | Continue Step 8 |  | Continue Step 8 | Complete Step 8 |
| TABLE 1 ITEM # |  |  | 3 |  |  |  |  | 6 |  | 8 & 9 | 10 |  | 12 | 13 |
| Key WP 5D Deliverable |  |  | Doc. IMT-2020/YYY |  |  |  |  | Doc. IMT-2020/ZZZ |  | Rpt M.[IMT-2020. OUTCOME] Provisional Rec ITU-R M.[IMT-2020.SPECS] needed for Transposition Basis | Provisional Rec ITU-R M.[IMT-2020.SPECS] |  |  | Rec ITU-R M.[IMT-2020.SPECS] |
| Action by Entity |  |  | WP 5D |  |  | WP 5D |  | WP 5D |  | WP 5D | WP 5D |  | BR | WP 5D |
|  |  | Part 2: Milestone Summary for RIT/SRIT Proponents, GCS Proponents, Transposing Organizations & IEGs for First Release of Recommendation ITU-R M.[IMT-2020.SPECS] |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | WP 5D #32 |  |  | WP 5D #33 |  | WP 5D #34 |  | WP 5D #35 | WP 5D #36 |  |  | WP 5D #36bis |
| Deadline | 2 July 2019 |  |  |  | 3 December 2019 |  | 12 February 2020 |  | 17 June 2020 |  |  | 8 October 2020 |  | 10 November 2020 |
| Meeting Designator | 7 days before Mtg #32 |  |  |  | 7 days before Mtg #33 |  | 7 days before Mtg #34 |  | 7 days before Mtg #35 |  |  | - |  | - |
| IMT-2020 Process Step | Complete Step 3 |  |  |  |  |  | Complete Step 4 |  | Start Step 8 |  |  |  |  | Complete Step 8 |
| TABLE 1 ITEM # | 2 |  |  |  |  |  | 5 |  | 7 |  |  | 11 |  |  |
| Key Deliverable | Final Submission |  |  |  |  |  | Evaluation Reports Form A |  | Global Core Specification (final) Certification B Overview Section |  |  | Transposition References (final) Certification C |  |  |
| Action by Entity | RIT/SRIT Proponent |  |  |  |  |  | Independent Evaluation Group RIT/SRIT Proponent |  | GCS Proponent Transposing Organization |  |  | Transposing Organization |  |  |

________________

____________________