## Slide 1: Discussion on timeline of Release 17
3GPP TSG-RAN Meetings #87 RP-200213
RAN plenary reflector 16th March.– 19th March. 2020
Agenda item: 9.10

## Slide 2: Evaluation of current status(1/2)
RAN Chair and RAN WG Chairs will propose
  One Quarter shift for Rel17 at RAN#87 e-meeting
  April meeting will be e-meeting again and it only focus on Rel16 WIDs i.e. no discussion on Rel17 WID/SID
If RAN1 doesn’t start from May meeting but from August meeting
  Basically it means Rel17 will be shifted two quarters
  After two e-meetings Rel16 opens issues suppose to be cleaned
  RAN WGs except for RAN1 are more or less ready to discuss Rel17 considering ASN.1 will be frozen in June. It mean RAN1 will start Rel17 together with other RAN WGs
If RAN1 starts from May meeting and keep 15 months for Rel17
  The total number of meetings are not changed for RAN1
  RAN1 is still one meeting in advance of RAN2/RAN3
  One less meeting for RAN2/3 to freeze stage3, but could have one more meeting to do ASN.1 review

## Slide 3: Evaluation of current status(2/2)
WID/SID content and TUs
  It will be painful to re-open discussion objectives and TUs again during e-meeting
  It would be desirable just to shift the TUs without any change
Plan for potential new WID/SID proposals
  The timeline is challenging considering uncertainty in whole 2020 and we’d better re-evaluate the endorsed proposal in RP-193243

## Slide 4: Proposals on R17 timeline
Proposal1: RAN1 can start R17 discussion from May meeting
Proposal2: RAN2/3 starts from August meeting and freeze stage3 in November meeting
Proposal3: No change to the WID/SIDs objectives except for target date
Proposal4: TUs are simply shifted from Feb. (April) to May (August) without any change for RAN1 and other RAN WGs respectively
Proposal5: Whether the door for new Rel17 WID/SID will re-open should be re-evaluated in future RAN meeting based on progress of Rel17 and meeting uncertainty due to COVID-19