Estimated Timelines and Project plan for revision of EN301893 (incl. 3GPP/Wi-Fi alliance timelines)

The below is an optimistic approach where it still takes 9,5 months after finalisation by the ETSI TB to have a standard published by ETSI. But publication by ETSI is not the same as publication by the EC in the OJEU. Assumes that takes another 6 months, means the standard appears in the OJEU on 1 April 2017 leaving only a few months to a manufacturer to modify and retest his product before the RE-D enters into force.

The big unknown is how long the delay would be for the Commission to publish in the OJEC once ETSI has finalised their work as this is normally done on an [annual] basis.

Example presented to WFA by the BRAN chairman of the (ETSI) time line for EN 300 328 & EN 301 893 (under the current active WIs for these)

      - 31 December 2015: ETSI TB completes the revision of the standard (which is still a draft at that point)

      - 1 Jan 2016: 2 weeks minimum processing time for ETSI secretariat to send the document out to all NSOs for ENAP

      - 1 Feb 2016: start of ENAP (public enquiry) which takes 120 days

      - 1 June 2016: end of ENAP. 1 week minimum processing time for the ETSI secretariat to prepare the comments resolution report and to make that available to the members of the TB well in advance of the resolution meeting

      - End June 2016 (soonest): ETSI TB will hold the resolution meeting (to deal with comments and produce a final draft for National Vote)

      - 1 August 2016: Start of National Vote (60 days)

      - 1 October 2016: If vote was successful: work of the ETSI TB is completed

      - 15 October 2016:  Publication by ETSI

      - Day/month/year: Publication by the EC in the OJEU (hopefully within 6 months after publication by ETSI). ONLY AFTER THE PUBLICATION IN THE OJEU THE STANDARD GETS THE FORMAL STATUS OF HARMONISED STANDARD

| Milestones | Outcome and project deadlines | Other Significant Meetings/dates |
| --- | --- | --- |
| 3GPP Plan for LAA studies | 3GPP approved the study item on LAA in September 2014. The study item includes the preparation of a technical report to be approved in at RAN#68, based on evaluations of sharing mechanisms. | 3GPP RAN#65 |
| Discuss initial proposals for EN 301893 (including adaptivity) | 06 – 10 April 2015 | BRAN 82 |
| Publish 3GPP Technical Report (TR36.889) on possible sharing mechanisms | June 2015 (RAN#68) | TSG-RAN Meeting #68, 15th – 18th June 2015 Malmo, Sweden |
| 3GPP Plan for LAA specification work in LTE | 3GPP expected approval of a Work Item on LAA for LTE Release 13 | TSG-RAN Meeting #68, 15th – 18th June 2015 Malmo, Sweden |
| Review contributions and proposals for initial drafts | 23 – 26 June 2015 Evaluation results for WLAN-LAA coexistence are encouraged to be available as input contributions to this meeting. | BRAN 83 |
| Agree Basic Draft of EN301 893 Standard | To aim to reach a common understanding with regard to the requirements of objective (4) in the work Item to be included in the harmonised standard | by 31st of July |
| 3GPP Work Item on LAA | Work on technical specifications for LAA | 3 working group meetings: Aug 24-28 Oct 5-9 Nov 16-20 |
| Agree stable Draft of EN301 893 Standard | 13 – 16 October 2015 | BRAN 84 |
| 3GPP functional freeze of LTE Release 13 technical specifications | Dec 2015 | TSG-RAN Meeting #70, 7-10 Dec 2015, Sitges, Spain |
| ETSI TB completes the revision of the standard (which is still a draft at that point) | Dec 2015 | BRAN 85 |
| BRAN send to ETSI for preparation for ENAP | 31 December 2015 |  |
| 2 weeks minimum processing time for ETSI secretariat to send the document out to all NSOs for ENAP | 1 Jan 2016 |  |
| start of ENAP (public enquiry) which takes 120 days | 1 Feb 2016 |  |
| End of ENAP. 1 week minimum processing time for the ETSI secretariat to prepare the comments resolution report and to make that available to the members of the TB well in advance of the resolution meeting | 1 June 2016 |  |
| ETSI TB will hold the resolution meeting (to deal with comments and produce a final draft for National Vote) | End June 2016 (soonest) |  |
| Start of National Vote (60 days) | 1 August 2016 |  |
| If vote was successful: work of the ETSI TB is completed | 1 October 2016 |  |
| Publication by ETSI | 15 October 2016 |  |
| Publication by the EC in the OJEU (hopefully within 6 months after publication by ETSI). ONLY AFTER THE PUBLICATION IN THE OJEU THE STANDARD GETS THE FORMAL STATUS OF HARMONISED STANDARD | Day/month/year? |  |
| Deadline for last R&TTE use | 16-17 June 2017??? |  |

Meeting dates

| 2015 |  |
| --- | --- |
| 07 -10 April | BRAN 82 |
| 20 – 24 April | 3GPP RAN1#80bis |
| 11 – 15 May | IEEE 802.11 Inter |
| 25 – 29 May | 3GPP RAN1#81 |
| 09 – 11 June | Wi-Fi Alliance |
| 15 - 18 June | 3GPP RAN#68 |
| 23 - 26 June | BRAN 83 |
| 12 – 17 July | IEEE 802.11 Plen |
| 24 – 28 August | 3GPP RAN1#82 |
| 14 – 18 September | 3GPP RAN#69 |
| 14 – 18 September | IEEE 802.11 Inter |
| 5 – 9 October | 3GPP RAN1#82bis |
| 13 - 16 October | BRAN 84 |
| 20 – 22 October | Wi-Fi Alliance |
| 09 - 13 November | IEEE 802.11 Plen |
| 16 – 20 November | 3GPP RAN1#83 |
| 7 – 10 December | 3GPP RAN#70 |
| December | BRAN 85 |
| 2016 |  |
| 2017 |  |