3GPP TSG-RAN WG2 Meeting #113-e	R2-2101010

E-meeting, 25th Jan – 5th Feb, 2021                                          	Update of R2-2009334

Agenda item:		8.1.1

Source: 		Huawei, CMCC, HiSilicon

Title: 	Updated Rel-17 NR MBS workplan

Document for:	Information

1	Introduction

TSG RAN has setup a new WI on NR MBS at RAN#86 in [1] and some editorial corrections have been made on the WID in [2], with the following objectives.

- Specify RAN basic functions for broadcast/multicast for UEs in RRC_CONNECTED state [RAN1, RAN2, RAN3]:

  - Specify a group scheduling mechanism to allow UEs to receive Broadcast/Multicast service [RAN1, RAN2]

    - This objective includes specifying necessary enhancements that are required to enable simultaneous operation with unicast reception.

  - Specify support for dynamic change of Broadcast/Multicast service delivery between multicast (PTM) and unicast (PTP) with service continuity for a given UE [RAN2, RAN3]

  - Specify support for basic mobility with service continuity [RAN2, RAN3]

  - Assuming that the necessary coordination function (like functions hosted by MCE, if any) resides in the gNB-CU, specify required changes on the RAN architecture and interfaces, considering the results of the SA2 SI on Broadcast/Multicast (SP-190625) [RAN3]

  - Specify required changes to improve reliability of Broadcast/Multicast service, e.g. by UL feedback. The level of reliability should be based on the requirements of the application/service provided.[RAN1, RAN2]

  - Study the support for dynamic control of the Broadcast/Multicast transmission area within one gNB-DU and specify what is needed to enable it, if anything [RAN2, RAN3]

- Specify RAN basic functions for broadcast/multicast for UEs in RRC_IDLE/ RRC_INACTIVE states [RAN2, RAN1]:

  - Specify required changes to enable the reception of Point to Multipoint transmissions by UEs in RRC_IDLE/ RRC_INACTIVE states, with the aim of keeping maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. [RAN2, RAN1].

Note: the possibility of receiving Point to Multipoint transmissions by UEs in RRC_IDLE/ RRC_INACTIVE states, without the need for those UEs to get the configuration of the PTM bearer carrying the Broadcast/Multicast service while in RRC CONNECTED state beforehand, is subject to verification of service subscription and authorization assumptions during the WI.

This contribution is an update of work plan [4] in RAN2#112-e based on the progress in RAN#90-e [3].

2	Workplan

2.1	Prioritization of efforts

RAN1-led efforts:

- For broadcast/multicast for UEs in RRC_CONNECTED state:

  - Specify a group scheduling mechanism to allow UEs to receive Broadcast/Multicast service [RAN1, RAN2]

    - This objective includes specifying necessary enhancements that are required to enable simultaneous operation with unicast reception.

  - Specify required changes to improve reliability of Broadcast/Multicast service, e.g. by UL feedback. The level of reliability should be based on the requirements of the application/service provided.[RAN1, RAN2]

RAN2-led efforts:

- For broadcast/multicast for UEs in RRC_CONNECTED state:

  - Specify support for dynamic change of Broadcast/Multicast service delivery between multicast (PTM) and unicast (PTP) with service continuity for a given UE [RAN2, RAN3]

  - Specify support for basic mobility with service continuity [RAN2, RAN3]

  - Study the support for dynamic control of the Broadcast/Multicast transmission area within one gNB-DU and specify what is needed to enable it, if anything [RAN2, RAN3]

- For broadcast/multicast for UEs in RRC_IDLE/ RRC_INACTIVE states:

  - Specify required changes to enable the reception of Point to Multipoint transmissions by UEs in RRC_IDLE/ RRC_INACTIVE states, with the aim of keeping maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. [RAN2, RAN1].

RAN3-led efforts:

- For broadcast/multicast for UEs in RRC_CONNECTED state:

  - Assuming that the necessary coordination function (like functions hosted by MCE, if any) resides in the gNB-CU, specify required changes on the RAN architecture and interfaces, considering the results of the SA2 SI on Broadcast/Multicast (SP-190625) [RAN3]

2.2	Timeline

Table 1 summarizes a timeline for RAN1/2/3/4, which has been derived from the interdependences among tasks in different TSGs and WGs.

Table 1: Timeline for RAN1, 2, 3 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN1 | #1 (#102-e) | Aug. 2020 | 0 | Focus on high-level concepts discussion for the following: - Specify group scheduling mechanism for MBS, e.g. discuss the high level candidate mechanisms, identify the potential issues, etc. - Specify mechanisms to improve reliability of MBS, e.g. UL feedback. - Identify required changes to enable MBS reception in RRC_IDLE/ RRC_INACTIVE states, aiming to keep maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. This can be lower priority if RAN2 input is needed. |
| RAN2 | #1 (#111-e) | Aug. 2020 | 2 | - Stage-2 discussion and collect different views on: - Dynamic switch between PTP and PTM. - L2 architecture. - MBS reception in idle/inactive - Mobility and service continuity. |
| RAN3 | #1 (#109-e) | Aug. 2020 | 1 | - Initial discussion on RAN architecture discussion to support NR MBS (stage 2) - RAN architecture to support NR MBS - CU or DU to make decision of PTP or PTM - Initial discussion on how to setup MBS Session, UE associated or non-UE associated, common tunnel setup, over NGAP and F1AP - Take SA2 progress into account - Initial discussion on Service Continuity (stage 2) - Potential scenarios, uses cases - Identify issues to be solved. |
| RAN#89e (Sept. 2020) |  |  |  |  |
| RAN1 | #2 (#103-e) | Oct. 2020 | 1 | - Continue specification on group scheduling mechanism for MBS, including enhancements to enable simultaneous operation with unicast reception. - Specify mechanisms to improve reliability of MBS, e.g. UL feedback. Evaluation results can also be discussed if necessary. - Identify and specify necessary changes to enable MBS reception in RRC_IDLE/ RRC_INACTIVE states, aiming to keep maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. |
| RAN2 | #2 (#112-e) | Nov. 2020 | 2 | - Discuss based on email discussion summaries to make progress on: - Dynamic switch between PTP and PTM. - L2 architecture. - MBS reception in idle/inactive. - Mobility and service continuity. - Handle the SA2 LS in S2-2006044 and reply the LS. |
| RAN3 | #2 (#110-e) | Nov. 2020 | 1 | - Continue discussion on RAN architecture - Session Management over NG - Dynamic Change Between PTP and PTM for UEs in RRC_CONNECTED State - Bearer Management over F1/E1 - Take SA2 and RAN2 progress into account - Continue discussion on Service Continuity - Mobility Between MBS Supporting Nodes - Mobility Between MBS Supporting and non-MBS Supporting Nodes - Potential RAN3 impacts analyses, take SA2 and RAN2 progress into account |
| RAN#90e (Dec. 2020) |  |  |  |  |
| RAN1 | #3 (#104-e) | Jan. 2021 | 1 | - Continue specification on group scheduling mechanism for MBS, including enhancements to enable simultaneous operation with unicast reception. - Continue specification on mechanisms to improve reliability of MBS, e.g. UL feedback. - Continue specification on necessary changes to enable MBS reception in RRC_IDLE/ RRC_INACTIVE states, aiming to keep maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. |
| RAN2 | #3 (#113-e) | Jan. 2021 | 2 | - Continue stage-2 discussion on and try to make decision: - L2 architecture, and Dynamic switch between PTP and PTM, e.g. PDCP based or RLC based. - Reliability enhancement, e.g. L2 reliability needed or not. - Delivery mode 2 issues - Mobility and service continuity. - RAN2 aspects for group scheduling |
| RAN3 | #3 (#111-e) | Jan. 2021 | 2 | - Continue discussion on RAN architecture - Session Management over NG - Dynamic Change Between PTP and PTM for UEs in RRC_CONNECTED State - Bearer Management over F1/E1 - Take SA2 and RAN2 progress into account - Continue discussion on Service Continuity - Mobility Between MBS Supporting Nodes - Mobility Between MBS Supporting and non-MBS Supporting Nodes - Potential RAN3 impacts analyses, take SA2 and RAN2 progress into account - Update stage 2 BL CRs |
| RAN#91e (Mar. 2021) |  |  |  |  |
| RAN1 | #4 (#104bb-e) | Apr. 2021 | 0.5 | - Continue specification on group scheduling mechanism for MBS, including enhancements to enable simultaneous operation with unicast reception. - Continue specification on mechanisms to improve reliability of MBS, e.g. UL feedback. - Continue specification on necessary changes to enable MBS reception in RRC_IDLE/ RRC_INACTIVE states, aiming to keep maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. |
| RAN2 | #4 (#113b-e) | Apr. 2021 | 1.5 | - Finalize stage-2 discussion on: - Dynamic switch between PTP and PTM. - L2 architecture. - MBS reception in idle/inactive - Mobility and service continuity. - Initiate Stage-3 discussion on: - Multicast bearer configuration. - MBS reception in idle/inactive |
| RAN3 | #4 (No bis meeting in this quarter) |  | N/A |  |
| RAN1 | #5 (#105-e) | May. 2021 | 1.5 | - Continue specification on group scheduling mechanism for MBS, including enhancements to enable simultaneous operation with unicast reception. - Continue specification on mechanisms to improve reliability of MBS, e.g. UL feedback. - Continue specification on necessary changes to enable MBS reception in RRC_IDLE/ RRC_INACTIVE states, aiming to keep maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. |
| RAN2 | #5 (#114-e) | May. 2021 | 1.5 | - Initiate/continue Stage-3 discussion on: - Dynamic switch between PTP and PTM. - Other L2 configuration. - MBS reception in idle/inactive - Mobility and service continuity. |
| RAN3 | #5 (#112-e) | May. 2021 | 1 | - Continue discussion on RAN architecture (stage 3) - Based on the adopted solution, further analyses - NGAP procedures/signalling impacts - F1AP procedure/signalling impacts - E1AP procedure/signalling impacts - Continue discussion on Service Continuity (stage 3) - Based on the adopted solution, further analyses - XnAP procedures/signalling impacts - NGAP, F1AP, E1AP impacts, if any - Update stage 2 BL CRs - Start draft stage3 Baseline CRs |
| RAN#92e (June 2021) |  |  |  |  |
| RAN1 | #6 (#106-e) | Aug. 2021 | 1 | - Continue specification on group scheduling mechanism for MBS, including enhancements to enable simultaneous operation with unicast reception. - Continue specification on mechanisms to improve reliability of MBS, e.g. UL feedback. - Continue specification on necessary changes to enable MBS reception in RRC_IDLE/ RRC_INACTIVE states, aiming to keep maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. - Discuss initial RRC parameters for MBS. |
| RAN2 | #6 (#115-e) | Aug. 2021 | 2 | - Continue stage-3 discussion on: - Dynamic switch between PTP and PTM. - Other L2 configuration. - MBS reception in idle/inactive - Mobility and service continuity. - L1 configuration. - Start draft running CRs |
| RAN3 | #6 (#113-e) | Aug. 2021 | 1 | - Continue discussion on RAN architecture (stage 3) - Based on the adopted solution, further analyses - NGAP procedures/signalling impacts - F1AP procedure/signalling impacts - E1AP procedure/signalling impacts - Continue discussion on Service Continuity (stage 3) - Based on the adopted solution, further analyses - XnAP procedures/signalling impacts - NGAP, F1AP, E1AP impacts, if any - Update stage 2/3 BL CRs |
| RAN#93e (Sept. 2021) |  |  |  |  |
| RAN1 | #7 (#106b-e) | Oct. 2021 | 1 | - Finalize specification on group scheduling mechanism for MBS, including enhancements to enable simultaneous operation with unicast reception. - Finalize specification on mechanisms to improve reliability of MBS, e.g. UL feedback. - Finalize specification on necessary changes to enable MBS reception in RRC_IDLE/ RRC_INACTIVE states, aiming to keep maximum commonality between RRC_CONNECTED state and RRC_IDLE/RRC_INACTIVE state for the configuration of PTM reception. - Finalize RRC parameters for MBS. |
| RAN2 | #7 (#115b-e) | Oct. 2021 | 2 | - Continue stage-3 discussion on: - Dynamic switch between PTP and PTM. - Other L2 configuration. - MBS reception in idle/inactive - Mobility and service continuity. - L1 configuration. - Update running CRs |
| RAN3 | #7 (#113b-e) | Oct. 2021 | 1 | - Continue discussion on RAN architecture (stage 3) - Based on the adopted solution, further analyses - NGAP procedures/signalling impacts - F1AP procedure/signalling impacts - E1AP procedure/signalling impacts - Continue discussion on Service Continuity (stage 3) - Based on the adopted solution, further analyses - XnAP procedures/signalling impacts - NGAP, F1AP, E1AP impacts, if any - Update stage 2/3 BL CRs |
| RAN1 | #8 (#107-e) | Nov. 2021 | 1 | - Discuss and conclude on the open issues, if any. - Close the MBS WI from RAN1 perspective. |
| RAN2 | #8 (#116-e) | Nov. 2021 | 1.5 | - Continue stage-3 discussion on: - Dynamic switch between PTP and PTM. - Other L2 configuration. - MBS reception in idle/inactive - Mobility and service continuity. - L1 configuration. - Update running CRs |
| RAN3 | #8 (#114-e) | Nov. 2021 | 1 | - Continue discussion on RAN architecture (stage 3) - Based on the adopted solution, further analyses - NGAP procedures/signalling impacts - F1AP procedure/signalling impacts - E1AP procedure/signalling impacts - Continue discussion on Service Continuity (stage 3) - Based on the adopted solution, further analyses - XnAP procedures/signalling impacts - NGAP, F1AP, E1AP impacts, if any - Update stage 2/3 BL CRs |
| RAN#94e (Dec. 2021) Rel-17 completion for RAN1 |  |  |  |  |
| RAN1 | #9 (#108-e) | Jan/Feb. 2022 | 0 | - Corrections |
| RAN2 | #9 (#117-e) | Jan/Feb. 2022 | 2 | - Finalize stage-3 discussion on: - Dynamic switch between PTP and PTM. - Other L2 configuration. - MBS reception in idle/inactive - Mobility and service continuity - L1 configuration. - Finalize running CRs |
| RAN3 | #9 (#115-e) | Jan/Feb. 2022 | 1 | - Finalize discussion of stage-3 aspects - Finalize Baseline CRs |
| RAN#95e (Mar. 2022) Rel-17 completion for RAN2, 3, 4 (core part) |  |  |  |  |
| RAN1 | #10 |  | 0 | - Corrections |
| RAN2 | #10 |  | 0 | - Corrections |
| RAN3 | #10 |  | 0 | - Corrections |
| RAN1 | #11 |  | 0 | - Corrections |
| RAN2 | #11 |  | 0 | - Corrections |
| RAN3 | #11 |  | 0 | - Corrections |
| RAN#96e (June 2022) Rel-17 completion for ASN.1 |  |  |  |  |

References

[1] RP-193248	New WID proposal: NR Multicast and Broadcast Services

[2] RP-201038	Revised WID: Core part: NR multicast and broadcast services

[3] RP-202868	RAN planning for Release 17

[4] R2-2009334	Updated NR MBS workplan	Huawei, CMCC, HiSilicon