## Slide 1: TSG SA WG4 (SA4) Status Report at TSG SA#100
Frédéric Gabin
SA4 Chair (Dolby Laboratories Inc.)
(Agenda Item 4.4)

## Slide 2: Outline
General
  Leadership and subgroups
  Meetings and statistics
  Progress highlights
Work progress
  CRs to features in Release 17 and earlier
  Rel-18 Work Items
  Study Items
  New Work Item(s)
IETF Dependencies
Summary of action items

## Slide 3: SA4 leadership and subgroups
SA4 officials:
  Chair: Frédéric Gabin (Dolby Laboratories Inc. , ETSI), re-elected at SA4#123-e
  Vice Chairs:
    Gilles Teniou (Tencent, CCSA), re-elected at SA4#123-e
    Jaeyeon Song (Samsung Electronics Co., Ltd, TTA)
  Secretary: Andrijana Brekalo (MCC Support)
  Elections for one Vice-Chair of SA WG4 will be held during SA4#125, 21-25 august 2023.
Sub Working Groups and their Chairs
Audio SWG | Multicast-Broadcast-Streaming (MBS) SWG | Real Time Communications (RTC) SWG | Video SWG
Imre Varga (Qualcomm CDMA Technologies, ETSI) & Stéphane Ragot (Orange, ETSI) | Frédéric Gabin (Dolby Laboratories Inc. , ETSI) | Nikolai Leung (Qualcomm Incorporated, ATIS) | Gilles Teniou (Tencent, CCSA)

## Slide 4: Meetings held since SA#99
SWG AH conference calls (2 to 3 hours each)
  MBS SWG (all A.I.s): 30 March, 11 May (inc. a joint session with 5G-MAG)
  Audio SWG:
    eUET: 27 March
    ISAR: 27 March, 8 May
    ATIAS/FS_DaCED: 24 March
    IVAS: 3, 28 April, 8 May
  RTC SWG (all A.I.s): 29 March, 3 May
  Video SWG (all A.I.s): 28 March, 9 May
SA4 plenary meetings
Meetings | Dates | Venue and Host
SA4#123-e | E-meeting: 17-21 April 2023 | Host: MCC, Electronic meeting
SA4#124 | F2F: 22-26 May 2023 | Host: ETSI, Venue: Berlin, Germany

## Slide 5: Calendar of future meetings - 1
SWG AH conference calls
  MBS SWG (all A.I.s): 29 June, 13, 27 July, 10 August
  Audio SWG:
    FS_DaCED: 31 July
    IVAS: 12, 21 June, 8 August
  RTC SWG (all A.I.s): 12 July, 9 August
  Video SWG (all A.I.s): 20, 27 June, 25 July, 1 August
SA4 plenary meetings (2023)
Meetings in 2023 | Dates | Venue and Host
SA4#125 | F2F: 21-25 August 2023 | Host: E3MAG, Venue: Gothenburg, Sweden
SA4#126 | F2F: 13-17 November 2023 | Host: ATIS, Venue: Chicago, USA

## Slide 6: Calendar of future meetings - 2
SA4 plenary meetings (2024)
Meetings in 2024 | Dates | Venue and Host
SA4#127 | F2F: 29 January - 2 February 2024 | Host: ETSI, Venue: Sophia-Antipolis, France
SA4#127bis-e | E-meeting: 8-12 April 2024 | Host: MCC, Electronic meeting
SA4#128 | F2F: 20-24 May 2024 | Host: TBD, Venue: Korea
SA4#129-e | E-meeting: 19-23 August 2024 Note: agreement to have NO SA4 meetings in August 2025 | Host: MCC, Electronic meeting
SA4#130 | F2F: 18-22 November 2024 | Host: TBD, Venue: North-America

## Slide 7: SA4 meeting statistics
Note that, as for SA4#121 and SA4#122 mega-meetings, the number of F2F participants (169) at SA4#124 collocated meeting in Athens, Greece, is not representative of a regular standalone SA4 F2F meeting.

## Slide 8: SA4 progress highlights
No CRs prior to Rel-16.
Rel-16 corrections on 5G Media streaming Architecture and Stage 3, aligning with CT WGs.
Rel-17 corrections on 5MBS, 5GMS, ITT4RT and EVEX.
Progress on all Rel-18 items (highlights):
  Corrections to completed Rel-18 Work Item 5GMS_Audio_Ph2 and ITT4RT.
  TEI18 addition of 5GMS Service URL to TR 26.804 (5G media streaming extensions)
  Completed 5G Media Streaming Architecture Phase 2. Several CRs to 26.501 for approval. Corresponding Rel-18 Stage 3 WID ready for approval
  Completed the Generic architecture for RT and AR/MR (GA4RTAR). TS 26.506 ready for approval.
  Ready to perform selection testing during the summer for EVS Codec Extension for Immersive Voice and Audio Services (IVAS_Codec).
  Completed Feasibility Study on Smartly Tethering AR Glasses (FS_SmarTAR). TR 26.806 v2.0.0 ready for approval
  Feasibility Study on AR and MR QoE Metrics (FS_ARMRQoE) TR 26.812 presented for information.
2 new WIDs and 3 new SIDs targeting Rel-18
  5G-Advanced media PROfiles for MessagIng Services (PROMISE)
  5G Media Streaming Protocols Phase 2 (5GMS_Pro_Ph2)
  Feasibility Study on Film Grain synthesis (FS_FGS)
  Feasibility Study on new HEVC profiles and operating points (FS_HEVC_Profiles)
  Feasibility Study on Avatars for Real-Time Communication (FS_AVATAR)
One ongoing SID targeting Rel-19
  Study on Diverse audio Capturing system for End-user Devices (FS_DaCED)
Keeping focus on Rel-18. Rel-19 planning to be discussed starting from December 2023

## Slide 9: CRs to features in Release 17 and earlier 1/2
SP-230546 : Rel-16 CRs on 5GMS3: corrections
  CR 26.117-0003 and CR 26.117-0004 on [5GMS3] Corrections to references (Rel-16 and Rel-17): Corrections to internal references.
  CR 26.512-0033 rev2 on [5GMS3] Rel-17 corrections (Rel-17): renaming conflicting YAML information element names.
  CR 26.512-0033 rev5 on [5GMS3, TEI17] Rel-17 corrections (Rel-17): resolving further element names conflict, adding version indication, clarify server URL format, expose when a policy template is not acceptable, add domain name aliases when reserving server certificates.
  CR 26.512-0035 on [5GMS3] Rel-16 corrections (Rel-16): Rel-16 subset of issues resolved just above.
SP-230547 : Rel-16 CRs on 5GMSA: Feature description
  CR 26.501-0067 rev2 on [5GMSA, TEI17] Feature description and CR 26.501-0068 rev2 on [5GMSA] Feature description: A high-level description of 5G Media Streaming features is added.
SP-230548 : Rel-17 CR on 5MBP3: Manifest format for Object Collection and Carousel
  CR 26.517-0007 rev5 on [5MBP3] Manifest format for Object Collection and Carousel.

## Slide 10: CRs to features in Release 17 and earlier 2/2
SP-230549 : Rel-17 CRs on 5MBUSA
  CR 26.502-0015 rev9 on [5MBUSA] Object Distribution Method and notification event corrections (Rel-17). Corrected specification of notification events, improved specification of Object Distribution Method, object ingest base URL definition corrected. Linked to corrections to TS 29.580.
  CR 26.502-0023 rev2 on Security mechanisms for MBS traffic (Rel-17). Adding security support in static information model and the MBS Distribution Session (Announcement) parameters and general description for the MBS security mechanism referring to TS 33.501.
SP-230550 : Rel-17 CRs on EVEX
  CR 26.532-0003 rev4 on [EVEX] Data Reporting Configuration Inclusion of Data Sampling Rules and Data Reporting Rules (Rel-17).
  CR 26.531-0005 rev1 on [EVEX] Provisioning of Data Collection and Reporting Configuration (Rel-17).
  CR 26.531-0006 rev1 on [EVEX] Precedence Rules on Data Collection, Reporting and Event Exposure (Rel-17).
SP-230551 : Rel-17 CRs on ITT4RT
  CR 26.114-0554 rev1 and CR 26.114-0555 on scene description-based overlays (Rel-17 & Rel-18).
  CR 26.114-0552 and CR 26.114-0553 rev1 on [ITT4RT] Correction to SDP example for itt4rt_group (Rel-17 & Rel-18).

## Slide 11: Overview of work progress Rel-18 Work Items
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950014 | Immersive Real-time Communication for WebRTC | iRTCW | 12/12/2023 | 30% | SP-221032 | 55% | 
950015 | Media Capabilities for Augmented Reality | MeCAR | 12/12/2023 | 40% | SP-220242 | 60% | 
960042 | IMS-based AR Conversational Services | IBACS | 12/12/2023 -> 3/3/2024 | 20% | SP-230165 | 30% | 
960044 | Generic architecture for RT and AR/MR | GA4RTAR | 6/6/2023 | 70% | SP-220672 | 100% | Stage 2 – Complete
960045 | Split Rendering Media Service Enabler | SR_MSE | 12/12/2023 -> 3/3/2024 | 25% | SP-220685 | 40% | 
960046 | Real-time Transport Protocol Configurations | 5G_RTP | 12/12/2023 -> 3/3/2024 | 15% | SP-220613 | 35% | Revised WID in SP-230541
830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 12/12/2023 | 30% | SP-190040 | 40% | 
770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 03/03/2024 | 55% | SP-220608 | 65% | 
960043 | UE Testing Phase 2 | eUET | 12/12/2023 | 20% | SP-220610 | 30% | 
980009 | 5G Media Streaming Audio codec phase 2 for 5G-Advanced | 5GMS_Audio_Ph2 | 3/3/2023 | 100% | SP-221033 |  | Complete
960047 | 5G Media Streaming Architecture Phase 2 | 5GMS_Ph2 | 6/6/2023 | 50% | SP-230164 | 100% | Stage 2 – Complete
980007 | Enhanced Multiparty RTT | MP_RTT | 12/12/2023 | 5% | SP-221346 | 30% | 
990025 | Immersive Audio for Split Rendering Scenarios | ISAR | 03/2024 | 0% | SP-230167 | 10% | 

## Slide 12: CRs to completed Rel-18 items and TEI18
SP-230552 : Rel-18 CR on Corrections to references (5GMS_Audio_Ph2)
  CR 26.117-0002 on Corrections to references (Rel-18).
SP-230552 : Rel-18 CR on 5GMS Service URL (FS_5GMS_EXT, TEI18)
  CR 26.804-0005 rev2 on 5GMS Service URL (Rel-18).

## Slide 13: Immersive Real-time Communication for WebRTC (iRTCW)
Purpose
Define a non-vertical/modularized protocol stack, functional components, I/Os formats, for iRTC clients to support WebRTC-based real-time transport of media over 5G; Identify the required architecture for radio access network QoS realization over 5G systems. Identify the minimum information / elements in the C/U-Plane signal to establish media sessions with appropriate QoS for WebRTC-based applications. Document informative examples of iRTC operations to assist implementers.
Progress in the last quarter
A figure for the functional components of iRTC (following a similar figure of MTSI)
Simple WebRTC Signaling Protocol
Refer baseline XR client architecture defined in MeCAR
Clarify text can be entered into iRTC client via user interface
Sent LS to CT WGS on the iRTCW signalling protocol
Update TS 26.113 to clarify operation of the SWAP protocol
Next steps
Progress TS 26.113 to v1.0.0
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950014 | Immersive Real-time Communication for WebRTC | iRTCW | 12/12/2023 | 30% | SP-221032 | 55% | 

## Slide 14: Media Capabilities for Augmented Reality (MeCAR)
Purpose
Define at least one AR device category that addresses the constraints of an EDGAR-type AR glass. Integrate IVAS once available. Define capability exchange mechanisms based on complexity of AR media and capability of device to support EAS KPIs for provisioning of edge/cloud resources. Identify QoE metrics and KPIs for AR media. Specify encapsulations into RTP, ISOBMFF and CMAF. Specify the relevant codec-level parameters for session setup. Enable AR media in 5G Media Streaming. Define typical traffic characteristics for AR media
Progress in the last quarter
Audio capabilities with MPEG-4 Low Delay AAC v2 and EVS for which the encoding and decoding capabilities are described in the permanent document as a basis for further analysis on their applicability.
QoE metrics framework aspects including the identification of the observation points and associated timestamps, call flow on QoE timing measurement as well as available visualization space.
Proposals to consider compression formats for volumetric video such as MIV and V-PCC under the V3C format for transporting visual volumetric media.
Agreed to document into the permanent document some use cases illustrating the use of volumetric video addressing content creation.
It remains to be clarified which representation formats could be supported by which device type before considering associated compression candidates.
Good progress made in updating the Draft TS with a list of working assumptions on the device reference design and how to connect the media capabilities with the XR runtime and rendering loop functions specific to XR devices.
Agreed version of an XR baseline device architecture! Invite other Work or Study Items to refer to it if needed and provide feedback eventually.
Next steps
Draft TS 26.119 v1.0.0 to be sent to SA plenary for information
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950015 | Media Capabilities for Augmented Reality | MeCAR | 12/12/2023 | 30% | SP-220242 | 40% | 

## Slide 15: IMS-based AR Conversational Services (IBACS)
Purpose
The objective of this work item is to create a new specification for IMS-based AR conversational services. The features for RTP-based real-time communication, which can be used by IMS and non-IMS (AR) conversational services, will be specified in another new specification (as part of the 5G_RTP work). The relevant features and functional components specified for MTSI in TS 26.114 will be referenced and/or enhanced, if required.
Progress in the last quarter
Updates to PD (552 (section 2.1 + 2.2 only), 694 and 697)
  Rendering for AR communication
  Generic Call Flows for Avatar Calls
  Split rendering architecture and call flow
  AR communication architecture alignment with SA2 (updates still expected)
  3D model exchange with MRF
  UE AR procedures and rendering
  Clarifications on spatial description
Completion date moved to March 2024
Next steps
Progress the permanent document and TS 26.264
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960042 | IMS-based AR Conversational Services | IBACS | 12/12/2023 -> 3/3/2024 | 20% | SP-230165 | 30% | 

## Slide 16: Generic architecture for Real-Time and AR/MR media (GA4RTAR)
Purpose
This WID is the follow-up normative work from the recommendations in TR 26.998 and TR 26.928, SA2 Stage 2 TR (TR 23.700-87) and SA1 requirements (TR 22.873). The work scope of this WID is focused on the 5G generic architecture for real-time media communication. Other aspects such as AR Runtime, Scene Manager, and Codecs of the Media Access Function will be addressed by MeCAR WID, which is in synergy with this work. This new architecture will follow the principles and use the 5GMS architecture, specified in TS 26.501, as a baseline.
Progress in the last quarter
Draft TS 26.506 5G Real-time Media Communication Architecture (Stage 2) updated with:
  Call flow for collaboration scenario 3 agreed
  Call flow for AF-driven RTC edge processing agreed
  Annex A updated to be normative
  Adding a prefix of “RTC” to the term MSH in architecture
  5GS centric architecture diagram
  Support of ANBR-based network assistance
TS 26.506 to be presented in SA plenary for approval (SP-230536)
Work Item Summary endorsed (SP-230554)
Next steps
Maintenance
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960044 | Generic architecture for RT and AR/MR | GA4RTAR | 6/6/2023 | 70% | SP-220672 | 100% | Stage 2 – Complete

## Slide 17: Split Rendering Media Service Enabler (SR_MSE)
Purpose
This work item will develop a Media Service Enabler that packages all the required enablers and defines the required formats and protocols to make split rendering accessible to media service and application providers. The package is aligned with the philosophy of Media Service Enablers and envisions deployments as an SDK that is offered to application developers.
Progress in the last quarter
TS 26.565 Split Rendering Media Service Enabler progressed to v0.5.0
  Improvements and Corrections to edge and dynamic policy procedures in SR
  General updates to TS26.565
  SR Rendering API
  Pixel Streaming Media Profile
  pCR on signaling for SR session control
  On SR configuration API and view configuration
Revised completion date to March 2024
Next steps
Refine split rendering functionality. Perform final alignment with other work items.
Agree API IDL definitions and implementation guidelines.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960045 | Split Rendering Media Service Enabler | SR_MSE | 12/12/2023 -> 3/3/2024 | 25% | SP-220685 | 40% | 

## Slide 18: 5G Real-time Transport Protocols (5G_RTP)
Purpose
The objective of this work item is to specify functionalities of RTP to improve support for traditional and immersive real-time services and enablers. To develop a commercially relevant set of functionalities that only include technologies that are either commercially relevant or deployed or demonstrate clear performance or relevant functionality that justifies introducing additional implementation or interoperability complexity.
Progress in the last quarter
The basic foundation of the RTP Header Extension for PDU Sets has been agreed and inserted in the TS 26.522. This will be sent to SA2 in order to be referenced.
Update of TS 26.522 includes: SDP signaling for PDU Set and EoB marking, Guidelines for marking PDU Set importance, PDU Set size semantics, Reuse of rendered pose RTP HE in multiple streams, Clarifications on the definitions
Other contributions on RTP Header Extension have been agreed for the Permanent Document and will be considered for further developments (use cases, pose information, time to next burst, end of burst signaling, reports for PDU Sets).
Completion date revised to March 2024
Next steps
Specify RTP functionalities that support IMS-, WebRTC-, split rendering-based XR services and enablers (e.g., multiple simultaneous RTP streams in a single RTP session, multiple RTP sessions, RTP retransmission, RTP header extensions, FEC, RTP retransmission, SRTP, RTCP feedback reporting procedures). Specify usage of SDP to configure RTP appropriately.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960046 | Real-time Transport Protocol Configurations | 5G_RTP | 12/12/2023 -> 3/3/2024 | 15% | SP-220613 | 35% | Revised WID in SP-230541

## Slide 19: Terminal Audio quality performance and Test methods for Immersive Audio Services (ATIAS)
Purpose
The overall objective of this work item is to develop a set of test specifications similar to TS 26.131 and 26.132 for objective characterization of terminals for 3GPP immersive services. This covers both conversational services based on MTSI / telepresence and non-conversational services. The tests will be limited to the use of an acoustic or a digital / analog audio interface.
Progress in the last quarter
Three proposed updates on test methods covering DoA, spatial separation and level calculations were agreed. Proposed updates on stereo testing, lowest frequency for MASA test signals and general comments on the current ATIAS Pdoc were reviewed. An update of the ATIAS-1 PD merging all proposed updates was agreed.
Next steps
Progress Performance Requirements (TS 26.261) and Test Methods (CR to TS 26.260)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 12/12/2023 | 30% | SP-190040 | 40% | 

## Slide 20: EVS Codec Extension for Immersive Voice and Audio Services (IVAS_Codec)
Purpose
The overall objective of this work item is to develop a single general-purpose audio codec for immersive 4G and 5G services and applications including the VR use cases envisioned in 3GPP TR 26.918.
Progress in the last quarter
Significant achievement:
  IVAS-1 Overview -- agreed as v.0.5.0, next working draft
  IVAS-2 Project Plan – agreed as v.0.7.0, next working draft
  IVAS-3 Performance Requirements – approved as v.1.1.0, update of v.1.0.0
  IVAS-4 Design Constraint – approved as v.1.2.0, update of v.1.1.0
  IVAS-5 Selection Rules – approved as v.1.0.0
  IVAS-6 Selection Deliverables –approved as v.1.0.0
  IVAS-7a Processing Plan for Selection Phase – approved as v.1.0.0
  IVAS-8a Selection Test Plan – approved as v.1.0.0
Offer was received and accepted for Global Analysis Lab (GAL) function from HEAD Acoustics
The 4 Listening Labs reserved their capacities for July and August to run the tests. ETSI MCC is tasked to sign the service contracts (for a total of 646k€) with LLs and GAL before June 27.
Multiparty NDA and payments are all on track
Prepared material collection for selection test
An invitation was circulated over the reflector to get offers for floating-point to fixed-point conversion, as part of characterization phase, and one offer was received.
Discussed Rapporteurship of IVAS specifications
Next steps
Submission of IVAS codec candidate executable; sign service contracts with LL and GAL; run selection tests; Review test report; Codec selection at SA4#125.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 03/03/2024 | 55% | SP-220608 | 65% | 

## Slide 21: Enhancements to UE Testing (eUET)
Purpose
In TS 26.131 and TS 26.132: Define missing SWB frequency masks and review related test methods. Update "Jitter buffer management behavior" and "Test conditions" for jitter buffer management. Develop a new specification to verify correct implementations of the RTP payload format for 3GPP codecs. Review receiving performance of UEs at maximum volume control and define, if necessary, requirements and test methods to ensure an adequate user experience. Document in TR 26.801 any relevant finding from the round robin activity and additional tests conducted in the Rel-17 HaNTE work.
Progress in the last quarter
One Tdoc providing a status update on JBM performance tests was discussed and noted.
Updated SWB measurement results for eUET results were presented – further results and proposed frequency masks are expected at the next meeting. Draft changes to TS 26.131 and 26.132 for JBM performance testing were discussed, however this proposal needs further details for consideration
Next steps
Progress discussions on new specification for RTP payload format conformance, performance requirements (TS 26.131), test methods (TS 26.132), test results on HaNTE (TR 26.801)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960043 | UE Testing Phase 2 | eUET | 12/12/2023 | 20% | SP-220610 | 30% | 

## Slide 22: 5G Media Streaming Architecture Phase2 (5GMS_Ph2)
Purpose
The Work Item has the following objectives: Uplink streaming, End-to-end low latency live streaming, 5GMS over 5MBS, 5GMS hybrid services (5MBS and 5GMS) and Hybrid DASH/HLS operation
Progress in the last quarter
Completed work with following CRs for approval: SP-230545: Rel-18 CRs on 5GMS_Ph2
  5GMS AS configuration via M3
  Multiple-manifest: Improvements on the multiple manifest downlink streaming call flow
  Uplink Streaming: editorial correction
  Data collection for ANBR-based NA
  5GMS over 5MBS
  Feature description, dynamic policies and Service URL handling
Corresponding Stage 3 Work Item agreed
Next steps
Maintenance
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960047 | 5G Media Streaming Architecture Phase 2 | 5GMS_Ph2 | 6/6/2023 | 50% | SP-230164 | 100% | Stage 2 – Complete

## Slide 23: Enhanced Multiparty RTT (MP_RTT)
Purpose
This WI will specify suitable solutions for multiparty RTT media in IMS, for both RTP and IMS data channel transport, focusing on the transport format and procedures in IETF RFC 9071
Progress in the last quarter
Agreed on architecture and call flow for IMS data channel solution
Documented an RTP based solution including architecture and call flows
Updated the Permanent Document accordingly
Next steps
Discuss the comparisons and guidelines between RTP and IMS data channel solutions.
Interworking and security considerations.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
980007 | Enhanced Multiparty RTT | MP_RTT | 12/12/2023 | 5% | SP-221346 | 30% | 

## Slide 24: Immersive Audio for Split Rendering Scenarios (ISAR)
Purpose
The overall objective of this work item is to develop solutions for immersive binaural audio on head-tracked devices that are compatible with the envisaged split architectures (MeCAR, 26.998). The solutions should consider low-complex and lightweight devices and demonstrate operational benefits over solutions with full decoding and rendering in the end device.
Progress in the last quarter
Initial requirements document from was agreed as the basis of further work.
Work plan was agreed.
Contributions were received on ISAR requirements covering scenarios, architectures, interfaces, with a certain degree of overlap. Inputs from all contributions were included in the next version of the ISAR requirements TR 26.865, removing overlap and cleanup in editing sessions. The result was agreed as the next working draft.
Next steps
Agree on TR on ISAR requirements v.2.0.0 to be sent to SA plenary for approval
Initiate work on solutions for Immersive Audio for Split Rendering Scenarios also considering potential solutions offered by the IVAS work item
Initiate work on performance characterization of solutions for Immersive Audio for Split Rendering Scenarios also considering potential solutions offered by the IVAS work item
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
990025 | Immersive Audio for Split Rendering Scenarios | ISAR | 03/2024 | 0% | SP-230167 | 10% | 

## Slide 25: Overview of work progress Study Items
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
870013 | Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems | FS_XRTraffic | 6/6/2023 -> 9/9/2023 | 90% | SP-210043 | 95% | 
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 12/12/2023 -> 3/3/2024 | 25% | SP-220328 | 35% | 
960048 | Study on Media Streaming aspects of Network Slicing Phase 2 | FS_MS_NS_Ph2 | 12/12/2023 | 25% | SP-220675 | 40% | 
950012 | Study on immersive Real-time Communication for WebRTC Phase 2 | FS_eiRTCW | 3/3/2024 | 35% | SP-220239 | 45% | 
950013 | Study on Smartly Tethering AR Glasses | FS_SmarTAR | 6/6/2023 | 70% | SP-220240 | 100% | Complete
960049 | Study on AR and MR QoE Metrics | FS_ARMRQoE | 12/12/2023 | 15% | SP-220616 | 27% | 
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 9/9/2024 | 5% | SP-221330 | 30% | Rel-19
960050 | Study on Audio Aspects for Glasses-type AR/MR Devices | FS_Audio_5GSTAR | 12/2022 | 100% | SP-220617 |  | Complete
940010 | Study on 5G Media Service Enablers | FS_5G_MSE | 12/2022 | 100% | SP-211338 |  | Complete

## Slide 26: Feasibility Study on Typical Traffic Characteristics for XR Services and other Media (FS_XRTraffic)
Purpose
Objective: Collect and document traffic characteristics for different services, and additional information, such as codecs and protocols in use. Identify additional relevant XR and other media services and document their traffic characteristics.
Progress in the last quarter
Agreed the transfer of the remaining useful material from Permanent document to the Draft Technical report
The study is close to completion, but more time is needed for a sanity check.
Study expected to be completed by the next SA4 meeting in August.
Next steps
Present TR 26.926 in version 2.0.0 for approval
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
870013 | Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems | FS_XRTraffic | 6/6/2023 -> 9/9/2023 | 90% | SP-210043 | 95% | 

## Slide 27: Feasibility Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media (FS_AI4Media)
Purpose
The objectives of the study item are primarily to identify relevant interoperability requirements and implementation constraints of AI/ML in 5G media services.
Progress in the last quarter
Document one use case related to Natural Language Processing into the PD.
A significant part of the time at both meetings was allocated to the definition of the evaluation framework for which needs have been listed such as a repository of Test data, scripts, AIML models, configuration files. Evaluation framework is a significant piece of work that needs a study item update reflecting this objective, the creation of dedicated working documents, a PD and a specific TR.
Also progressed the implementation of federated learning control plane messages and architecture workflows and procedures for split operations.
Next steps
Agree on TR 26.927 v1.0.0 to be sent to SA plenary for information
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 12/12/2023 -> 3/3/2024 | 25% | SP-220328 | 35% | 

## Slide 28: Study on Media Streaming aspects of Network Slicing Phase 2 (FS_MS_NS_Ph2)
Purpose
List and describe use cases that can be addressed using network slicing, and study collaboration scenarios and deployment architectures to support network slicing for media services. Describe and document provisioning aspects for configuring media services with one or more network slices at M1. Identify impact of network slicing on dynamic policy invocation APIs at M5. Identify potential areas for normative work as the next phase.
Progress in the last quarter
3GPP TR 26.941 progressed to V0.5.0 and now includes Candidate Solution for Key Issue #1: Service Provisioning.
Sent an LS on network slice replacement procedure to SA2
Next steps
Progress work on:
  Description of key issues and candidate solutions
  Identification of possible new key issues in scope of TR 26.941 for inclusion in TR
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960048 | Study on Media Streaming aspects of Network Slicing Phase 2 | FS_MS_NS_Ph2 | 12/12/2023 | 25% | SP-220675 | 40% | 

## Slide 29: Feasibility Study on the enhancements for immersive Real-time Communication for WebRTC (FS_eiRTCW)
Purpose
In addition to the foreseen approach identified in TR 26.998 (Support of 5G glass-type AR/MR devices) and taken in WID on iRTCW (immersive Real-time Communication for WebRTC), which leaves C-plane signalling details open and simply makes use of the northbound APIs for end-to-end QoS), the possibility of another approach (i.e., defining a set of advanced details (including C-plane signalling) for the common and wider use among several WebRTC implementations) will be investigated under this SID.
Progress in the last quarter
Signalling protocol requirements and Signalling protocol details were discussed
Update to Permanent Document to include:
  High-level network model and target use cases
  Possible architecture for collaboration scenario #4
Next steps
Progress TR 26.930
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950012 | Study on immersive Real-time Communication for WebRTC Phase 2 | FS_eiRTCW | 6/6/2023 -> 3/3/2024 | 30% | SP-220239 | 35% | 

## Slide 30: Feasibility Study on Smartly Tethering AR Glasses (FS_SmarTAR)
Purpose
Defining different tethering architectures for AR Glasses including 5G sidelink and non-5G access based on existing 5G System functionalities. Study the relationship with PIN (Personal IoT Network). Identify media handling aspects. Identify end-to-end QoS-handling of tethering. Provide recommendations for suitable architectures to meet typical AR requirements such as low power consumption, low latency, high bitrates, security and reliability.
Progress in the last quarter
TR 26.806 Study on Tethering AR Glasses – Architectures, QoS and Media Aspects (Rel-18, FS_SmarTAR) progressed to v1.4.0. Latest additions:
  Editorials (references, terms etc.)
  Key Issue #5: Compute distribution across UE and network for tethered glasses
  Updates to Key Issue #2: How to determine the non-5G delay for the 5G relay architecture and Updates to Key Issue #3: What and how to report the non-5G delay
  End-to-end QoS metrics aspects, updates to End-to-end delay measurement solution, detailed Call-flows
TR 26.806 v2.0.0 ready for approval
Next steps
Maintenance
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950013 | Study on Smartly Tethering AR Glasses | FS_SmarTAR | 6/6/2023 | 70% | SP-220240 | 100% | Complete

## Slide 31: Feasibility Study on AR and MR QoE Metrics (FS_ARMRQoE)
Purpose
Collect relevant external information on QoE Metrics for AR and XR services. Conduct subjective tests on XR QoE metrics, if considered relevant. Collect a set of relevant XR QoE Metrics and define their impact on the user experience. Based on a well-defined device architecture based on MeCAR, define the relevant observation points and define the measurement and derivation of relevant XR QoE metrics. Study the support of XR QoE metrics in 3GPP metrics collection frameworks such as NWDAF, RRC-based metrics configuration and collection, etc. Provide recommendation on normative work for new XR QoE metrics based on the findings in this study.
Progress in the last quarter
TR 26.812 progressed to V0.5.0
  Agreed to document the typical procedures for ARMR QoE metrics identification and the observation points monitoring.
  Progressed the identification of the observation points for monitoring QoE parameters.
  Particularly focused on pose error prediction and delays related to one way and round-trip time.
Next steps
Agree on Draft TR 26.812 v1.0.0 to be sent to SA plenary for information
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960049 | Study on AR and MR QoE Metrics | FS_ARMRQoE | 12/12/2023 | 15% | SP-220616 | 27% | 

## Slide 32: Study on Diverse audio Capturing system for End-user Devices (FS_DaCED)
Purpose
This study item considers codec-independent immersive voice and audio capturing configurations for end-user devices. The outcome of the studies can be used as guidelines for the manufacturers to deploy immersive voice and audio services.
Progress in the last quarter
TR 26.933 was progressed to v0.1.0 and agreed as basis for further work.
Two text proposals on summary of phone size and stereo capture were agreed.
Proposed new text on binaural capture was reviewed and included in the TR.
Next steps
Continue to work on:
  Components used in audio capture.
  Acoustic design including acoustic structure, microphone array design, etc.
  Signal processing Including necessary relevant processing for audio format, enhancement solution for immersive, speech enhancement, etc
Start work on: Characterization of the audio capture performance
Complete work on: UE categories determination;
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 9/12/2024 | 0% | SP-221330 | 5% | Rel-19

## Slide 33: New Work and Study Item(s)
Note: Progress since last SA is shown with blue colour.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000015 | 5G-Advanced media profiles for messaging services | PROMISE | 3/3/2024 |  | SP-230542 |  | 
1000018 | 5G Media Streaming Protocols Phase 2 | 5GMS_Pro_Ph2 | 3/3/2024 |  | SP-230543 |  | 
1000016 | Feasibility Study on Film Grain synthesis | FS_FGS | 12/12/2023 |  | SP-230539 |  | 
1000017 | Feasibility Study on new HEVC profiles and operating points | FS_HEVC_Profiles | 3/3/2024 |  | SP-230540 |  | 
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 3/3/2024 |  | SP-230544 |  | 

## Slide 34: 5G-Advanced media PROfiles for MessagIng SErvices (PROMISE)
Purpose
The purpose of this Work Item is to specify SMS/MMS/RCS/Messaging formats and codecs that GSMA and other organizations or application vendors can then reference and/or profile to improve messaging service quality and interoperability.
In particular the following objectives are addressed
  1) Adding or upgrading codecs and formats in 3GPP TS 26.140, 3GPP TS 26.141.
    a. Specify the EVS codec and introduce support for Super-Wideband and Full band for speech message.
    b. When the IVAS codec is completed & approved in 3GPP, it should be added to speech messaging.
    c. Specify support for xHE-AAC codec for audio messaging in addition to aacPlus and AMR-WB+, in alignment with 5GMS TS 26.511.
    d. Add basic formats to support exchange 3D scenes and assets, based on Khronos glTF and MPEG-I Scene Description possibly in alignment with TS 26.119 and based on VR Audio/Video formats and codecs, in alignment with 5GMS TS 26.511 and TS 26.118.
    e. Upgrade video profiles in alignment with 5GMS TS 26.511.
  2) Removing codecs and formats in 3GPP TS 26.140, 3GPP TS 26.141;
    a. Consider each profile and formats in light of deployed services and remove unused ones.
  3) Create a new Messaging Media profiles specification for potential reference by MMS, GSMA RCS and third-party messaging application potentially used over the 5G System.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000015 | 5G-Advanced media profiles for messaging services | PROMISE | 3/3/2024 |  | SP-230542 |  | 

## Slide 35: 5G Media Streaming Protocols Phase 2 (5GMS_Pro_Ph2)
Purpose
The work item addresses stage-3 support for 5GMS protocol extensions for provisioning, ingest, user plane, control plane and device APIs for the following functionalities:
  uplink streaming
  end-to-end low latency live streaming
  5GMS over MBS and 5GMS hybrid services
  support for multiple media service entry points
  traffic identification
  Addition of HTTP/3 to the 5GMS protocols
  Background Data Transfer
  usage of Oauth 2.0
  3GPP Service Handler and URL
  enhancements based on feedback from 5G-MAG Reference tool developments
  Specification of data types for data reporting of ANBR-based Network Assistance invocations
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000018 | 5G Media Streaming Protocols Phase 2 | 5GMS_Pro_Ph2 | 3/3/2024 |  | SP-230543 |  | 

## Slide 36: Feasibility Study on Film Grain synthesis (FS_FGS)
Note: Progress since last SA is shown with blue colour.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000016 | Feasibility Study on Film Grain synthesis | FS_FGS | 12/12/2023 |  | SP-230539 |  | 
Purpose
This study aims to:
  1. Define motivating use cases and scenarios for the use of Film Grain synthesis in 5G video video services.
  2. Document relevant existing Film Grain Synthesis technologies that are not included in 3GPP today.
  3. Provide evaluation using HEVC of the benefits/drawbacks of corresponding solutions, including film grain characteristics SEI message (ITU-T H.274) including performance results, complexity and implementation aspects, interoperability, system integration, etc. following the example in TR26.955 based on selected scenarios.
  4. Use the characterization framework in TR26.955 when possible and extend it when necessary, i.e. with subjective tests results.
  5. Study and identify relevant UE requirements for consistent usability of the technology.
  6. Collaborate with MPEG/JVET and other organizations to ensure broad interoperability across different ecosystems.
  7. Identify relevant interoperability and system level aspects to potentially support Film Grain Synthesis.
  8. Identify if any new normative work would be justified and if so, provide relevant conclusions.
This study will be done in collaboration with other organizations as needed, e.g. JVET, MPEG, CTA WAVE, 5G-MAG, DASH-IF etc.

## Slide 37: Feasibility Study on new HEVC profiles and operating points (FS_HEVC_Profiles)
Note: Progress since last SA is shown with blue colour.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000017 | Feasibility Study on new HEVC profiles and operating points | FS_HEVC_Profiles | 03/03/2024 |  | SP-230540 |  | 
Purpose
This study aims to:
  1. Identify and gather the opportunities for improving HEVC-based services. This will include documentation of motivating use cases and scenarios. Use cases and scenarios include (listed in priority):
  2. Gather HEVC based solutions to address each opportunity. This will also include relevant existing HEVC profiles that are not included in 3GPP specifications today. In particular, the following solutions, in order of priority, have been identified and will be studied:
    a. HEVC Multiview profiles,
    b. HEVC Scalable profiles, and
    c. HEVC 4:4:4 (up to 10 bits) capable profiles.
  Other solutions may also be included, if identified, at a later stage.
  3. Define a methodology to investigate and document the pros and cons of the proposed solutions for each key issue including performance results, complexity and implementation aspects, etc. Two of the possibilities are:
  4. Conclude on the relevancy of each solution for the key issues and propose a way forward, also identifying if any new normative work would be justified.
This study will be done in collaboration with other organizations as needed, e.g. MPEG, CTA WAVE, 5G-MAG, DASH-IF etc.

## Slide 38: Feasibility Study on Avatars for Real-Time Communication (FS_AVATAR)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 3/3/2024 |  | SP-230544 |  | 
Purpose
The study item has the following objectives:
  Identify and extract the Avatar-related use cases and requirements as defined in TR22.856.
  Document the use cases for Avatars and classify avatar representations,
  Collect and document Avatar animation and representation approaches:
  Document the requirements for an interoperable base Avatar format:
    Prioritize deployed representations.
  Document formats for the animation data,
  Study the integration of Avatars into the RTC services (including WebRTC and IMS),
  Study the cross-operation with split rendering,
  Investigate the QoS, processing, and storage requirements for Avatars,
  In collaboration with SA3, investigate security aspects of Avatars, including authentication, privacy, DRM, …
  Document the network procedures and the impact on the 5G-RTC architecture.
  Discuss with relevant 3GPP groups on architecture and security aspects.
NOTE: this study will not impact the integration of volumetric video formats such as V3C.

## Slide 39: Dependencies on IETF drafts in SA4
No new dependency introduced
All dependencies removed
IETF dependencies in SA4: new ones with red colour, those removed with green colour, and other updates by blue colour:
IETF draft name | 3GPP spec. number | CR# which introduced the dependency | Responsible person (in SA4) | Feature (Release) | Comments

## Slide 40: Summary of action items
Action Points from SA#99 to SA4:
  AP to SA4 : provide WG input to SA Rel-19 Workshop
    See input to Rel-19 Workshop
Action items from SA4 to SA#100:
  Approve all SA4 agreed CRs
  Approve TS 26.506
  Approve TR 26.806
  Approve 3 new Work Items, 1 revised Work Item, 1 revised Study Item and 2 new Study Items