## Slide 1: SA WG6 status report to TSG SA#105
Atle Monrad
SA6 Chair (InterDigital Communications)

## Slide 2: SA6 Leadership
Chair:
  Mr. Atle Monrad InterDigital Corporation / ATIS1
Vice-chairs:
  Mr. Jukka Vialen Airbus DS SLC / ETSI2
  Mr. Basavaraj (Basu) Pattan Samsung Electronics Ind. Co., Ltd. / TTA3
Secretary:
  Bernt Mattsson (MCC)
1 Elected February 2024
2 Re-elected for third term April 2023
3 Re-elected by acclamation for second term at SA6#62

## Slide 3: Executive Summary
Two meetings held in Q3 2024
  SA6#62 ad-hoc-e, 10 – 18 July 2024
  SA6#62, 19 – 23 August 2024
Rel-15/Rel-16/Rel-17 activities
  0 CRs agreed
Rel-18 activities
  29 CRs agreed
Rel-19 activities
  68 CRs agreed and 226 pCRs approved
  Good progress on SIDs, 5 of the 8 studies are completed
  1 TR provided for information and 4 TRs provided for approval
  Normative work has started and is progressing according to the conclusions of the corresponding studies
  Revised WIDs: XR and Metaverse – functionality aligned/adjusted
  New follow-up WIDs from studies: CAPIF_Ph3 and Generic_IOPS
  New SID: SEAL enhancements

## Slide 4: Ongoing and upcoming topics
Release 19 Progress
  Most SIDs are completed.
  Most corresponding WIDs to the SIDs (7 out of 8) are provided for approval.
  All WIDs progress according to plan
  Two SIDs are pending conclusions in SA2 before completion. This delay corresponding normative work.
  On all open SIDs, work move from study phase towards normative work as topics are concluded.
  One additional study item proposal is provided on enhancements to SEAL on improvements and enhancements to network capabilities exposure.
Other topics
  Rapporteurs are asked how to handle Editor’s Notes in frozen releases.
  Discussions will be initiated on how to approach Rel-20 and Rel-21.
Meeting Schedule for next quarter
  October 2024 – SA6#63 Hyderabad, India.
  November 2024 – SA6#64 Orlando, USA

## Slide 5: SA6#62 Ad-Hoc-e Statistics
Meeting dates: 10 – 18 July 2024
  E-meeting, daily confcalls
Statistics
  200 Tdoc numbers initially reserved, 332 Tdoc numbers used by end-of-meeting
  9 Agreed CRs for Rel-19
  107 Approved pCRs for Rel-19
  17 incoming LSs, 4 Approved outgoing LSs
  Time allocation: Rel-19: ~100%
Conference calls (pre-SA6#62 Ad-Hoc-e)
  4 informal conference calls

## Slide 6: SA6#62 Statistics
Meeting dates: 19 – 23 August 2024
  5 quarters on Monday, 5 quarters on Tuesday – Thursday, 3 quarters on Friday
Statistics
  306 Tdoc numbers initially reserved, 703 Tdoc numbers used by end-of-meeting
  88 Agreed CRs - 0 for pre Rel-18, 29 for Rel-18, 59 for Rel-19
  119 Approved pCRs for Rel-19
  5 incoming LSs, 4 Approved outgoing LSs
  Time allocation: Pre-Rel-19: ~15%; Rel-19: ~85%
Conference calls (pre-SA6#62)
  4 informal conference calls

## Slide 7: Number of Tdocs in SA6

## Slide 8
Number of approved pCRs & agreed CRs per SA6-meeting

## Slide 9: Progress of approved Release 19 Study Items
UID | Name | Acronym | Target Month/year | Old % | WID | New %
1000035 | Enhanced application layer support for location services | FS_eLSAPP | Sep-2024 | 85% | SP-230778 | 100%
1000034 | Service aspects for supporting the eMMTel service | FS_eMMTelAPP | Sep-2024 | 70% | SP-230779 | 80%
1010005 | Application layer support for AI/ML services | FS_AIMLAPP | Sep-2024 | 95% | SP-231182 | 100%
1020052 | Application enablement for Localized Mobile Metaverse Services | FS_MetaverseApp | Sep-2024 | 70% | SP-231806 | 100%
1020051 | Application enabler for XR Services | FS_XRApp | Sep-2024 | 65% | S6-233295 | 90%
1020053 | Application enablement for Satellite access enabled 5G Services | FS_5GSAT_Ph3_App | Sep-2024 | 60% | SP-231738 | 100%
1020062 | CAPIF Phase 3 | FS_CAPIF_Ph3 | Sep-2024 | 55% | SP-231741 | 90%
1040071 | MC services for generic support on IOPS mode of operation | FS_Generic_IOPS | Dec-2024 | 0% | SP-241017 | 40%

## Slide 10: Progress of approved Release 19 Work Items 1/2
UID | Name | Acronym | Target month/year | Old % | WID | New %
1000039 | Enhanced Mission Critical Architecture | enhMC | Dec-2024 | 60% | SP-230695 | 75%
1000036 | Sharing of administrative configuration between interconnected MC service systems | MCShAC | Dec-2024 | 90% | SP-230692 | 100%
1000038 | Railways specific Enhancements to Mission Critical Services | FRMCS_Ph5 | Dec-2024 | 55% | SP-230780 | 70%
1000037 | Application Architecture for MSGin5G Service Phase 3 | 5GMARCH_Ph3 | Dec-2024 | 40% | SP-230781 | 50%
1010007 | Architecture for enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | Dec-2024 | 80% | SP-231160 | 85%
1010008 | Application Architecture for UAS applications Phase 3 | UASAPP_Ph3 | Dec-2024 | 60% | SP-230991 | 75%
1010009 | Guidelines for CAPIF Usage | CAPIF_EXT | Sep-2024 | 80% | SP-231161 | 90%
1010006 | SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | Dec-2024 | 70% | SP-230989 | 80%

## Slide 11: Progress of approved Release 19 Work Items 2/2
UID | Name | Acronym | Target Month/year | Old % | WID | New %
1040072 | Enhanced application layer support for location services | eLSAPP | Sep-2024 | 0% | SP-230778 | 30%
1040073 | Service aspects for supporting the eMMTel service | MMTel_APP | Sep-2024 | 0% | SP-230779 | 10%
1040075 | Application layer support for AI/ML services | AIML_App | Sep-2024 | 0% | SP-231182 | 40%
1040076 | Application enablement for Localized Mobile Metaverse Services | Metaverse_App | Sep-2024 | 0% | SP-231806 | 25%
1040074 | Application enabler for XR Services | XRM_Ph2_App | Sep-2024 | 0% | S6-233295 | 15%
1040077 | Application enablement for Satellite access enabled 5G Services | 5GSAT_Ph3_App | Sep-2024 | 0% | SP-231738 | 5%

## Slide 12
Future SA6 meetings
Meeting | Date | Location
2024 |  | 
SA6#63 | 14 – 18 October 2024 | Hyderabad, India
SA6#64 | 18 – 22 November 2024 | Orlando, USA
2025 |  | 
SA6#65 | 17 – 21 Feb 2025 | Athens, Greece
SA6#66 | 7 – 11 April 2025 | Gothenburg, Sweden
SA6#67 | 19 – 23 May 2025 | Japan, Location, TBC
SA6#68 | 25 – 29 August 2025 | Gothenburg, Sweden
SA6#69 | 13 – 17 October 2025 | China, Location, TBC
SA6#70 | 17 – 21 November 2025 | Dallas, USA
Planning of meetings for 2026 is in progress, 6 f2f meetings scheduled.

## Slide 13: FS_eLSAPP
Progress since SA#104:
  10 pCRs agreed, TR sent for approval
  Main Progress made for:
    3 Update Solutions for Sol#4, Sol#10 and Sol#11 respectively
    2 Solution evaluations for Sol#10 and Sol#12 respectively
    Finish Overall evaluation and Conclusions for all of KIs
RAN and other impacts and dependencies:
  None
UID | Name | Acronym | Target month/year | Old % | WID | New %
1000035 | Study on enhanced application layer support for location services | FS_eLSAPP | Sep-2024 | 85% | SP-230778 | 100%
Contentious Issues:
  None
Next steps:
  None

## Slide 14: FS_eMMTelAPP
Progress since SA#104:
  SA6#62 Adhoc-e: 5 pCRs agreed
  SA6#62: 7 pCRs agreed
  Progress made for 4 new solutions, 4 updated solutions, Architectural requirements, deployment guide, 1 conclusions
    Solutions on providing application layer caller information to callee, configuration of application layer caller information on MMTel Enabler server, MMTel Enabler layer adaptation to CAPIF, Data channel application related capability exposure
RAN and other impacts and dependencies:
  solution on data channel application related capability exposure and some objectives of normative work depended on Reply LS from SA2
UID | Name | Acronym | Target month/year | Old % | WID | New %
1000034 | Study on Service aspects for supporting the eMMTel service | FS_eMMTelAPP | Sep-2024 | 70% | SP-230779 | 80%
Contentious Issues:
  None
Next steps:
  Update architecture requirements
  Solution for 1 Key Issues
  New/Updated solution evaluations based on Reply LS from SA2
  New/Updated conclusions based on Reply LS from SA2

## Slide 15: FS_AIMLAPP
Progress since SA#103:
  SA6#62 Adhoc-e: 8 pCRs approved
  SA6#62: -
  Progress made for:
    Remaining EN resolutions and updates to Overall Evaluation and Conclusions for Solution #31
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1010005 | Study on application layer support for AI/ML services | FS_AIMLAPP | Sep-2024 | 95% | SP-231182 | 100%
Contentious Issues:
  None
Next steps:
  None

## Slide 16: FS_Metaverse_App
Progress since SA#104:
  Total 43 pCRs agreed
  Progress made:
    New solutions were discussed
    Solution evaluations for all key issues are completed
    Overall evaluation and conclusions for all key issues (except one) are completed
    Study is marked as complete
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1020052 | Study on application enablement for Localized Mobile Metaverse Services | FS_MetaverseApp | Sep-2024 | 70% | SP-231806 | 100%
Contentious Issues:
  None
Next steps :
  To bring all conclusions to the normative work
  Continue discussion on
    Possible enhancements to the EDGEAPP to support metaverse services
    Asset permission management architecture and procedures

## Slide 17: FS_XRApp
Progress since SA#104:
  SA6#62-ad hoc-e: 16 pCRs agreed
  SA6#62: 12 pCRs agreed, TR sent for approval
  Progress made for
    The Architectural requirements and Application enablement architectureare updated and concluded;
    Solution updated to support the tethered devices, to utilize the RTP/RTCP, to utilize UE IP address information;
    New solution to enhance XR EAS selection based on N6 delay measurement, to make coordination between direct and indirect connection, to utilize application enablement layer capabilities;
    Overall solution evaluation for all KIs.
    Conslusion for KI#1, KI#2, KI#3, KI#4, KI#5, KI#7, KI#8.
UID | Name | Acronym | Target month/year | Old % | WID | New %
1020051 | Study on Application enabler for XR Services | FS_XRApp | Sep-2024 | 65% | S6-233295 | 90%
RAN and other impacts and dependencies:
  Solutions for Key issue about the XR application server selection enhancement has dependency on the SA2 working progress.
Contentious Issues:
  None
Next steps:
  Conclusion on KI#6
  Normative work
Notes: 1.The Architectural requirements are updated.
2.Application enablement architecture has been updated and concluded.
3.Solution updated:
a.Sol#4 updated to support the tethered devices;
b.Sol#6 updated to utilize the RTP/RTCP;
c.Sol#11 updated to support the tethered devices;
d.Sol#12 updated to utilize UE IP address information.
4.New solution to enhance XR EAS selection based on N6 delay measurement, new solutions to make coordination between direct and indirect connection, new solutions to utilize application enablement layer capabilities.
5.Architecture evaluation.
6.Overall solution evaluation for KI#1, KI#2, KI#3, KI#4, KI#5, KI#6, KI#7, KI#8.
7.Conclusions for KI#1, KI#2, KI#3, KI#4, KI#5, KI#7, KI#8.

## Slide 18: FS_5GSAT_Ph3_App
Progress since SA#104:
  43 pCRs approved, TR sent for approval
  Progress made for:
    Abbreviations, Architecture Requirements, Architecture and Deployment options, Business Relationships
    7 solution updates, 1 new KI, 2 new solutions
    Solution evaluation (all 9 solutions), Overall evaluation and Conclusions (all 9 KIs)
RAN and other impacts and dependencies:
  None identified
Contentious Issues:
  None
Next steps:
  Study is completed. Continue normative work
UID | Name | Acronym | Target month/year | Old % | WID | New %
1020053 | Study on application enablement for Satellite access enabled 5G Services | FS_5GSAT_Ph3_App | Sep-2024 | 60% | SP-240296 | 100%

## Slide 19: FS_CAPIF_Ph3
Progress since SA#104:
  SA6#62-ad hoc-e: 12 pCRs approved
  SA6#62: 27 pCRs approved
  Progress made capturing Solutions, evaluations and conclusions mainly for:
    Consent/Purpose Management (10 solutions)
    Enhancement for AEF status and service API status (3 solutions)
    Enhancements of API invoker onboarding (2 solutions)
    Architecture evolution (1 solution)
    Enhanced CAPIF interconnection services (1 solution)
RAN impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1020062 | Study on CAPIF Phase 3 | FS_CAPIF_Ph3 | Sep-2024 | 55% | SP-231741 | 90%
Contentious Issues:
  None
Next steps:
  Continue capturing solutions to existing key issues
  Continue capturing evaluations to existing/new solutions
  Start normative work

## Slide 20: FS_Generic_IOPS
Progress since SA#104:
    10 pCR’s submitted on key issues and solutions
    Two pCR’s agreed
    Group agreed to not re-discuss previous KI’s in TR 23.778, instead focus on new KI’s, hence only 2 PCR’s agreed.
    Group agreed to on how to progress solution on one KI related to existing work.
    One pCR on satellite impacts was also agreed.
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1040071 | Study on MC services for generic support on IOPS mode of operation | FS_Generic_IOPS | Sep-2024 | 0% | SP-241017 | 40%
Contentious Issues:
  None
Next steps:
  Work on bringing in solutions on how to generalize TS23.180
  Work on 5G satellite solution
  Finish the Overall evaluation and Conclusions for the new approved solutions

## Slide 21: eLSAPP
Progress since SA#104:
  10 pCRs agreed
    1 CR for supporting adaptive location configuration and reporting
    3 CRs for supporting Geofencing and dynamic Geofencing
    1 CR for supporting history location querying
    2 CRs for support of Location-related UE Group Analytics and Collision Detection Analytics based on ADAES
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1040072 | Enhanced application layer support for location services | eLSAPP | Dec-2024 | 0% | SP-241005 | 30%
Contentious Issues:
  None
Next steps:
  Update the existing solutions to capture outstanding Editor’s Notes
  Continue the normative work for remaining solutions approved in the TR

## Slide 22: MMTel_App
Progress since SA#104:
  SA6#62 Adhoc-e: 5 pCRs agreed
  SA6#62: 0 pCRs agreed
  Progress made for skeleton, scope, terms, Abbreviations and Architecture
RAN and other impacts and dependencies:
  procedures on session management related solutions, data channel application related capability exposure etc. depended on Reply LS from SA2
UID | Name | Acronym | Target month/year | Old % | WID | New %
1040073 | Application enablement aspects for MMTel | MMTel_App | Dec-2024 | 0% | SP-241019 | 10%
Contentious Issues:
  None
Next steps:
  procedures on session management related solutions, data channel application related capability exposure etc. based on TR Conclusion and Reply LS from SA2
  Architectural requirements

## Slide 23: AIML_App
Progress since SA#104:
  SA6#62 Adhoc-e: 2 pCRs approved
  SA6#62: 18 pCRs approved (TS 23.482), 2 CRs agreed (TS 23.434, TS 23.436)
  Progress made for:
    Skeleton, Scope, Definitions and Introduction
    Architecture and requirements
    Annexes on deployment/business scenarios and ML model lifecycle
    New features for ADAES for AI/ML Member capability Analytics
    New features for AIMLE including:
      Support for model distribution, model management and ML/FL training
      Support for FL member registration and events notification
      Support Transfer of Intermediate AIML Operation Information
      Support for AIMLE client registration, discovery and selection
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1040075 | Application enablement for AI/ML services | AIML_App | Dec-2024 | 0% | SP-241008 | 40%
Contentious Issues:
  None
Next steps:
  Progress on further AIMLE and ADAES related features based on concluded solutions in TR 23.700-82
  EN resolutions and completion of existing features (including flows and API definitions)

## Slide 24: Metaverse_App
Progress since SA#104:
  WID is revised
    To move support for QoS/Resource coordination to XRM_Ph2_App WID
    To add new TS for digital asset management
  7 pCRs agreed
  Progress made for
    Skeleton of the TS
    Introduction and Scope of the TS
    Spatial anchors service
      Architecture and basic CRUDS procedures along with IE tables and APIs
    Spatial map service
      Architecture and basic CRUDS procedures.
RAN impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1040076 | Application enablement for mobile metaverse services | Metaverse_App | Dec-2024 | 0% | SP-241009 | 25%
Contentious Issues:
  None
Next steps:
  Continue the work on the remaining objectives

## Slide 25: XRM_Ph2_App
Progress since SA#104:
  SA6#62: 3 CRs were agreed, WID revised
  Progress made for
    Support of QoS measurement for Multi-Modal traffic in SEALDD layer
    SEALDD policy configuration for multi-modal flows
    PDU set handling
    EAS instantiation enhancement to satisfy E2E KPI requirements for XR application
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1040074 | Application enablement for XRM Services Phase 2 | XRM_Ph2_App | Dec-2024 | 0% | SP-241007 | 15%
Contentious Issues:
  None
Next steps:
  Continue the work on remaining objectives

## Slide 26: 5GSAT_Ph3_App
Progress since SA#104:
  Normative work kicked-off
  Progress made for:
    1 CR to 3GPP TS 23.558 is Agreed
RAN and other impacts and dependencies:
  None identified
Contentious Issues:
  None
Next steps:
  Continue normative work
UID | Name | Acronym | Target month/year | Old % | WID | New %
1040077 | Application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | Dec-2024 | 0% | SP-241010 | 5%

## Slide 27: 5GMARCH_Ph3
Progress since SA#104:
  SA6#62 Adhoc-e: not in the meeting scope
  SA6#62: 3 CRs agreed
  Progress made for
    New feature on Update to store mechanism
    Updated feature on Application Server in Group messaging and the related APIs
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1000037 | Application Architecture for MSGin5G Service Phase 3 | 5GMARCH_Ph3 | Dec-2024 | 35% | SP-230781 | 50%
Contentious Issues:
  None
Next steps
  provide solutions for solutions for Rel-19 objectives, e.g.
    technical solutions to fulfil the remaining stage 1 requirements [R-5.1.2-001] in TS 22.262
    APIs provided by MSGin5G Client

## Slide 28: FRMCS_Ph5
Progress since SA#104:
  SA6#62: 15 CRs were agreed
  Progress made for
    IP address of target data host or DNS server for IPcon
    Interworking private call
    Interworking ad hoc group call based on criteria
    Interworking ad hoc group call based on list of users
    Ad hoc group call towards a migrated MC service user
    Migration during ad hoc group call procedure
    Various details and corrections
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1000038 | Railways specific Enhancements to Mission Critical Services | FRMCS_Ph5 | Dec-2024 | 55% | SP-230780 | 70%
Contentious Issues:
  None
Next steps:
  Continue the work on remaining objectives

## Slide 29: MCShAC
Progress since SA#104:
  SA6#62 ad-hoc: No contributions as of no MC topics
  SA6#62 contributions finishing WI:
    A.9 ACM client user profile configuration data
    MCShAC cleanup
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1000036 | Sharing administrative configuration between interconnected MC service systems | MCShAC | Dec-2024 | 90% | S6-232194 | 100%
Contentious Issues:
  None
Next steps:
  None

## Slide 30: enhMC
UID | Name | Acronym | Target month/year | Old % | WID | New %
1000039 | Enhanced Mission Critical Architecture | enhMC | Dec-2024 | 60% | SP-230695 | 75%
Progress since SA#104:
  SA6#62: 3 CRs agreed
  Progress made for
    Agreement on MC Logging, Recording & Replay architecture
    5G network congestion information to MCX services
    MCPTT/Ambient enhancements
RAN and other impacts and dependencies:
  None identified
Contentious Issues:
  None
Next steps:
  MCX enhancements according to the remaining objectives, especially:
    Further architecture work related to Logging/recording & discreet listening
    Expand the message storage coverage to also MCPTT and MCVideo services
    Temporary MCX User with Limited Service mode
  Enhancements to the existing procedures or specify new procedures for all MC services to cover the gaps if any identified

## Slide 31: EDGEAPP_Ph3
Progress since SA#104:
  SA6#62: 7 CRs agreed
  Progress made for
    Common EAS discovery, selection, and relocation
    Common EAS bundle discovery and selection
    Resolving editor’s notes
RAN impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1010007 | Architecture for enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | Dec-2024 | 80% | SP-231160 | 85%
Contentious Issues:
  None
Next steps:
  Continue the work on the remaining objectives and remove the editor’s notes

## Slide 32: UASAPP_Ph3
Progress since SA#104:
  SA6#62-adhoc-e - 1 CR agreed
  SA6#62 - 1 CR agreed
  Progress made for:
    Flight route selection support
    Assistance for ground-based UAE layer DAA
RAN impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1010008 | Application Architecture for UAS applications Phase 3 | UASAPP_Ph3 | Dec-2024 | 60% | SP-240741 | 75%
Contentious Issues:
  None
Next steps:
  Continue the work on remaining objectives and resolve Editor’s Notes.

## Slide 33: SEALDD_PH2
Progress since SA#104:
  SA6#62: 3 CRs were agreed
  Progress made for
    Information flow and service API for Seamless SEALDD server relocation
    Corrections
RAN and other impacts and dependencies:
  None identified
UID | Name | Acronym | Target month/year | Old % | WID | New %
1010006 | SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | Dec-2024 | 70% | SP-230989 | 80%
Contentious Issues:
  None
Next steps:
  Further enhancement to the SEALDD according to the objectives

## Slide 34: CAPIF_EXT
UID | Name | Acronym | Target month/year | Old % | WID | New %
1010009 | Guidelines for CAPIF Usage | CAPIF_EXT | Dec-2024 | 80% | SP-231161 | 90%
Progress since SA#104:
  SA6#62: 14 pCRs agreed
  Progress made for
    Overview of CAPIF
    Role of Stakeholders for API Exposure
    Exemplary Use Cases and Adoption
RAN and other impacts and dependencies:
  None identified
Contentious Issues:
  Cooperation with FS_CAPIF_ph3 and CAPIF_ph3
Next steps:
  Work on the following chapters
    Exemplary Use Cases and Adoption

## Slide 35: For TSG SA information and action

## Slide 36: For TSG SA information and action (1/4)
Action: CRs for approval – CR packs:
  SP-241211 Rel-18 CRs to TS23436 for ADAES
  SP-241212 Rel-18 CRs to TS23434, TS23436 for AIML_App
  SP-241213 Rel-18 CRs to TS23222 for CAPIF, TEI18
  SP-241214 Rel-18 CRs to TS23558 for EDGEAPP_Ph2
  SP-241215 Rel-18 CRs to TS23435 for NSCALE
  SP-241216 Rel-18 CRs to TS23433 for SEALDD
  SP-241217 Rel-18 CRs to TS23222 for SNAAPP
  SP-241218 Rel-18 CRs to TS23282 for enh4MCPTT
  SP-241219 Rel-19 CRs to TS23558 for EDGEAPP_Ph3
  SP-241220 Rel-19 CRs to TS23434, TS23436 for eLSAPP
  SP-241221 Rel-19 CRs to TS23554 for 5GMARCH_Ph3
  SP-241222 Rel-19 CRs to 23.558 for 5GSAT_Ph3_App
  SP-241223 Rel-19 CRs to TS23280, TS23289, TS23379 for enhMC
  SP-241224 Rel-19 CRs to TS23280, TS23281, TS23282, TS23283 and TS23379 for FRMCS_Ph5

## Slide 37: For TSG SA information and action (2/4)
Action: CRs for approval – CR packs:
  SP-241225 Rel-19 CRs to 23700-82 for FS_AIMLAPP
  SP-241226 Rel-19 CRs to 23280 for MCShAC
  SP-241227 Rel-19 CRs to TS23433 for SEALDD_Ph2
  SP-241228 Rel-19 CRs to TS23222 for TEI19
  SP-241229 Rel-19 CRs to TS23434 for TEI19, eSEAL, SEAL_Ph3
  SP-241230 Rel-19 CRs to TS23558 for TEI19, EDGEAPP_Ph2
  SP-241231 Rel-19 CRs to TS23255 for UASAPP_Ph3
  SP-241232 Rel-19 CRs to TS23558 for XRM_Ph2_App

## Slide 38: For TSG SA information and action (3/4)
Information: Technical Reports/Specifications
  SP-241201 Presentation of TR 23.700-22 v100 for Information
Action: Technical Reports/Specifications
  SP-241202 Presentation of TR 23.700-01 v200 for Approval
  SP-241070 Presentation of TR 23.700-21 v200 for Approval
  SP-241069 Presentation of TR 23.700-23 v200 for Approval
  SP-241205 Presentation of TR 23.700-72 v200 for Approval

## Slide 39: For TSG SA information and action (4/4)
Action: Revised SIDs/WIDs
  SP-241206 Revised WID on Application enablement architecture for mobile metaverse services
  SP-241207 Revised WID on application enablement for XRM Services Phase 2
Action: New SIDs/WIDs
  SP-241062 New SID for SEAL Phase 4
  SP-241063 New WID on CAPIF Phase 3
  SP-241064 New WID on MC services for generic support on IOPS mode of operation
Potential Action: Endorsed SIDs/WIDs
  None

## Slide 40: Thank You