## Slide 1
Andrew Bennett (SA2 Chair, Samsung)
Maurice Pope (SA2 Support, MCC)
SA2 Status Report to
TSG SA#106

## Slide 2: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 3: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 4: 1) General Aspects (1/7)
SA2 meetings held since SA#105
  SA2#165: 14 – 18 October, Hyderabad, India
  SA2#166: 18 – 22 November, Orlando, USA
Upcoming SA2 meetings (Q1 2025)
  SA2#166 AH-E: 20 - 24 January (e-meeting)
  SA2#167: 17 - 21 February 2025, Athens, Greece

## Slide 5: 1) General Aspects (2/7)
SA2 WG leadership
  Chair: Andrew Bennett (Samsung)
  Vice Chairs: Dario Serafino Tonesi (Qualcomm), Wanqiang Zhang (Huawei)
  Secretary: Maurice Pope (MCC)
Many thanks to Maurice Pope, and Vice Chairs Wanqiang Zhang and Dario Serafino Tonesi, for their outstanding support during this quarter

## Slide 6: 1) General Aspects (3/7)
Statistics at SA WG2 #165 (14 - 18 October 2024, Hyderabad, India):
217 delegates ‘attended’ (checked-in) for SA WG2 #165 122 registered for ‘On-Line’ participation
  1608 documents (including revisions), (451 documents were not handled) including:
    1252 CRs (including revisions)
    58 Incoming LSs, of which 14 were postponed
    23 Outgoing LSs Approved
  41 other documents postponed
Total CRs agreed: 151 (excluding agreed CRs which were revised at SA2#166)
Statistics at SA WG2 #166 (18 - 22 November 2024, Orlando, USA):
358 delegates ‘attended’ (checked-in) for SA WG2 #166 90 registered for ‘On-Line’ participation
  1679 documents (including revisions), (575 documents were not handled) including:
    1179 CRs (including revisions)
    60 Incoming LSs, of which 25 were postponed
    23 Outgoing LSs Approved
  30 other documents postponed
Total CRs agreed: 150
786 people registered on the SA WG2 e-mail reflector on 2 December 2024

## Slide 7: 1) General Aspects (4/7)
Chart: SA WG2 meeting attendance

## Slide 8: 1) General Aspects (6/7) Document Handling / Meeting
Number of Tdocs
Chart: 

## Slide 9: 1) General Aspects (7/7) SA2 Agreed CRs by Release / Meeting
Number of CRs
Chart: 
| REL-14 FREEZE: 116-bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 122e | 123 | REL-15 FREEZE: 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | REL-16 FREEZE: 133 | 134 | 135 | 136 | 136AH | 137-e | 138-e | 139-e | 140-e | 141-e | 142-e | 143-e | 144-e | REL-17 FREEZE: 145-e | 146-e | 147-e | 148-e | 149-e | 150-e | 151-e | 152-e | 153-e | 154 | 154AH-e | 155 | 156-e | 157 | 158 | 159 | 160 | 160AH-e | 161 | 162 | 163 | 164 | 165 | 166
Rel-15 PCR/draftCR | 63 | 126 | 117 | 121 | 171 | 214 | 62 | 287 | 328 | 182 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-15 CR | 19 | 19 | 27 | 27 | 12 | 351 | 201 | 213 | 119 | 159 | 100 | 102 | 78 | 74 | 50 | 40 | 17 | 6 | 10 | 3 | 4 | 6 | 2 | 5 | 6 | 0 | 3 | 2 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-16 PCR/draftCR | 43 | 80 | 170 | 147 | 181 | 171 | 207 | 250 | 88 | 87 | 71 | 103 | 26 | 39 | 30 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-16 CR | 2 | 3 | 66 | 133 | 117 | 233 | 279 | 205 | 260 | 174 | 197 | 248 | 31 | 123 | 79 | 9 | 74 | 8 | 29 | 38 | 0 | 31 | 17 | 1 | 13 | 8 | 2 | 1 | 3 | 1 | 2 | 2 | 3 | 1 | 2 | 0 | 3 | 1 | 0 | 0 | 1 | 0
Rel-17 PCR/draftCR | 48 | 55 | 91 | 0 | 0 | 348 | 407 | 356 | 276 | 158 | 113 | 146 | 144 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-17 CR | 12 | 0 | 0 | 0 | 209 | 135 | 262 | 314 | 189 | 236 | 202 | 107 | 57 | 77 | 45 | 12 | 36 | 4 | 26 | 4 | 24 | 13 | 8 | 4 | 13 | 6 | 0 | 4 | 1 | 0
Rel-18 PCR/draftCR | 245 | 440 | 599 | 535 | 306 | 69 | 57 | 17 | 27 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-18 CR | 0 | 0 | 0 | 0 | 25 | 83 | 240 | 215 | 290 | 272 | 226 | 184 | 198 | 208 | 118 | 75 | 21 | 88 | 41 | 2
Rel-19 PCR/draftCR | 85 | 126 | 35 | 126 | 119 | 36 | 31 | 27 | 37 | 0 | 26 | 29 | 168 | 175 | 228 | 85 | 36 | 9 | 13
Rel-19 CR | 67 | 69 | 23 | 111 | 156 | 44 | 50 | 39 | 36 | 0 | 0 | 0 | 0 | 0 | 6 | 15 | 144 | 108 | 148

## Slide 10: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 11: 2.1) Rel-14 and before Maintenance (1/1)
Work Progress on Corrections
(Category A CRs are not counted)
  R12: none
  R13: none
  R14: none

## Slide 12: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 13: 2.2) Rel-15 and before Maintenance (1/2)
Progress since SA#105 - excluding 5GS_Ph1
(Category A CRs are not counted)
  R15: none

## Slide 14: 2.2) Rel-15 and before Maintenance (2/2)
Progress since SA#105 - 5GS_Ph1
(Category A CRs are not counted)
  R15: none

## Slide 15: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 16: 2.3) Rel-16 Maintenance (1/1)
Progress since SA#105
(Category A CRs are not counted)
  1 CR to TS 23.273 5G_eLCS

## Slide 17: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 18: 2.4) Rel-17 Work Summary
Acronym | Work Item Title | WID# | Progress since last TSG SA meeting
5GSAT_ARCH | Architecture aspects for using satellite access in 5G | SP-200445 | No CRs
eEdge_5GC | Enhancement of support for Edge Computing in 5G Core network | SP-201107 | No CRs
IIoT | Study on enhanced support of Industrial Internet of Things | SP-200973 | No CRs
5G_ProSe | Proximity based Services in 5GS (5G_ProSe) | SP-201132 | No CRs
MUSIM | System enablers for Multi-USIM devices | SP-200978 | No CRs
5MBS | Architectural enhancements for 5G multicast-broadcast services (5MBS) | SP-201106 | No CRs
eNS_Ph2 | Enhancement of Network Slicing Phase 2 | SP-200976 | No CRs
eNA_Ph2 | WID on Enablers for Network Automation for 5G - phase 2 | SP-201133 | 1 CR to TS 23.288 (Rel-19)
eNPN | Enhanced support of Non-Public Networks | SP-200980 | No CRs
ID_UAS | Support of Unmanned Aerial Systems Connectivity, Identification, and Tracking | SP-200979 | No CRs
eV2XARC_Ph2 | Architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | SP-210090 | No CRs
ATSSS_Ph2 | Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 2 | SP-200977 | No CRs
5G_AIS | 5G System Enhancement for Advanced Interactive Services | SP-190564 | No CRs
5G_eLCS _Ph2 | Enhancement to the 5GC LoCation Services-Phase 2 | SP-200082 | No CRs
MPS2 | Multimedia Priority Service (MPS) Phase 2 | SP-200519 | No CRs
MINT | Minimization of Service Interruption | SP-210582 | No CRs
ARCH_NR_REDCAP | Architecture Enhancement for NR Reduced Capability Devices | SP-211100 | No CRs
IoT_SAT_ARCH_EPS | Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS | SP-211306 | 1 CR to TS 23.401 (Rel-18)
NR_QoE_enh-Core | [RAN3] Core part: Enhancement on NR QoE management and optimizations for diverse services | RP-223488 | No CRs

## Slide 19: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 20: 2.5) Rel-18 Study/Work (1/5)
Acronym | Work Item Title | WID# | Remarks
5GSATB | 5G System with Satellite Backhaul | SP-230111 | No CRs
5GSAT_Ph2 | Satellite access, Phase2 | SP-230109 | 1 CR to TS 23.401
PIN | Personal IoT Networks | SP-221343 | 1 CR to TS 23.501
UAS_Ph2 | Phase 2 of UAS, UAV and UAM | SP-230091 | 1 CR to TS 23.401
Ranging_SL | Ranging based services and sidelink positioning | SP-230106 | 1 CR to TS 23.273
5G_eLCS _Ph3 | Enhancement to the 5GC LoCation Services-Phase 3 | SP-230093 | No CRs
5G_ProSe_Ph2 | Proximity-based Services in 5GS Phase 2 | SP-230097 | No CRs
GMEC | Generic group management, exposure and communication enhancements | SP-230101 | No CRs

## Slide 21: 2.5) Rel-18 Study/Work (2/5)
Acronym | Work Item Title | WID# | Remarks
AIMLsys | System Support for AI/ML-based Services | SP-230095 | 1 CR to TS 23.502
5MBS_Ph2 | Architectural enhancements for 5G multicast-broadcast services Phase 2 | SP-230099 | 1 CR to TS 23.247 (Rel-19)
eNS_Ph3 | Network Slicing Phase3 | SP-230104 | 1 CR to TS 23.502
XRM | XR (Extended Reality) and media services | SP-230092 | 3 CRs to TS 23.503
NR_REDCAP_Ph2 | 5GS support of NR RedCap UE with long eDRX for RRC_INACTIVE State | SP-230171 | No CRs
NG_RTC | System architecture for next generation real time communication services | SP-230098 | 1 CR to TS 23.228
ATSSS_Ph3 | Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 | SP-221334 | No CRs

## Slide 22: 2.5) Rel-18 Study/Work (3/5)
Acronym | Work Item Title | WID# | Remarks
UPEAS | UPF enhancement for Exposure And SBA | SP-230103 | 2 CRs to TS 23.502
EDGE_Ph2 | Edge Computing Phase 2 | SP-230112 | 2 CRs to TS 23.548
TRS_URLLC | 5G Timing Resiliency and TSC & URLLC enhancements | SP-230107 | No CRs
VMR | Architecture Enhancements for Vehicle Mounted Relays | SP-230105 | 1 CR to TS 23.501
5WWC_Ph2 | Support for 5WWC, Phase 2 | SP-230367 | No CRs
MPS_WLAN | MPS when access to EPC/5GC is WLAN | SP-230108 | No CRs
AMP | 5G AM Policy | SP-221335 | No CRs
eNA_Ph3 | Enablers for Network Automation for 5G - phase 3 | SP-230110 | 1 CR to TS 23.501, 9 CRs to TS 23.288

## Slide 23: 2.5) Rel-18 Study/Work (4/5)
Acronym | Work Item Title | WID# | Remarks
eNPN_Ph2 | Enhanced support of Non-Public Networks | SP-230096 | 1 CR to TS 23.503 (Rel-19)
eUEPO | Enhancement of 5G UE Policy | SP-230094 | 1 CR to TS 23.501, 1 CR to TS 23.503
SFC | System Enabler for Service Function Chaining | SP-230120 | No CRs
DetNet | 5GS DetNet interworking | SP-230172 | No CRs
SUECR | Seamless UE context recovery | SP-220810 | No CRs

## Slide 24: 2.5) Rel-18 Study/Work (5/5)
Acronym | Work Item Title | WID# | Remarks
TEI18_SDNAEPC | Secondary DN authentication and authorization in EPS IWK case | SP-220798 | No CRs
TEI18_MLR | Multiple location report for MT-LR Immediate Location Request for the regulatory service | SP-220795 | No CRs
TEI18_MBS4V2X | MBS support for V2X services | SP-220793 | No CRs
TEI18_SLAMUP | Spending Limits for AM and UE Policies in the 5GC | SP-220794 | No CRs
TEI18_ADEE | Enhancement of Application Detection Event Exposure | SP-220796 | No CRs
TEI18_IPv6PD | General Support of IPv6 Prefix Delegation | SP-220797 | No CRs
TEI18_DCAMP_Ph2 | Dynamically Changing AM Policies in the 5GC Phase 2 | SP-230102 | No CRs
eNSAC | Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection | SP-230113 | 1 CR on TS 23.502
TEI18 mini WIDs

## Slide 25: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 26: SA WG2 progress -Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 06/06/2024 | 100% | SP-231391 | 100% | 
1050112 | (WA) Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 0% | SP-241388 | 70% | 
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 12/12/2024 | 15% | SP-240991 | 85% | 
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 06/06/2024 | 100% | SP-231800 | 100% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | 12/12/2024 | 80% | SP-240969 | 90% | 
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 06/06/2024 | 100% | SP-231199 | 100% | 
1040027 | Integration of satellite components in the 5G architecture Phase III | 5GSAT_Ph3_ARCH | 12/12/2024 | 15% | SP-240986 | 65% | 
1010032 | Study on Extended Reality and Media service (XRM) Phase 2 | FS_XRM_Ph2 | 09/09/2024 | 100% | SP-231671 | 100% | 
1040032 | Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | 12/12/2024 | 5% | SP-240990 | 65% | 
1040035 | UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 12/12/2024 | 65% | SP-240995 | 100% | 
1020003 | Study on UPF enhancement for Exposure And SBA Phase 2 | FS_UPEAS_Ph2 | 06/06/2024 | 100% | SP-231795 | 100% | 
1040036 | Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 12/12/2024 | 30% | SP-240996 | 97% | 
1020004 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | FS_eEDGE_5GC_Ph3 | 09/09/2024 | 100% | SP-240962 | 100% | 
Updates in RED

## Slide 27: SA WG2 progress -Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040034 | Multi-Access (ATSSS_Ph4) | MASSS | 12/12/2024 | 50% | SP-240994 | 100% | 
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 09/09/2024 | 100% | SP-240467 | 100% | 
1040026 | System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 12/12/2024 | 10% | SP-240985 | 70% | 
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 09/09/2024 | 95% | SP-231196 | 100% | 
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 65% | SP-240997 | 99% | 
1020002 | Study on System aspects of 5G NR Femto | FS_5G_Femto | 09/09/2024 | 100% | SP-231797 | 100% | 
1040028 | System aspects of 5G NR Femto | 5G_Femto | 12/12/2024 | 30% | SP-240629 | 100% | 
1020066 | Study on Proximity-based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3 | 09/09/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 12/12/2024 | 70% | SP-240988 | 100% | 
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 09/09/2024 | 95% | SP-240493 | 100% | 
1040031 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 12/12/2024 | 40% | SP-240989 | 100% | 
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 09/09/2024 | 93% | SP-231804 | 100% | 
1040085 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 12/12/2024 | 15% | SP-240971 | 90% | 
1040029 | (stage 2 of) MPS for IMS Messaging and SMS services | MPS4msg | 12/12/2024 | 80% | SP-240987 | 100% | 
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 06/06/2024 | 100% | SP-231197 | 100% | 
Updates in RED

## Slide 28: SA WG2 progress – (TEI19)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1030010 | On-demand broadcast of GNSS assistance data | TEI19_OBGAD | 12/12/2024 | 100% | SP-240487 | 100% | 
1040078 | Stage 2 of Minimize the Number of Policy Associations | TEI19_MINPA | 03/03/2025 | 100% | SP-240118 | 100% | 
1030014 | Spending Limits for UE Policies in Roaming scenario | TEI19_SLUPiR | 06/06/2024 | 100% | SP-240486 | 100% | 
1040079 | Stage 2 of Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | 12/12/2024 | 100% | SP-240121 | 100% | 
1030017 | Multiple Location Procedure for Emergency LCS Routing | TEI19_MLR4RTR | 12/12/2024 | 0% | SP-240123 | 100% | 1 CR to TS 23.273
1030018 | Roaming traffic offloading via session breakout in HPLMN | TEI19_HSBO | 12/12/2024 | 0% | SP-240491 | 100% | 1 CR to TS 23.501
1030019 | Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports | TEI19_DLPMR | 12/12/2024 | 0% | SP-240125 | 100% | 1 CR to TS 23.273
1030011 | (Stage 2 of) Indirect Network Sharing | TEI19_NetShare | 06/06/2024 | 100% | SP-240488 | 100% | 1 maintenance CR to TS 23.501
1030013 | Architecture support of roaming value-added services | TEI19_RVAS | 06/06/2024 | 100% | SP-240119 | 100% | 
1030016 | ProSe support in NPN | TEI19_ProSe_NPN | 06/06/2024 | 100% | SP-240122 | 100% | 
1030020 | QoS monitoring enhancement | TEI19_QME | 06/06/2024 | 100% | SP-240961 | 100% | 1 maintenance CR
1030021 | Subscription control for reference time distribution in EPS | TEI19_TIME_SUB_EPS | 12/12/2024 | 100% | SP-240127 | 100% | 
1040080 | Stage 2 of Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | 12/12/2024 | 0% | SP-240128 | 100% | 1 CR to TS 23.501, 1 CR to TS 23.502
1030023 | NF discovery and selection by target PLMN | TEI19_NFsel_by_tPLMN | 06/06/2024 | 100% | SP-240490 | 100% | 
Updates in RED

## Slide 29: FS_5GSAT_Ph3_ARCH/5GSAT_Ph3_ARCH
Progress since SA#105
  8 CRs and 2 LS out are approved in SA2#165.
  4 CRs (including 2 revisions approved in SA2#165) and 2 LS out are approved in SA2#166.
  KI#1 (Regenerative-based satellite access): 1 CR on support of regenerative based satellite access in 5GS, 2 LS Out to reply LS from RAN3.
  KI#2 (S&F): 1 CR for common functional description, 1 CR for procedure, 1 CR for split MME option, 1 CR for full EPC option, 1 CR for event exposure, and 1 LS Out to reply LS In from SA3.
  KI#3 (UE-satellite-UE): 4 CRs to support UE-satellite-UE communication activation with IMS-AGW onboard satellite, and 1 LS Out to reply LS from SA3-LI.
  RAN impacts and dependencies
  Yes, KI#1 depends on RAN3 conclusion, and KI#2 has RAN impact (on SIB information and transitioning between S&F mode and normal mode)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040027 | Integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 12/12/2024 | 15 | SP-240986 | 65 | In progress
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 21/06/2024 | 100 | SP-231199 | 100 | Complete

## Slide 30: FS_5GSAT_Ph3_ARCH/5GSAT_Ph3_ARCH
Contentious issues
  KI#2: how to support “S&F Monitoring List” and “List of satellite ID(s)”.
  KI#3: how to support procedures for change of the on-board IMS-AGW.
Next steps
  If the exception is granted from SA plenary, continue the normative work as indicated in the exception sheet, including:
    KI#1: Alignment to RAN conclusion on support of regenerative-based satellite access
    KI#2: Addressing unsolved issues:
        Support of the “List of satellite ID(s)” and “S&F Monitoring List” features
        UE behavior while transitioning between S&F mode and non-S&F mode
        Whether and how to support Attach with PDN connection and UE-initiated PDN connectivity request procedure in the example deployment model of split MME.
    KI#3: Support of UE-satellite-UE communication with IMS-AGW onboard satellite:
        Mobility support if the serving satellite changes;
        Allocation of AGW on satellite after early media stop during the call setup

## Slide 31: FS_NG_RTC_Ph2/NG_RTC_Ph2
General
  In SA2 #165/166 meetings 84 contributions were submitted and 45 contributions were handled with 26 CRs agreed
  Achievements:
    Controvarsial issues of KI#1, KI#2, KI#4 and KI#6 were solved with SoH and offline discussions
    Archiectures and basic procedures of all KIs were discussed and agreed
    TR 23.700-77 was sent for approval after EN in KI#6 was removed
  An exception sheet to extend the completion time to March 2025 was sent to SA#106, with no controversial issue
    WT8
      Usage of URL of DC AS for downloading the avatar ID list
      How the MF interacts with BAR for direclty downloading avatar representation
      Whether and how to download Avatar representation via bootstrap DC
    WT7:
      Whether and how the originating network handles the scenario of standalone IMS DC session when the terminating network rejects the session due to not supporting DC multiplexing
      Updates on services of IMS AS and MF
    WT5
      How IMS AS reports PS data off status to DCSF
    WT2
      Detailed call flows for the IMS AS behavior when updating and deleting an IMS session
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 12/12/2024 | 95% | SP-231196 | 100% | Completion target chenges to December 2024 to remove the remaining EN in KI#6
1040026 | System architecture for next generation real time communication services phase 2 | NG_RTC_Ph2 | 12/12/2024 | 10% | SP-240985 | 70% | An exception is to sent to SA#106 to request an extension of completion

## Slide 32: FS_NG_RTC_Ph2/NG_RTC_Ph2
  Controversial issues
    Remaining issues as listed in exception sheet
  RAN impacts and dependencies:
  None
Next steps:
  If the exception is granted from SA plenary, continue normative work and complete all remaining issues for all KIs

## Slide 33: FS_XRM_Ph2/XRM_Ph2
  Progress since SA#105:
  Normative work at SA2#165 and SA2#166
  SA2#165: 17 CRs are approved (KI#3: 1 CR, KI#5: 3 CRs, KI#6: 4 CRs, KI#7: 4 CRs, KI#2: 4 CRs, KI#4: 1 CR) and 4 LS OUT
  SA2#166: 10 CRs (revisions of approved/submitted CRs in SA2#165) (KI#1: 1 CR, KI#2: 4 CRs, KI#4: 1 CR, KI#5: 3 CRs, KI#6: 1 CR) and 1 LS OUT
  KI#6, KI#7 completed
  Impacts and dependencies on other WGs:
  Inter TSG: RAN2/3 (KI#1, KI#9)
  Controversial issues:
  Support differentiated QoS for encrypted multiplexed traffic
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010032 | Study on Extended Reality and Media service (XRM) Phase 2 | FS_XRM_Ph2 | 09/09/2024 | 100% | SP-231671 | 100% | 
1040032 | Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | 12/12/2024 | 5% | SP-240990 | 65% | 

## Slide 34: FS_XRM_Ph2/XRM_Ph2
  Issues that require more work
  PDU Set Information marking in case of no DL PDU Set QoS
  AL-FEC awareness at NG-RAN
  AQP with PDU Set QoS
  PDU Set QoS information for DSCP marking
  Exposure of available data rate
  Exposure of rate limitation
  Expedited Data Transfer
  TS 23.502, TS 23.503 CRs
  Next steps:
  If an exception sheet is approved at SA#106, work on the items approved in the exception sheet
  If an exception sheet is not approved at SA#106, then the percentage completion shall be changed to 100% and continue with maintenance

## Slide 35: FS_EnergySys
  Progress since SA#105
  The normative work started and is progressing
  147 Tdocs were submitted for SA2#165 and #166 (56 CRs are handled, 13 CRs are agreed)
  KI#1: 8 CRs agreed, a new NF (EIF) for energy info collection and its services are defined
  KI#2: 4 CRs agreed for Energy Saving indicator in UE Subscription Data, and BDT policy negotiation
  KI#3: 1 CR agreed for UP path adjustment
  Impacts and dependencies on other WGs
  An LS to RAN WG2 and RAN WG3 is sent to request feedback on the Energy Saving Indicator that may be provided from AMF to NG-RAN to assist energy saving at RAN
  Contentious issues
  None
  Next steps:
  Continue CR discussion
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 0% | SP-241388 | 70% | Normative work in progress
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 99% | SP-231192 | 100% | Study has been completed

## Slide 36: FS_MPS4msg/MPS4msg
Progress since SA#105:
  Continued normative phase.
  10 CRs submitted: 9 agreed, 1 merged.
  Normative work is 100% complete
Impacts and dependencies on other WGs:
  None
Controversial issues:
  None
Next steps:
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040029 | MPS for IMS Messaging and SMS services | MPS4msg | 12/12/2024 | 80% | SP-240987 | 100% | Normative work is complete
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 06/06/2024 | 100% | SP-231197 | 100% | 

## Slide 37: FS_VMR_Ph2/VMR_Ph2
Progress since SA#105:
  15 CRs to TS 23.501, TS 23.502 and TS 23.273 were agreed.
  Aspects agreed: NAT for BH PDU sessions; Additional ULI support; Emergency service support; QoS Handling Authorization of MWAB; UE access to MWAB; network slicing for UEs served by a MWAB; Backhaul PDU Session handling for MWAB; Impact of MWAB mobility; UE mobility served by MWAB.
Impacts and dependencies on other WGs:
  Pending response to LS (S2-2407345) sent to RAN3 and cc RAN2, with specific questions on access control and Additional ULI format.
  OAM support is expected to be handled by SA5, and security to be handled by SA3
Next steps:
  Alignment considering responses from RAN WGs on LS (S2-2407345), e.g. "Additional ULI" handling, etc.
  Other Alignment based on work progressed in other working groups
  Maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 09/09/2024 | 100% | SP-240493 | 100% | Agreed in SA#105 to mark 100%
1040031 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 12/12/2024 | 40% | SP-240989 | 100% | 

## Slide 38: FS_5G_ProSe_Ph3/5G_ProSe_Ph3
  Progress since SA#105
  Agreed 12 CRs to TS 23.304.
  All work tasks in the WID were captured in TS 23.304
  Support for Multi-hop ProSe discovery and selection, communication, QoS and relay re-selection for Layer 3 UE-to-UE and UE-to-Network relay.
  One reply LS sent to CT1 to clarify the relationship between single-hop and multi-hop capabilities and policies, and IP address allocation in U2N relay.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
Outstanding issues
  None.
Next steps
  Start maintenance work.
  Alignment with RAN for Layer 2 UE-to-Network Relay
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3 | 09/09/2024 | 100% | SP-231798 | 100% | 
1040030 | Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 12/12/2024 | 70% | SP-240988 | 100% | Completed

## Slide 39: FS_UIA_ARC/UIA_ARC
FS_UIA_ARC Progress since SA #105
  Based on the guidance that SA Plenary endorsed in SP-241401, 1 p-CR was approved which concludes that no normative work will take place in Rel-19 for Key Issues 1, 2, and 3 and TR 23.700-32 was sent to SA for approval.
UIA_ARC Progress since SA #105
  48 documents were submitted to SA2 #165. 11 were handled, 8 were Approved, and 3 were postponed. 53 documents were submitted to SA2 #166. 15 were handled, 4 were Approved, 1 was postponed, 10 were noted. In sumary 9 CRs were approved: 1 TS 23.316 CR, 3 TS 23.501 CRs, 3 TS 23.502 CRs, and 2 TS 23.503 CRs.
Impacts and dependencies on other WGs: none identified
  None identified
Contentious Issues
  DHCPv6 Solution – A solution using DHCPv6 to associate the Non-3GPP Device Identifier with a User Plane Address.
  Optional Restriction - The optional restriction within the 5GS on max number of simultaneously active Device Identifiers per UE/5G-RG.
  Differentiation Between PDU Sessions – How to indicate, in a NAS-SM message, that the PDU Session is associated with a device identifier when the PDU Session is used by just one device.
  Triggering the Request - no approved text that discusses the case whether and how the UE/5G-RG and/or AF triggers the UE/5G-RG to request for change of QoS Flows. The default assumption would be that this is implementation based.
  An exception sheet was discussed at SA2 #166 for the Contentious issues listed above, but no consensus on the content of the exception sheet was reached in SA2. Whether an exception is approved does not impact the content of the approved CRs.
Next Steps
  The work is complete unless an exception sheet is approved by SA Plenary (i.e. based on a company contribution).
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 09/09/2024 | 93% | SP-231804 | 100% | 
1040085 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 12/12/2024 | 15% | SP-240971 | 90% | If no exception is approved at plenary, the percent complete can be changed to 100%

## Slide 40: FS_eEDGE_5GC_ph3/ eEDGE_5GC_ph3
Progress since SA#105
  eEDGE_5GC_Ph3:
    96 papers were received, 30 CRs were approved.
  Impacts and dependencies on other WGs:
  None.
Controversial issues:
  KI#1: AF traffic influence information usage at I-SMF.
Next steps:
  Resolve the remaining ENs via CAT-F CRs and process other CAT-F CRs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040036 | Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 12/12/2024 | 30% | SP-240996 | 97% | 
1020004 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | FS_eEDGE_5GC_Ph3 | 09/09/2024 | 100% | SP-240962 | 100% | 

## Slide 41: FS_UAS_Ph3/UAS_Ph3
Progress since SA#105
  12 CRs to TS 23.256, 1 CR to TS 23.502 and 2 CRs to TS 23.288 were agreed.
  All work tasks in the WID were captured mainly in TS 23.256.
    WT#1: NEF services enhancements
      Pre-flight planning and in-flight monitoring for UAV UEs; C2 communication reliability; Changeover from one USS to another USS for UAV UE assisted by 5GC; ※ Security spec reference added
    WT#2: Network-assisted/ground-based mechanism for DAA (Detect And Avoid)
    WT#3: Support no-transmit zones for UAV UEs
  One LS on Clarification of Nnef_RetrieveInfoUAVFlight_Get service operation sent to CT3.
  One Reply LS on UAV regulation sent to RAN3
  Impacts and dependencies on other WGs
  CT3: Using Nnef_RetrieveInfoUAVFlight_Get in the procedure for USS changeover during a UAV flight
  RAN2/3: Procedures for altitude reporting for aerial UEs
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 65% | SP-240997 | 99% | 

## Slide 42: FS_UPEAS_Ph2/UPEAS_Ph2
Progress since SA#105:
  Continue normative work at SA2#165 and SA2#166
  10 CRs are approved at SA2#165, among of them 5 CR are further revised at SA2#166, and 2 new CR approved in SA2#166.
  All key issues were completed
Impacts and dependencies on other WGs:
  None
Controversial issues:
  None
Next steps:
  maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020003 | Study on UPF enhancement for Exposure And SBA Phase 2 | FS_UPEAS_Ph2 | 06/06/2024 | 100% | SP-231795 | 100% | 
1040035 | UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 12/12/2024 | 65% | SP-240995 | 100% | 

## Slide 43: FS_5G_Femto/5G_Femto
  Progress since SA#105
  A total of 11 CRs (including revisions of two approved CRs in SA2#165) were agreed on the following aspects:
  LS from SA WG3 – “LS to request clarification on the potential baseline system architecture of 5G NR Femto”.
    Reply LS to request clarification on the potential baseline system architecture of 5G NR Femto (S2-2412752) was agreed.
  LS from SA WG3 – “LS on Clarification regarding definition of 5G NR femto ownership”
    Reply LS on Clarification regarding definition of 5G NR femto ownership (S2-2411241) was agreed.
  RAN impacts and dependencies
  None.
Outstanding issues
  None.
Next steps
  Maintenance work and alignment based on work progressed in other working groups
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020002 | Study on System aspects of 5G NR Femto | FS_5G_Femto | 09/09/2024 | 100% | SP-231797 | 100% | 
1040028 | System aspects of 5G NR Femto | 5G_Femto | 12/12/2024 | 30% | SP-240629 | 100% | 

## Slide 44: FS_MASSS/MASSS
  Progress since SA#105
  FS_MASSS: Based on the guidance that SA Plenary endorsed in SP-241401, 1 pCR was approved which updates “interim conclusion” to final “conclusion” for KI#2.2
  MASSS: Focus was on normative work for KI#2.1. 40 Tdocs were submitted and 7 CRs were approved for TS 23.501/502/503
  RAN impacts and dependencies
  None
Contentious issues:
  None
Next steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040034 | Multi-Access (ATSSS_Ph4) | MASSS | 12/12/2024 | 50% | SP-240994 | 100% | 
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 09/09/2024 | 100% | SP-240467 | 100% | 

## Slide 45: FS_AmbientIoT
Progress since SA#105
  TR cover sheet (including TR 23.700-13 1.2.0) sent to TSG SA for information
  19 pCRs are approved and documented in TR conclusions
  Rel-19 Ambient IoT architecture are concluded that 2 options for Topology 1 (i.e. Direct interface option and Indirect interface option) and 2 options for Topology 2 (i.e. UP option and RRC indirect option)
  Other WG impacts and dependencies
  RAN and SA3 dependencies are listed in the TR cover sheet.
Outstanding issues
  Editor’s notes are captured in TR conclusion, which need further work by SA2 or coordination with other WG, details see TR cover sheet
Next steps
  Decide the R19 next phase work together with RAN, in SA#106
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | 12/12/2024 | 80% | SP-240969 | 90% | 

## Slide 46: FS_AIML_CN/AIML_CN
General
  308 papers(including discussion papers) were submitted, 22 CRs were agreed, 2 LS out were agreed, 2 LS reply were agreed.
  KI#1: 10 CRs are agreed, 2 LS out were agreed
  KI#2: 8 CRs are agreed
  KI#3: the CR for Support of QoS and policy assistance analytics is agreed
  KI#4: 3 CR is agreed
  Impacts and dependence with other WGs :
  Impact on RAN: For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
  Impact SA3: consent/privacy aspects, in coordination with SA3
Controversial issues
  NONE
Next Steps
  Continue normative work in 2025 Q1 (with exception sheet)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 12/12/2024 | 15% | SP-240991 | 85% | 
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 06/06/2024 | 100% | SP-231800 | 100% | 

## Slide 47: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 48: 2.7) IETF and External SDO Normative Reference Update
None

## Slide 49: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 50: 3) SA2 Work Planning
Summary of status of Rel-19 work and study items (excluding TEI19)
 | Study status | Work Item status | Comment
FS_5GSAT_ARCH_Ph3 5GSAT_ARCH_Ph3 | 100 | 65 | Exception sheet not agreed by SA2
FS_NG_RTC_Ph2 NG_RTC_Ph2 | 100 | 70 | Exception sheet agreed by SA2
FS_XRM Ph2 XRM Ph2 | 100 | 65 | Exception sheet agreed by SA2
FS_EnergySys | 100 | 70 | Exception sheet not agreed by SA2
FS_MPS4msg MPS4msg | 100 | 100 | 
FS_VMR_Ph2 VMR_Ph2 | 100 | 100 | 
FS_5G_ProSe_Ph3 5G_ProSe_Ph3 | 100 | 100 | 
FS_UIA_ARC UIA_ARC | 100 | 90 | Exception sheet not agreed by SA2
FS_eEDGE_5GC_ph3 eEDGE_5GC_ph3 | 100 | 97 | 
FS_UAS_Ph3 UAS_Ph3 | 100 | 99 | 
FS_UPEAS_Ph2 UPEAS_Ph2 | 100 | 100 | 
FS_5G_Femto 5G_Femto | 100 | 100 | 
FS_MASSS MASSS | 100 | 100 | 
FS_AmbientIoT | 90 | N/A | Continuation to be discussed in SA
FS_AIML_CN AIML_CN | 100 | 85 | Exception sheet agreed by SA2

## Slide 51: 3) SA2 Work Planning – Exception requests
Six Rel-19 Work Items have been assessed as less that 100% complete and requiring exceptions to complete Cat-B/C work
The exception sheets drafted by the rapporteurs were discussed during SA2#166 and in email approval following that meeting
Guidance was given to only include aspects that had consensus from SA2
  Other aspects discussed but not achieving consensus were not included in the SA2 input to SA, but could be submitted as company contributions to SA
 | Completion rate | SA2 exception sheet agreed?
5GSAT_ARCH_Ph3 | 65% | No
NG_RTC_Ph2 | 70% | Yes
XRM Ph2 | 65% | Yes
EnergySys | 70% | No
UIA_ARC | 90% | No
AIML_CN | 85% | Yes

## Slide 52: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 53: 4) Documents for Information and Approval (1/5)
Revised SID/WID for Approval
TSG SA# | Type | Title | Acronym
SP-241505 | WID REVISED | Revised WID on Enhancement of support for Edge Computing in 5G Core network phase 3 | eEDGE_5GC_Ph3

## Slide 54: 4) Documents for Information and Approval (2/5)
New SID/WID for Approval
TSG SA# | Type | Title | Acronym
SP-241498 | WID NEW | New WID on MSISDN verification operation support to Nnef_UEId Service | TEI19_MVOSNS
SP-241500 | WID NEW | New WID on ATSSS Rule Provisioning via 3GPP access connected to EPC | TEI19_ ARP3E
SP-241502 | WID NEW | New WID on Network Controlled Network Slice Selection | TEI19_SliceSel
SP-241504 | WID NEW | New WID on PRU Usage Extension supported by Core Network | TEI19_PRUE

## Slide 55: 4) Documents for Information and Approval (4/5)
TSs/TRs for Approval
TSG SA# | Title | Release | TR/TS | WI Acronym
SP-241507 | Presentation of TR 23.700-32: 'Study on User Identities and Authentication Architecture' to TSG SA#106 for approval | Rel-19 | 23.700-32 | FS_UIA_ARC
SP-241508 | Presentation of TR 23.700-54: 'Study on Multi-Access (DualSteer and ATSSS_Ph4)' to TSG SA for approval | Rel-19 | 23.700-54 | FS_MASSS
SP-241509 | Presentation of TR 23.700-77: 'Study on system architecture for next generation real time communication services; Phase 2' to TSG SA for approval | Rel-19 | 23.700-77 | FS_NG_RTC_Ph2
SP-241510 | Presentation of TR 23.700-84: 'Study on Core Network Enhanced Support for Artificial Intelligence (AI) / Machine Learning (ML)' to TSG SA for approval | Rel-19 | 23.700-84 | FS_AIML_CN

## Slide 56: 4) Documents for Information and Approval (5/5)
TSs/TRs for Information
TSG SA# | Title | Release | TR/TS | WI Code
SP-241506 | Presentation of TR 23.700-13: 'Study on Architecture support of Ambient power-enabled Internet of Things' to TSG SA for Information | Rel-19 | 23.700-13 | FS_AmbientIoT

## Slide 57: Contents
1) General aspects (events since SA#105, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Work and Maintenance
  2.5) Rel-18 Work and Maintenance
  2.6) Rel-19 Work and Maintenance
  2.7) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 58: 5) Collected Items requiring action from SA
Decisions for TRs for information/approval
Approval of new/revised WIDs
  Including WIDs and CRs for TEI19_MVOSNS, TEI19_ ARP3E, TEI19_SliceSel, TEI19_PRUE discussed and approved in this quarter
Decision on exception requests for normative work
  Including discussion of any company-submitted exception requests
Discussion of continuation of the Ambient IoT study

## Slide 59: Thank You !
Andrew Bennett
Chair of 3GPP SA2
a.bennett@Samsung.com
www.3gpp.org