TSG SA Meeting SA#106	SP-241867

10 - 13 December, 2024, Madrid, Spain

# Title:	AIoT way forward

# Source:	Nokia, Deutsche Telekom, T-Mobile USA, Ericsson

# Document for:	Endorsement

Agenda Item:	6.2.2

Introduction

SA#102 approved a study for Ambient IoT in SP-240969 with the understanding that SA2 will only work on the study in 2024, and TSGs will check in December 2024 for further Ambient IoT work taking into account RAN progress.

This contribution provides status for the Ambient IoT work in SA WGs at the time of stage 2 freeze. A reminder of Rel-19 timeline is provided below for convenience.

Status in SA2:

SA2 has been running study for AIoT during the whole 2024, for a total of 12.5 Tus, plus more than 3 TUs of drafting sessions. Initial plan was to do the study in 11.5 TUs.

At end of SA2#166, the SA2 study on Ambient IoT is 90% complete.

Following critical issues still need to reach conclusions in SA2 (this is a sub list of the outstanding issues listed in the TR coversheet as per S2-2413036):

-	Information that can be stored in the AIoT Device subscription-like data (static information) and Information that can be stored in AIoT device context data (dynamic information).

-	The entity to store the static and the dynamic information.

-	AIoT reader selection principles.

-	How to authorize the UE Reader in topology 2.

-	Whether and which additional methods for dynamically provisioning the UE with DNN/S-NSSAI and AIoT NF FQDN can be specified and in which release .

- The length of AIoT device ID is fixed or dynamic and its part2 information are FFS.

- Whether and how AIOTF selects BS readers or AIOT RAN nodes in topology 1.

- How addressing works for UL traffic (i.e. how the BS Reader identifies the appropriate AMF to which to forward UL messages) in the indirect path via AMF.

Although less critical issues, the following areas also need further work in the study in SA2:

-	AIoT data aggregation principles.

-	AMF service enhancement to communicate with AIOTF.

-	NEF exposure service design principle.

-	NF profile for AIOTF.

-	Whether and how to define areas or Reader sets to select Readers.

-	How to provide the necessary information for resource allocation in the UP option of topology 2.

It is our understanding that at least one additional quarter is needed for SA2 to complete the SA2 study for those issues under SA2 remit only, with discussions in January ad hoc, and final conclusions to be reached in February F2F meeting, for roughly 2 TUs. This would then mean a total of 9 meetings and more than 15 TUs to develop the full study for Ambient IoT.Outstanding issues with dependency on RAN WGs or SA3 may be at risk of only completing in Q2 2025 due to WGs meetings in parallel in February 2025.

A work item proposal for Ambient IoT was discussed in SA2, without agreement. Latest version for the work item was showing 9 TUs required. With the number of TUs spent on the study, it is our understanding that 9 TUs is optimistic estimate. Considering allocating 2 TUs per meeting to AIoT normative work would mean that at least 5 meetings are needed to complete AIoT normative work, which would then mean a completion at the earliest in December 2025, which means at ASN.1 and Open APIs freeze. This clearly goes well beyond Rel-19 timeline, not mentioning that CT WGs would then also need to progress their part of the work.

Status in SA3:

SA3 has been studying AIoT since the approval of the study item at SA#103 (March 2024), i.e. SA3 have spent 5 meetings trying to reach consensus until now, and leaves the group with, after SA3#119, 6 Key Issues, 42 solutions and 130 unresolved editors notes.

It should be noted that further key issues were submitted at SA3#119, which were not handled, as conclusions was prioritized by the rapporteur. However, no conclusions could be drawn due to the maturity and non-completed down selection of solutions.

Our assessment of the current state is that the following steps need to be completed before the study can be concluded:

- Inclusion of remaining applicable KI’s.

- Resolution of critical editor’s notes.

- Resolution of dependencies to SA2, SA1.

- Down selection of solutions based on principle directions.

The dependencies to SA2 relates to the architecture for topology 1 and topology 2 wherein the security procedures shall be applied. SA1 to give additional guidance to the use cases for SA3 to evaluate the trust model and the necessity for dedicated protection in the device.

SA3 is not at the conclusion phase and depends on other groups which are also behind schedule, therefore pulling normative security work into release 19 with the given schedule, will lead to security vulnerabilities not only for the AIoT feature but also the 3GPP technology itself.

Proposal:

Considering the status in SA WGs, it is proposed that:

- SA tasks SA2 and SA3 to complete their study in first half of 2025.

- SA recommends SA2 to bring a WID proposal for approval only when study is fully concluded, targeting Rel-20.

- SA informs RAN about such decision to allow for a holistic treatment of the feature, i.e. study in Rel-19 and normative work in Rel-20.