## Slide 1
3GPP Work Plan
Review at Plenary #107
Start-of-meeting version
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to TSG#107 (will be removed if not TSG-approved)
Does not include: - the company-proposed WIDs proposed/approved at TSG#107, revised WID/SID during TSG#106
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2024
SP-250364 (rev of CP-250262; CP-250016 / CP-250011 / SP-250318) 3GPP TSG#107, 12 -14 March 2024, Incheon, South Korea

## Slide 2: Content of this Work Plan review
Snapshot of all ongoing/future Releases
Ongoing Releases
  Rel-19 Timeline and Progress
  Rel-20 Timeline and Progress
  Rel-21 Timeline and Progress
Background information

## Slide 3
Releases 19 to 21 timelines
#108
Release 19
Note: All starting dates are indicative
#110
#112
#114
#116
#118
#120
#122
#124
#126
2025
2026
2028
*: +3 months for RAN4
**: - 3 months for RAN1 & + 3 months for RAN4 perf
#111
#113
#115
#119
#121
#123
#125
2027
2029
5GA Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1
&
Open
APIs
Stage 2
#117
#109
2024
#104
#106
#107
#105
Mar.
#103
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now
SA1 St.1, Content Definition (RAN & SA St.2): completed Dec. 2023
Release 20 5GA
Release 20 FS_6G
5GA Stage 2
5GA RAN Completion**
5GA Stage 3
Chart showing Normative dates
(timeline for 5GA studies not shown)
Chart showing Studies dates
(no 6G normative work in Rel-20)
FS_6G Stage 1
FS_6G RAN P
FS_6G Stage 2
or
FS_6G RAN WG**
FS_6G Stage 3
TBD
Release 21 6G
Rel-21 timeline to be decided no later than June 2026
ITU deadlines for 6G: March 2029 for technology proposal, mid-2030 for specifications
ASN.1

## Slide 4: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 5
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 6: Release 19 progress overview (1/2)
SA1 (Stage 1): completed and stable for some time - 14 Studies, 25 Normative items
SA2, SA6 (Stage 2): completed with 3 exceptions. 24 Studies, 72 Normative items
  Exceptions: Stage 2 for :
    AI/ML (UID 1040033, AIML_CN) (98%)
    NG_RTC_Phase 2 (UID 1040026) (98%)
    NB-IoT (new at SA#107, 30%, targeted for June)
  Reminder: 12 items were still opened at TSG#106

## Slide 7: Release 19 progress overview (2/2)
RAN
  Studies: 11 studies (same at previous TSG), OCI = 76 % (against 74% at previous TSG)
  RAN Core: 54 items (against 50 at previous TSG), OCI = 64 % (against 49% at previous TSG)
    Completion date now Sept. 2025 for all of these 50 items (as per Rel-19 timeline)
  RAN Perf: 36 items (against 32 at previous TSG), OCI = 23 % (against 17% at previous TSG)
    Several of these items already scheduled to be completed by March 2026 (a quarter later than Rel-19 timeline)
SA 3/4/5 & CT
  SA3/4/5:
    Studies: 53 studies (same at previous TSG), OCI = 90 % (against 82 % at previous TSG)
    Normative: 67 items (against 55 at previous TSG), OCI = 43 % (against 30 % at previous TSG)
  CT WG:
    Studies: 4 studies (same at previous TSG), OCI = 85 % (against 80% at previous TSG)
    Normative: 70 items (against 62 at previous TSG), OCI = 55% (against 44% at previous TSG)

## Slide 8: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 9: Release 20: introduction
Rel-20 has 2 components: “Rel-20_5GA” and “Rel-20_6G” (or “Rel-20_FS_6G”)
  Rel-20_5GA covers 5GA studies and normative;
  Rel-20_6G covers 6G studies only (6G normative in Rel-21)
  Up to each TSG/WG how to split their time on each component (e.g. in SA1, it is 50%-50%)

## Slide 10
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
2025
2026
2027
5GA ASN.1 & Open APIs
St.3 SID def. TBD
Release 20 5GA timeline
Note: All starting dates are indicative
Workshops
5GA RAN & SA
RAN WG SID def.
St.2 SID def.

## Slide 11: Release 20 5GA progress overview (1/2)
Stage 1:
  no more new topics to be introduced.
  3 studies, 1 normative, several “miniWIDs”. Items & progress:
Stage 2 & RAN: Workshop at TSG#106 to start identifying the work needed:
  SA: 27 candidate items identified (SP-241972/1989), selection to come later
  RAN: candidate items identified (RP-243292), selection to come later
Stage 3: not started
MiniWIDs
Unique_ID | Name | Acronym | Finish | %Complete
1030042 | Study on satellite access - Phase 4 | FS_5GSAT_Ph4 | 12/12/2024 | 85%
1060071 | Satellite access - Phase 4 | 5GSAT_Ph4-REQ | 03/02/2025 | 60%
1050105 | Indirect Network Sharing on Satellite Access Network | INS_SAT | 09/09/2024 | 100%
1060072 | MPS support in 3GPP system with satellite | MPS_Sat | 12/12/2024 | 100%
1030044 | Study on Energy Efficiency as Service Criteria Phase 2 | FS_EnergyServ_Ph2 | 03/03/2025 | 100%
1070051 | Stage 1 for Energy Efficiency as Service Criteria Phase 2 | EnergyServ_Ph2-REQ | 06/06/2025 | 0%
1030043 | Study on FRMCS Phase 6 | FS_FRMCS_Ph6 | 03/03/2025 | 100%
1070054 | Stage 1 for FRMCS Phase 6 | FRMCS_Ph6-REQ | 06/06/2025 | 0%
1070052 | Stage 1 of SMS to Emergency Centre Phase 2 | SMS2EC_Ph2-REQ | 03/03/2025 | 100%
1070053 | Stage 1 for Ambient listening enhancements including pause and resume in MCS | ALPR-REQ | 06/06/2025 | 100%
1060070 | Vehicle-Mounted Relays Phase3 | VMR_Ph3 | 12/12/2024 | 100%
1050106 | Indirect Network Sharing Phase 2 | NetShare_Ph2 | 09/09/2024 | 100%
1050107 | Resident Phase 2 | Resident_Ph2 | 09/09/2024 | 100%
1050108 | Combined QoS configuration and monitoring | CombQoS | 09/09/2024 | 100%
1050109 | Legacy Residential Gateway Supporting 5G LAN-type Service | LegacyRG_5GLAN | 09/09/2024 | 100%
1050111 | Exposure for Virtual Network information and capability | VNExposure | 09/09/2024 | 100%

## Slide 12: Release 20 5GA progress overview (2/2)
Stage 2 & RAN: Workshop at TSG#106 started identifying the work:
  Also in Rel-20: SA4’s Study on Ultra Low Bitrate Speech Codec (FS_ULBC, UID 1070055)
  Technical work not started
Stage 3: not started
Unique_ID | Name | Acronym | ResourceNames
1070011 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4-ARC | S2
1070025 | Logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | S6
1070024 | Discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | S6
1070026 | Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | S6
1070027 | SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | S6
1070028 | Application enablement aspects for MMTel Phase 2 | FS_MMTel_Ph2-APP | S6
1070029 | Application enablement for AI/ML service Phase 2 | FS_AIML_App_Ph2 | S6
1070030 | Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | S6
1070032 | Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | S6
1070033 | Stage 2 for application enablement for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | S6
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI) / Machine Learning (ML) Phase 2 | FS_AIML_CN_Ph2 | S2
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | S2
1070031 | Stage 2 for Railways specific Enhancements to Mission Critical Services Phase 6 | FRMCS_Ph6-MC | S6

## Slide 13
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
Workshop 6G TSGs
CT & St. 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop SA1 on IMT-2030 use cases
#116
SA1 6G Study(ies)
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 6G SID def. TBD
RAN2/3/4 6G Study(ies)
Release 20 (FS) 6G timeline
or
TBD
Note: All starting dates are indicative
SA3/4/5/6 6G Study(ies)TBD

## Slide 14: Release 20 FS_6G progress overview
Stage 1:
  Study on 6G Use Cases and Service Requirements (FS_6G_REQ, 1050110)
  Expected comletion by 03/03/2026, 25% complete
Other Stages/groups:
  Workshop in March 2025 to start investigating all other Stages (see RP-242437 and SP-241737)
  RAN 6G SID started in RAN chair
  Chairs’ notes Output of the workshop in 6GWS-250243

## Slide 15: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 16: Release 21
Release 21 is the release for submission to IMT-2030*, aka 6G
This implies that 3GPP (normative) work will be submitted to ITU-R before 2030
  ASN.1/OpenAPI freeze date is no earlier than March 2029
Release 21 Freezing dates and other milestones TBD
  Rel-21 timeline is to be decided no later than June 2026
Note that, as usual in 3GPP, previous Generations will in parallel continue to be maintained & enhanced in Rel-21 and after
* source: TSG#103-endorsed CT-240307/SP-240458/RP-240823

## Slide 17: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 18: Background information (1/2): overall background information
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 20; Master version in MS Project; Working versions in Excel
Tutorials on content, maintenance and other info on the Work Plan in subfolder /info
3GPP Releases Descriptions – R99 to Rel-17
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 17: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-18
To be completed at TSG#107

## Slide 19: Background information (2/2): Relationship between WGs, Stages and deadlines
Most 3GPP Working Groups handle only one Stage:
  SA1  Stage 1
  SA2  Stage 2; SA6  Stage 2
  CT WGs  Stage 3 (also Stage 2 for some specific items)
SA3, SA4 and SA5 handle several Stages for some or all their WIDs:
  SA3: handles Stages 2 and 3 for all its WIDs. Stage 2 at SA3 is one quarter after SA2/SA6’s deadline, but this date is an SA3-internal date since there is no dependency (i.e. SA3 is not expecting work from any other WGs)
  SA4: handles Stage 2 for some WIDs (for which SA4 might rely on CT WGs for Stage 3), and Stage 3 for a majority of its WIDs. Stage 2 WIDs in SA4 are clearly identified as such and have the same deadline as SA2/SA6’s date.
  SA5: handles Stages 1, 2 and 3 for all its WIDs. Stage 1 for SA5 is 4 quarters after SA1’s date. Stage 2 for SA5 is 2 quarters after SA2/SA6’s date. Stage 3 for SA5 is same date as CT WGs’ date.
  For SA3, SA4 and SA5, the completion date for all WIDs dealing with Stage 3 (fully or partially) is the same as for CT WGs.
  In this Work Plan review slides, SA3, SA4 and SA5 are reported in the “Stage 3” slides since their overall completion date is aligned with (CT’s) Stage 3. Except for SA4’s Stage 2-only WIDs but this cannot be handled by the present tools.
RAN has a slightly different process. RAN defines two dates:
  The “RAN Content Definition”, which is the same date as SA Stage 1 and SA content definition
  The “RAN Completion”, which is the same date as SA/CT’s Stage 3
  Note that there is no specific RAN-equivalent date for SA/CT’s Stage 2