## Slide 1: SA5 Status Report to SA#83 Charging Management (CH) Operation, Administration, Maintenance & Provisioning (OAM&P)
Thomas TOVINGER, SA5 Chair, Ericsson
Mirko CANO SOVERI, SA5 Secretary, ETSI MCC

## Slide 2: SA5 leadership
SA5
Thomas Tovinger (Ericsson) Chair since 08/2015 Jean-Michel Cornily (Orange) VC since 08/2013 Christian Toche (Huawei) VC since 08/2015
Charging Sub-Working Group (SWG)
Maryse Gardella (Nokia) Chair since 08/2013 Chen Shan (Huawei) VC since 05/2016
OAM&P Sub-Working Group (SWG) Christian Toche (Huawei) Chair since 01/2016

## Slide 3: 2019 meeting calendar
Meeting | Date | City | Country | Host | Co-location
SA5#123 | 21-25 Jan 2019 | Montreal | Canada | NAF3 | 
SA5#124 | 25 Feb – 1 Mar 2019 | Taipei | Taiwan | ChT | 
SA5#125 | 8-12 Apr 2019 | Newport Beach | USA | NAF3 | SA4, SA6
SA5#125 Ad-hoc | 25-28 June 2019 | Sapporo | Japan | JF3 | SA2, SA3
SA5#126 | 19-23 Aug 2019 | Bruges | Belgium | EF3 | 
SA5#127 | 14-18 October 2019 | Sophia Antipolis | France | ETSI | 
SA5#128 | 18-22 Nov 2019 | TBD | China | CF3 | 

## Slide 4: Statistics at SA5 level
 | SA5#119 | SA5#119Ad-Hoc | SA5#120 | SA5#121 | SA5#122 | SA5#123 | SA5#124 | SA5#125
Delegates | 43 | 21 | 39 | 30 | 49 | 44 | 38 | 56
Docs at meeting start | 305 | 144 | 325 | 243 | 259 | 272 | 236 | 278
Docs at meeting end | 597 | 355 | 605 | 469 | 514 | 478 | 437 | 531
Agreed CH CRs | 18 | - | 23 | 43 | 56 | 45 | 40 | 48
Agreed OAM CRs | 65 | - | 11 | 61 | 45 | 55 | 40 | 61
LS in | 10 | 6 | 22 | 21 | 11 | 16 | 6 | 17
LS out | 6 | 5 | 6 | 12 | 8 | 6 | 5 | 2

## Slide 5
 | SA#77 | SA#78 | SA#79 | SA#80 | SA#81 | SA#82 | SA#83 | SA#84
CRs | 24 | 42 | 43 | 120 | 34 | 201 | 180 | 109
TR/TS for information | 4 | 3 | 1 | 10 | 1 | 2 | 1 | 2
TR/TS for approval | 1 | 9 | 4 | 5 | 13 | 2 | 1 | 0
New or updated WIDs | 2 | 17 | 4 | 5 | 16 | 12 | 5 | 2
SA5 exploder | 388 | 393 | 401 | 406 | 402 | 409 | 406 | 403
Statistics at SA level

## Slide 6: Tdoc history

## Slide 7: CR/pCR history

## Slide 8: CR history

## Slide 9: WI history

## Slide 10: Summary of ongoing WIs/SIs (1/3)
WI code | WI Title | Completion rate | Target date
VBCLTE | Volume Based Charging Aspects for VoLTE | 50%->50% | SA#84 (06/2019) -> SA#85 (09/2019)
OFSBI_CH | Nchf Online and Offline Charging Services | 40%->70% | SA#85 (09/2019)
5GIEPC_CH | Charging Enhancement of 5GC interworking with EPC | 30%->60% | SA#85 (09/2019)
5GS_Ph1_NEFCH | Network Exposure Charging in 5G System Architecture | 20%->50% | SA#86 (12/2019)
5GS_Ph1_AMFCH | Charging AMF in 5G System Architecture Phase 1 | 20%->50% | SA#85 (09/2019)
FS_NETSLICE_CH | Study on Charging Aspects of Network Slicing | 30%->45% | SA#85 (09/2019)

## Slide 11: Summary of ongoing WIs/SIs (2/3)
WI code | WI Title | Completion rate | Target date
QOED | Management of QoE measurement collection | 55%->60% | SA#85 (09/2019)
EE_5G | Energy efficiency of 5G | 40%->45% | SA#86 (12/2019)
NETPOL | Network policy management for mobile networks based on NFV scenarios | 10%->10% | SA#85 (09/2019)
METHOGY | Methodology for 5G management specifications | 85%->85% | SA#84 (06/2019) -> SA#85 (09/2019)
IDMS_MN | Intent driven management services for mobile network | 30%->35% | SA#86 (12/2019)
5G_SLICE_ePA | Enhancement of performance assurance for 5G networks including network slicing | 60%->70% | SA#86 (12/2019)
5GDMS | Discovery of management services in 5G | 25%->35% | SA#85 (09/2019)
eNRM | NRM enhancements | 10%->20% | SA#85 (09/2019)

## Slide 12: Summary of ongoing WIs/SIs (3/3)
WI code | WI Title | Completion rate | Target date
TM_SBMA | Trace Management in the context of Services Based Management Architecture | 0->10% | SA#84 (06/2019) -> SA#85 (09/2019)
ONAP3GPP | Integration of ONAP and 3GPP 5G management framework | 0->10% | SA#86 (12/2019)
FS_MAN_EC | Study on management aspects of edge computing | 50%->65% | SA#85 (09/2019)
FS_PROTIMP | Study on protocol enhancement for real time communication | 0->0% | SA#86 (12/2019)
FS_TENANCYC | Study on tenancy concept in 5G network and network slicing management | 26%->40% | SA#85 (09/2019)
FS_CSMAN | Study on management aspects of communication services | 70%->75% | SA#85 (09/2019)
FS_SON_5G | Study on Self-Organizing Networks (SON) for 5G | 40%->50% | SA#86 (12/2019)
FS_OAM_RTT | Study on non-file-based trace reporting | 0->0% | SA#84 (06/2019)
FS_OAM_NPN | Study on non-public networks management | 0%->2% | SA#86 (12/2019)
FS_5GSAT_MO | Study on management and orchestration aspects with integrated satellite components in a 5G network | 0%->10 % | SA#86 (12/2019)

## Slide 13
Charging TSs & TRs
Number | Title | For
- | - | -

## Slide 14
Charging WIDs
Number | Title
SP-190367 | New IMS Charging in 5G System Architecture

## Slide 15
OAM&P TSs & TRs
Number | Title | For
SP-190365 | TR 28.805 - Study on management aspects of communication services | Information
SP-190366 | TR 28.803 - Study on the management aspects of edge computing | Information

## Slide 16
OAM&P WIDs
Number | Title
SP-190369 | Revised WID on energy efficiency of 5G

## Slide 17
Rel-16 CH WIs (1/5)
Work Item | Volume Based Charging Aspects for VoLTE |  | VBCLTE
 |  |  | 810021
Rapporteur | China Mobile | Percentage of completion | 50% -> 50%
Target | SA#84 – June 2019 -> SA#85 September 2019 | Main TSs | TS 32.251, TS 32.260, TS 32.299, TS 32.298
Summary of progress | No input |  | 
Outstanding issues | - |  | 
Documents | - |  | 

## Slide 18
Rel-16 CH WIs (2/5)
Work Item | Nchf Online and Offline Charging Services |  | OFSBI_CH
 |  |  | 820030
Rapporteur | Huawei | Percentage of completion | 40% -> 70%
Target | SA#85 September | Main TSs | TS 32.240, TS 32.255, TS 32.290, TS 32.291, TS 32.298
Summary of progress | CRs were agreed to TS 32.255 on: Fields setting for "Charging Data Request/Response" differentiated between "Converged charging" or "Offline only charging" CHF selection for "offline Only" by the SMF when using NRF. A CR was agreed to TS 32.290 for new API Nchf_OfflineOnlyCharging service. CRs were agreed to stage 3 TS 32.291 Nchf_OfflineOnlyCharging API on: Service Operations description Resources definition Data Model re-using data types from Nchf_ConvergedCharging service API error handling |  | 
Outstanding issues | - |  | 
Documents | Rel-16 CRs |  | 

## Slide 19
Rel-16 CH WIs (3/5)
Work Item | Charging Enhancement of 5GC interworking with EPC |  | 5GIEPC_CH
 |  |  | 820031
Rapporteur | Huawei | Percentage of completion | 30% -> 60%
Target | SA#85 – September 2019 | Main TSs | TS 32.255, TS 32.291, TS 32.298
Summary of progress | CRs were agreed to TS 32.255 on: Description of UE is served by EPC: when 5GS interworking is supported => the PGW-C+SMF with Nchf to CHF when 5GS interworking is NOT supported => the PGW-C+SMF acts as the PGW with Gy/Gz to OCS/OFCS Triggers related to interworking and counts/quota handling for source/target accesses. New Annex "Interworking" to capture the difference for Charging information compared to 5G A CR was agreed to TS 32.291 introducing "handover cancel/start/complete" triggers. |  | 
Outstanding issues | - |  | 
Documents | Rel-16 CRs |  | 

## Slide 20
Rel-16 CH WIs (4/5)
Work Item | Network Exposure Charging in 5G System Architecture |  | 5GS_Ph1_NEFCH
 |  |  | 820033
Rapporteur | Ericsson | Percentage of completion | 20% -> 50%
Target | SA#86 – December 2019 | Main TSs | TS 32.240, TS 32.254, TS 32.290, TS 32.291, TS 32.298
Summary of progress | CRs were agreed to TS 32.254 on: Triggers for NEF charging (API Invocation Request, API Invocation Response, API Notification to AF, Notification Acknowledge), their category (Immediate) and NEF action in IEC and ECUR mode. Charging data Request/Response message content for NEF converged charging. NEF charging information preliminary Information Elements (IEs) definition |  | 
Outstanding issues | - |  | 
Documents | Rel-16 CRs |  | 

## Slide 21
Rel-16 CH WIs (5/5)
Work Item | Charging AMF in 5G System Architecture Phase 1 |  | 5GS_Ph1_AMFCH
 |  |  | 820034
Rapporteur | Nokia | Percentage of completion | 20% -> 50%
Target | SA#85 – September 2019 | Main TSs | TS 32.240, TS 32.290, TS 32.291, TS 32.298, TS 32.297
Summary of progress | pCRs were agreed to TS 32.256 on: Message flows for N2 connection (UE Triggered Service Request and AN release) event based offline charging. Triggers for AMF charging (Registration accept sending from AMF, Deregistration Request, Deregistration Request sending from AMF, N2 request Ack, N2 UE Context Release Complete), their category (Immediate) and AMF action: Charging Data Request [Event]. CDRs generation and CDRs transfer (Bam) Charging data Request/Response message content for 5G connection and mobility charging Connection Mobility Charging Information preliminary Information Elements (IEs) definition |  | 
Outstanding issues | - |  | 
Documents | - |  | 

## Slide 22
Charging SIs (1/1)
Study Item | Study on Charging Aspects of Network Slicing |  | FS_NETSLICE_CH
 |  |  | 820029
Rapporteur | Huawei | Percentage of completion | 30% -> 45%
Target | SA#85 September | Main TR | TR 32.845
Summary of progress | The following were introduced: 3rd solution for "Network Slice Performance based charging" based on CTF in "Management Function", and similar interaction with CHF as SMF The 3 solutions rely on TS 28.550 "Performance assurance" PM services for acquiring the performance data. Aggregation performed by the billing domain for "usage based charging for network slice instance", enabled by network slice instance information in the CDR Solution evaluation for solution #1.4 (Function separate from CHF) |  | 
Outstanding issues | - |  | 
Documents | - |  | 

## Slide 23
Rel-16 OAM&P WIs (1/10)
Work Item | Management of QoE measurement collection |  | QOED
 |  |  | 760058
Rapporteur | Ericsson | Percentage of completion | 55% -> 60%
Target | SA#85 – Sep. 2019 | Main TSs | TS 28.404, 28.405, 28.406, 28.307, 28.308, 28.309
Summary of progress | The structure of 28.405 was changed to specify UMTS and LTE in different clauses, instead of interleaving the RATs for the different actions. Used abbreviations were specified. Management based activation, deactivation and handover handling in LTE were added. |  | 
Outstanding issues | None. |  | 
Documents for approval by SA5 | None. |  | 

## Slide 24
Rel-16 OAM&P WIs (2/10)
Work Item | Energy efficiency of 5G |  | EE_5G
 |  |  | 810023
Rapporteur | Orange | Percentage of completion | 40% -> 45 %
Target | SA#86 – Dec. 2019 | Main TSs | TS 28.310
Summary of progress | A discussion paper (S5-193164) was endorsed, stating that gNBCU/gNBCU-CP/gNBCU-UP power consumption is assumed to be very small compared to gNBDU and that given that, in some cases, the gNBCU/gNBCU-CP/gNBCU-UP may be virtualized, it is proposed that in Rel-16 SA5 only considers the energy consumed in gNBDU(s) (in case of split scenarios) and in non-split gNBs. A new requirement has been added to reflect this agreement. Text from TR 32.972 was imported in TS 28.310 re. EE KPI definition. The WID has been revised to reflect the agreement made in the endorsed discussion paper. |  | 
Outstanding issues | None. |  | 
Documents for approval by SA5 | WID revised |  | 

## Slide 25
Rel-16 OAM&P WIs (3/10)
Work Item | Network policy management for mobile networks based on NFV scenarios |  | NETPOL
 |  |  | 810025
Rapporteur | China Mobile | Percentage of completion | 10% -> 10%
Target | SA#85 – Sept. 2019 | Main TSs | TS 28.311
Summary of progress | No input. |  | 
Outstanding issues | None. |  | 
Documents for approval by SA5 | None. |  | 

## Slide 26
Rel-16 OAM&P WIs (4/10)
Work Item | Methodology for 5G management specifications |  | METHOGY
 |  |  | 810026
Rapporteur | Ericsson | Percentage of completion | 85% -> 85%
Target | SA#85 – Sept. 2019 (Previously SA#84 – June 2019) | Main TSs | TS 32.160
Summary of progress | As input were 9 contributions of which 5 were discussion papers. Break-out sessions took place to address guidelines for mapping of stage 2 to stage 3, good progress on this was made. The group continues to work off-line to prepare such guidelines for the next meeting. |  | 
Outstanding issues | None. |  | 
Documents for approval by SA5 | None. |  | 

## Slide 27
Rel-16 OAM&P WIs (5/10)
Work Item | Intent driven management services for mobile networks |  | IDMS_MN
 |  |  | 810027
Rapporteur | Huawei | Percentage of completion | 30% -> 35%
Target | SA#86 – Dec. 2019 | Main TSs | TR 28.812, TS 28.312
Summary of progress | Contributions on the scope of intent driven management, introduction for IDMS and Intent translation, comparison of policy management and intent driven management have been discussed and agreed. The work item includes a study phase and a work item phase. Study phase: 70 % (previously 65%). Work item phase is not started. |  | 
Outstanding issues | None. |  | 
Documents for approval by SA5 | None. |  | 

## Slide 28
Rel-16 OAM&P WIs (6/10)
Work Item | Enhancement of performance assurance for 5G networks including network slicing |  |  | 5G_SLICE_ePA
 |  |  |  | 810031
Rapporteur | Intel, China Mobile | Percentage of completion |  | 60% -> 70%
Target | SA#86 – Dec. 2019 | Main TSs |  | TS 28.550, 28.552, 28.554
Summary of progress | The group discussed CRs on the following topics and agreed 15 of them: |  |  | 
 | Threshold monitoring service; Threshold monitor control IOCs; Stage 3 of performance data streaming operations; Way forward on MDAS; E-UTRA-NR Dual Connectivity related measurements; Packet loss rate measurement for N3; Packet delay measurement for N3; Measurements related to service request via untrusted non-3GPP access; |  | Measurements related to PDU session management via untrusted non-3GPP access; Measurements related to QoS of cell; Measurements related to inter-gNB and intra-gNB handover; KPI on NG-RAN handover success rate; Measurements, KPIs and LSs on DRB retainability; Correction of DRB setup related measurements; Correction of PDCP data volume measurements; Correction of PRB measurements. | 
Outstanding issues | None. |  |  | 
Documents for approval by SA5 | Rel-15 / Rel-16 CRs |  |  | 

## Slide 29
Rel-16 OAM&P WIs (7/10)
Work Item | Discovery of management services in 5G |  | 5GDMS
 |  |  | 820035
Rapporteur | Huawei | Percentage of completion | 25% -> 35%
Target | SA#85 – Sept. 2019 | Main TSs | TS 28.533
Summary of progress | As input to the meeting there were 3 CRs and 2 discussion papers. All available contributions were treated (one approved as DraftCR; one discussion paper endorsed). The group discussed: MnS discovery study aspects for way forward; MnS metainformation in general and in the context of discovery; Stage 1 discovery of MnS access information use case and related requirements; Stage 1 discovery of MnS capability information use case related requirements; Stage 1 discovery of MnS metainformation use case related requirements. |  | 
Outstanding issues | None. |  | 
Documents for approval by SA5 | None. |  | 

## Slide 30
Rel-16 OAM&P WIs (8/10)
Work Item | NRM enhancements |  | eNRM
 |  |  | 820032
Rapporteur | Nokia | Percentage of completion | 10% -> 20%
Target | SA#85 – Sept. 2019 | Main TSs | TS 28.541
Summary of progress | 12 eNRM contributions were discussed, which included Network Resource Model (NRM) definition for managed NF services and related attributes, as well as additional changes on NRM to support other new features. |  | 
Outstanding issues | As the style guideline for JSON and YANG solution set has not been completed, the stage 3 change for the new feature CRs were suspended until we have a stable stage 3 style guideline. RRMPolicy definition of NRCellCU or NRCellDU is still open, need to communicate with RAN team for clarification. |  | 
Documents for approval by SA5 | Rel-15 / Rel-16 CRs |  | 

## Slide 31
Rel-16 OAM&P WIs (9/10)
Work Item | Trace Management in the context of Services Based Management Architecture |  | TM_SBMA
 |  |  | 820036
Rapporteur | Nokia | Percentage of completion | 0% -> 10%
Target | SA#85 – Sept. 2019 (Previously SA#84 – June 2019) | Main TSs | 
Summary of progress | Discussed the NRM methodology for configurable trace. Reached an agreement on the full alignment between configurable PM, configurable notifications and configurable Trace. Offline work prior to SA5#125AH will follow. |  | 
Outstanding issues | None. |  | 
Documents for approval by SA5 | None. |  | 

## Slide 32
Rel-16 OAM&P WIs (10/10)
Work Item | Integration of ONAP and 3GPP 5G management framework |  | ONAP3GPP
 |  |  | 830026
Rapporteur | AT&T | Percentage of completion | 5% -> 10%
Target | SA#86 – Dec 2019 (Previously SA#87 - March 2020) | Main TSs | 
Summary of progress | CR to TS 28.532 dealing with adding a RESTful HTTP-based fault supervision solution for integration with ONAP VES --- was agreed. CR to TS 28.532 dealing with adding a new NRM fragment supporting the management of notifications recipients was discussed. CR to TS 28.533 to add examples to the Annex of the ONAP DCAE Collection Framework and Controllers utilizing 3GPP management services was agreed. |  | 
Outstanding issues | None. |  | 
Documents for approval by SA5 | Rel-16 CRs |  | 

## Slide 33
OAM&P SIs (1/8)
Study Item | Study on protocol enhancement for real time communication |  | FS_PROTIMP
 |  |  | 800037
Rapporteur | Nokia | Percentage of completion | 0% -> 0%
Target | SA#86 – Dec. 2019 | Main TR | TR 28.823
Summary of progress | No input. |  | 
Outstanding issues | None. |  | 
Documents | None. |  | 

## Slide 34
OAM&P SIs (2/8)
Study Item | Study on management aspects of edge computing |  | FS_MAN_EC
 |  |  | 800039
Rapporteur | Intel | Percentage of completion | 50% -> 65%
Target | SA#85 – Sept. 2019 | Main TR | TR 28.803
Summary of progress | The group discussed and agreed the following contributions to: add text in introduction clause; add a solution for end-to-end performance assurance add the conclusion for the study The group agreed to send TR 28.803 to SA plenary for information |  | 
Outstanding issues | None. |  | 
Documents | TR 28.803 for information |  | 

## Slide 35
OAM&P SIs (3/8)
Study Item | Study on tenancy concept in 5G networks and network slicing management |  | FS_TENANCYC
 |  |  | 810022
Rapporteur | Huawei | Percentage of completion | 26% -> 40%
Target | SA#85 – Sept. 2019 | Main TR | TR 28.804
Summary of progress | The group discussed and agreed the tenancy concept in context of: Representation for tenant in 3GPP management system Management entity handling for tenant in 3GPP management system Adding tenant type description Adding definition Tenant in 3GPP management system |  | 
Outstanding issues | None. |  | 
Documents | None. |  | 

## Slide 36
OAM&P SIs (4/8)
Study Item | Study on management aspects of communication services |  | FS_CSMAN
 |  |  | 810029
Rapporteur | Ericsson | Percentage of completion | 70% -> 75%
Target | SA#85 – Sept. 2019 | Main TR | TR 28.805
Summary of progress | As input to the meeting there were 18 contributions, of which 14 were agreed. The treated contributions include further clarifications in the concepts and background clause outlining relationship between communication services and management concepts, updates to use cases, new use cases and requirement were also introduced. The group made good progress in understanding the scope of management of communication services. The group agreed to send the draft TR 28.805 to SA for information. |  | 
Outstanding issues | None. |  | 
Documents | TR 28.805 for information |  | 

## Slide 37
OAM&P SIs (5/8)
Study Item | Study on Self-Organizing Networks (SON) for 5G |  | FS_SON_5G
 |  |  | 810030
Rapporteur | Intel, Verizon | Percentage of completion | 40% -> 50%
Target | SA#86 – Dec. 2019 | Main TR | TR 28.861
Summary of progress | The group discussed and approved 16 pCRs related to the following topics: Clarification, correction, and enhancement of legacy SON concept in clause 4.3. Use cases: Service quality optimization Automatic NSI creation PCI configuration pCR 28.803 solution for ANR optimization Beam optimization in CCO Cross-slice network resource optimization Multi-dimensional Resource Optimization Solution for ANR optimization |  | 
Outstanding issues | None. |  | 
Documents | None. |  | 

## Slide 38
OAM&P SIs (6/8)
Study Item | Study on non-file-based trace reporting |  | FS_OAM_RTT
 |  |  | 820037
Rapporteur | Nokia | Percentage of completion | 0% -> 0%
Target | SA#84 – June 2019 | Main TR | TR 28.806
Summary of progress | No input. |  | 
Outstanding issues | None. |  | 
Documents | None. |  | 

## Slide 39
OAM&P SIs (7/8)
Study Item | Study on non-public networks management |  | FS_OAM_NPN
 |  |  | 830024
Rapporteur | Huawei | Percentage of completion | 0% -> 2%
Target | SA#86 – Dec. 2019 | Main TR | TR 28.807
Summary of progress | The group discussed and agreed the initial skeleton. |  | 
Outstanding issues | None. |  | 
Documents | None. |  | 

## Slide 40
OAM&P SIs (8/8)
Study Item | Study on management and orchestration aspects with integrated satellite components in a 5G network |  | FS_5GSAT_MO
 |  |  | 830025
Rapporteur | Thales | Percentage of completion | 0% -> 10 %
Target | SA#86 – Dec. 2019 | Main TR | TR 28.808
Summary of progress | The skeleton of the Technical Report was created. The introduction and the scope of the technical report were approved. 3 use cases have been introduced with the associated potential requirements. |  | 
Outstanding issues | None. |  | 
Documents | None. |  | 

## Slide 41
TEI CRs (Charging & OAM&P)
Number | Title
SP-190379 | Rel-15 CRs on TEI (TEI15)
SP-190386 | Rel-13 CRs on TEI (TEI13)

## Slide 42
Charging CRs
Number | Title
SP-190380 | Rel-16 CRs on Network Exposure Charging in 5G System Architecture (5GS_Ph1_NEFCH )
SP-190381 | Rel-16 CRs on Charging Enhancement of 5GC interworking with EPC (5GIEPC_CH )
SP-190382 | Rel-16 CRs on Nchf Online and Offline charging services (OFSBI_CH )
SP-190383 | Rel-15 CRs on Data Charging in 5G System Architecture Phase 1 (5GS_Ph1-DCH)
SP-190384 | Rel-15 CRs on Service Based Interface for 5G Charging (5GS_Ph1-SBI_CH)

## Slide 43
OAM&P CRs
Number | Title
SP-190370 | Rel-15 CRs on Provisioning of network slicing for 5G networks and services (NETSLICE-PRO_NS)
SP-190371 | Rel-16 CRs on Enhancement of performance assurance for 5G networks including network slicing (5G_SLICE_ePA)
SP-190372 | Rel-16 CRs on Integration of ONAP and 3GPP 5G management framework (ONAP3GPP)
SP-190373 | Rel-16 CRs on NRM enhancements (eNRM)
SP-190374 | Rel-15 CRs on Network Resource Model (NRM) for 5G networks and network slicing (NETSLICE-5GNRM)
SP-190375 | Rel-15 CRs on Performance Assurance for 5G networks including network slicing (NETSLICE-ADPM5G)
SP-190376 | OAM8 Rel-8 Operations, Administration, Maintenance and Provisioning (OAM&P)
SP-190377 | OAM11 Rel-11 Operations, Administration, Maintenance and Provisioning (OAM&P)
SP-190378 | Rel-15 CRs on REST Solution Sets (REST_SS)
SP-190385 | Rel-15 CRs on 5G Trace management (NETSLICE-5GTRACE)

## Slide 44
Open Mobile Alliance (OMA)
  OMA ARC maintains the OMA Data Definition Specification (DDS) based on the SA5 specification for Diameter AVP code definitions (TS 32.299).
Charging cooperation

## Slide 45: OAM&P cooperation
ETSI ISG NFV
  Regular LS exchanges on the alignment of SA5 and ETSI specifications.
ETSI TC EE & ITU-T Study Group 5
  Regular LS exchanges on Energy Efficiency in mobile networks.
Network Slicing
  Regular LSs exchanges on Network Slicing with GSMA, BBF, MEF, NGMN, ETSI ISG NFV, etc.
ONAP
  SA5 representatives attended a Multi-SDO workshop arranged by ONAP in April

## Slide 46: Incoming CH LSs
Tdoc | Title | Source | Decision | ReplyIn
S5-193255 | Resubmitted LS to SA2 and SA5 on VoWiFi – VoLTE handover | GSMA | Postponed | 
S5-193249 | Reply LS from RAN3 cc SA5 on Data Volume Reporting for 5GC | R3-190935 | Noted | 
S5-193256 | LS from SA2 cc SA5 on VoWiFi – VoLTE handover | S2-1902884 | Noted | 

## Slide 47: Outgoing CH LSs
Tdoc | Title | To | Cc | ReplyTo
- | - |  |  | 

## Slide 48: Incoming OAM&P LSs
Tdoc | Title | Source | Decision | ReplyIn
S5-193246 | LS from RAN1 to SA5 on completion of CLI-RIM in RAN1 | R1-1903676 | Postponed | 
S5-193247 | Ls from RAN2 cc SA5 on L1 and L2 measurements | R2-1902806 | Noted | 
S5-193248 | LS from RAN2 to SA5 on network slicing terminology | R2-1902823 | Noted | 
S5-193250 | Reply LS from RAN3 ccSA5 on providing information on SLA fulfilment to NG-RAN | R3-191091 | Noted | 
S5-193251 | Resubmitted LS from ITU-TSG12 to SA5 on Draft new Recommendation E.RQST – “KPI targets for mobile networks” | ITU-T SG12 | Noted | 
S5-193252 | LS from TSG RAN ccSA5 on Draft new Recommendation E.RQST – “KPI targets for mobile networks” | RP-190673 | Noted | 
S5-193253 | LS from TSG SA ccSA5 in reply to LS on Draft new Recommendation E.RQST – “KPI targets for mobile networks”LS in reply to LS on Draft new Recommendation E.RQST – “KPI targets for mobile networks” | SP-190269 | Noted | 
S5-193254 | LS from SA2 to SA5 on the slicing terminology and the role of S-NSSAI parameter | S2-1902847 | Postponed | 
S5-193259 | LS from ITU-T SG2 to SA5 on cooperation on methodology harmonization and REST-based network management framework | ITU-T SG2 | Postponed | 
S5-193260 | LS from ITU-T to SA5 on new Recommendation Q.5020 (formerly Q.NS-LCMP): Protocol requirements and procedures for network slice lifecycle management | ITU-T SG11 | Noted | 

## Slide 49: Outgoing OAM&P LSs
Tdoc | Title | To | Cc | ReplyTo
S5-193391 | LS on Data activity reporting | RAN3 | RAN2 | 

## Slide 50: 2020 meeting calendar
Meeting | Date | City | Country | Host | Co-location
SA5#129 | 10-14 Feb 2020 | Sophia Antipolis | France | EF3 | 
SA5#130 | 20-24 Apr 2020 | India (city TBD) | India | IF3 | 
SA5#131 | 25-29 May 2020 | Vilnius | Lithuania | EF3 | 
SA5#132 | 24-28 Aug 2020 | N.Am. (city TBD) | N.Am. | NAF3 | 
SA5#133 | 12-16 Oct 2020 | N.Am. (city TBD) | N.Am. | NAF3 | 
SA5#134 | 16-20 Nov 2020 | China (city TBD) | China | CF3 | 

## Slide 51
Thank you!