## Slide 1: Findings from Rel-18 Discussions – Input to Rel-19 Process Discussions
3GPP SA Chair

## Slide 2: About
The planning for the Rel-19 process should try to improve on the experience gained during the Rel-18 planning and decision making.
This paper focusses on some issues that came up during the Rel-18 timeline and decision making in 3GPP SA.
The following issues came up during the Rel-18 discussions in 3GPP SA and might be considered to be improved during the upcoming Rel-19 discussions.
The list focusses on the SA2 prioritization as long as not otherwise mentioned.

## Slide 3: 6 Months Content Discussions
Rel-18 timeline for SA2 started in June 2020, the content approval for SA2 was done in December 2020. During these 6 months, SA2 kept on working mainly on Rel-17 items.
The Rel-18 work during that time was limited to discussion on S/WID details.
For Rel-17 the situation was similar.
Problems/Issues:
  “old” release overlaps too long with “new” release
  time for technical work on R18 in SA2 got practically reduced by 6 months
  forces SA2 to continue working on R18 into the R19 timeline (perpetuates situation)
  makes it hard for other WGs (SA and CT) to do a decent planning of their own Release content

## Slide 4: Number of W/SIDs approved
In the end of the R18 content discussions a large number of Study Items were approved. In fact, none of the initial proposals were dropped from the list.
Problems/Issues:
  Such a large list of approved items is close to impossible to handle in parallel in meetings, as many delegates are interested in several of the issues.
Question:
  Should there be more/stricter criteria to remove SID/WIDs from the proposed content early on, e.g. already in SA2 or at least closer to the start of the 6 month content discussions?
  Should there possibly be a limit to the number of SID/WIDs that can be handled in one Release by SA2/a SA WG?

## Slide 5: Proposal
The above listed issues should be taken into account during the Rel-19 process discussion in 3GPP SA.
It might be feasible to compile a list of issues which need to be further discussed and decided upon e.g. in September or December 2022, so that the Rel-19 stage 2 content discussions can be handled more smoothly.