## Slide 1: SA2 Chair inputs on Rel-18 study progress and a way forward proposal
Puneet Jain
SA2 Chair
TSG SA Meeting #98-e SP-221296
Dec 13 – 19, 2022

## Slide 2: Rel-18 timelines
SA#92-e
Jun/2021
SA#93e
Sep/2021
SA#94-e
Dec/2021
SA#95
Mar/2022
SA#96
Jun/2022
SA#97
Sep/2022
SA#98
Dec/2022
SA#99
Mar/2023
R17
stage 2
freeze
R17
stage 3
freeze
R17 code
freeze
stage 1
100%;
SA2 SIDs prioritization
R18 stage 2
Functional freeze
R18 stage 3
freeze
stage 1
>= 80%; SA2 SIDs Discussion
SA#100
Jun/2023
SA
Rel-18
Workshop
RAN
Rel-18
Workshop
Rel-18
timeline
Rel-18
content agreed
Rel-17
Schedule
Rel-18
Planning
exceptions
S1 normative ongoing;
SA2 SID Discussion
SA#101
Sep/2023
SA#102
Dec/2023
Exceptions
(if any)
R18 stage 2
SID Completion
/WIDs Approval
SA#103
Mar/2024
R18 code
freeze
R18 Stage 2 Study Phase
R18 Stage 2 Normative Phase
TEI18 propsoal submission/approval
TEI18 handling
R18 Stage 2 Study Agreed/ Endorsed

## Slide 3: SA2 Meeting Planning
TSG
153
(5)
152
(5)
TSG
Planned as E-meetings
June
2022
30-3
6-10
20-24
13-17
T
S
G
#
9
6
July
2022
27-1
4-8
18-29
11-15
Aug
2022
1-5
8-12
22-26
15-19
Sep
2022
29-2
5-9
19-23
12-16
T
S
G
#
9
7
Oct
2022
26-30
3-7
17-21
10-14
Nov
2022
24-28
31-4
7-11
SA2
152-E
(3+5)
SA2
153-E
(5)
14-18
Planned as F2F
154
(5)
January
2023
February
2023
16-20
23-27
30-03
06-10
13-17
20-24
March
2023
27-03
06-10
13-17
T
S
G
#
9
9
155
(5)
TSG
S
P
R
I
N
G
F
E
S
T
I
V
A
L
20-24
E-meetings
F2F -meetings
December
2022
21-25
28-02
05-08
12-16
19-30
02-06
09-13
T
S
G
#
9
8
T
H
A
N
K
S
G
I
V
I
N
G
X
M
A
S
&
N
E
W
Y
E
A
R
SA2
154-AH
(5)
Planned as E-Meetings
Planned as F2F

## Slide 4: SA2 meeting dates for 2022 & 2023
SA2 F2F meeting calendar
  SA2 #153-E (10 – 14 Oct, 2022) – Electronic ordinary meeting
  SA2 #154 (14 – 18 Nov, 2022) – F2F ordinary meeting in Toulouse, FR
  SA2 #154-AH-E (16 – 20 Jan, 2023) – Electronic Adhoc meeting
  SA2 #155 (20 – 24 Feb, 2023) – F2F ordinary meeting in Athens, GR

## Slide 5: Rel-18 Study/Work Items: Summary
UID | Name | Acronym | SID | Target | AT SA#97-e | AT SA#98-e (study/work) | Study TU (Planned) | Study TU (Used) | Normative TU (Planned) | Normative TU (Used) | Total TU (Remaining)
940060 | Study on Support of Satellite Backhauling in 5GS | FS_5GSATB | SP-211639 | 9/12/2022 | 80% | 100% / 30% | 3.5 | 3.5 | 1.5 | 1 | 0.5
940074 | Study on 5GC enhancement for satellite access Phase 2 | FS_5GSAT_Ph2 | SP-211651 | 9/12/2022 | 75% | 100% / 0% | 4 | 4 | 1 | 0 | 1
940065 | Study on Personal IoT Networks | FS_PIN | SP-211643 | 9/12/2022 | 75% | 95% / 0% | 3.5 | 3.5 | 2 | 0 | 2
940051 | Study on Phase 2 of UAS, UAV and UAM | FS_UAS_Ph2 | SP-211632 | 9/12/2022 | 80% | 98% / 0% | 3.25 | 3.25 | 2.25 | 0 | 2.25
940069 | Study on Ranging based services and sidelink positioning | FS_Ranging_SL | SP-211647 | 12/12/2022 | 70% | 85% / 0% | 3.5 | 3 | 2 | 0 | 2.5
940058 | Study on Enhancement to the 5GC LoCation Services-Phase 3 | FS_eLCS_Ph3 | SP-220069 | 12/12/2022 | 80% | 100% / 30% | 6.25 | 7.25 | 4 | 1 | 2
940077 | Study on Stage 2 for Proximity based Services Phase 2 | FS_5G_ProSe_Ph2 | SP-211653 | 12/12/2022 | 75% | 100% / 20% | 6 | 7 | 3.25 | 1 | 1.25
940061 | Study on generic group management, exposure and communication enhancements | FS_GMEC | SP-211603 | 9/12/2022 | 90% | 95% / 15% | 4 | 4 | 1.75 | 0.5 | 1.25
940071 | Study on 5G System Support for AI/ML-based Services | FS_AIMLsys | SP-220071 | 12/12/2022 | 70% | 100% / 5% | 7 | 8.5 | 5 | 0.5 | 3
940067 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | FS_5MBS_Ph2 | SP-220072 | 12/12/2022 | 75% | 100% / 20% | 7.5 | 8.5 | 4.5 | 0.5 | 3
940063 | Study on Enhancement of Network Slicing Phase 3 | FS_eNS_Ph3 | SP-220073 | 12/12/2022 | 70% | 100% / 1% | 6 | 7.75 | 3.25 | 0.25 | 1.25
940068 | Study on architecture enhancement for XR and media services | FS_XRM | SP-220705 | 12/12/2022 | 75% | 100% / 0% | 9 | 11 | 5 | 0 | 3
940056 | Study on RedCap Phase 2 | FS_REDCAP_Ph2 | SP-220074 | 9/12/2022 | 98% | 100% / 60% | 2 | 2 | 1 | 0.5 | 0.5
940066 | Study on system architecture for next generation real time communication services | FS_NG_RTC | SP-220288 | 9/12/2022 | 79% | 85% / 0% | 4 | 4.5 | 2 | 0 | 1.5
940070 | Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 | FS_ATSSS_Ph3 | SP-211612 | 12/12/2022 | 80% | 100% / 0% | 6 | 6 | 2.5 | 0 | 2.5
940076 | Study on UPF enhancement for Exposure And SBA | FS_UPEAS | SP-220417 | 12/12/2022 | 80% | 98% / 20% | 3.25 | 3.5 | 2.25 | 0.5 | 1.5
940059 | Study on Stage 2 of Edge Computing phase 2 | FS_EDGE_Ph2 | SP-220352 | 12/12/2022 | 83% | 100% / 15% | 7.25 | 8 | 4.25 | 1 | 2.5
940055 | Study on 5G Timing Resiliency and TSC&URLLC enhancements | FS_5TRS_URLLC | SP-211634 | 9/12/2022 | 83% | 98% / 50% | 5 | 7 | 4 | 1 | 1
940057 | Study on Architecture Enhancements for Vehicle Mounted Relays | FS_VMR | SP-211636 | 9/12/2022 | 80% | 100% / 20% | 2.75 | 3.5 | 2.25 | 1 | 0.5
840085 | Study on enhancement of support for 5WWC | FS_5WWC_Ph2 | SP-220419 | 12/12/2022 | 80% | 90% / 20% | 1.5 | 1.5 | 1 | 0.5 | 0.5
940053 | Stage 2 of MPS_WLAN | MPS_WLAN | SP-211595 | 3/12/2023 | 0% | NA / 0% | 0 | 0 | 2 | 1 | 1
940064 | Study on 5G AM Policy | FS_AMP | SP-220647 | 9/12/2022 | 100% | 100% / 80% | 1.5 | 1.5 | 0.5 | 0.25 | 0.25
940073 | Study on Enablers for Network Automation for 5G - phase 3 | FS_eNA_Ph3 | SP-220678 | 9/12/2022 | 75% | 100% / 25% | 8 | 9 | 6 | 1 | 4
940075 | Study on enhanced support of Non-Public Networks phase 2 | FS_eNPN_Ph2 | SP-220418 | 12/12/2022 | 75% | 98% / 50% | 5.5 | 7 | 4.25 | 1 | 1.75
840020 | Study on enhancement of 5G UE Policy | FS_eUEPO | SP-211649 | 12/12/2022 | 80% | 95% / 0% | 4.25 | 4.25 | 1.5 | 0 | 1.5
940052 | Study on System Enabler for Service Function Chaining | FS_SFC | SP-220415 | 9/12/2022 | 80% | 100% / 0% | 2.5 | 3 | 1.5 | 0 | 1
940054 | Study on Extensions to the TSC Framework to support DetNet | FS_DetNet | SP-211633 | 9/12/2022 | 90% | 90% / 0% | 1 | 1 | 1 | 0 | 1
940079 | Study on Seamless UE context recovery | FS_SUECR | SP-211654 | 9/12/2022 | 100% | 100% / 100% | 1.5 | 1.5 | 0.25 | 0.25 | 0
NOTE 1: The yellow box shows Rel-18 study items that are not 100% complete and were not on the agenda for SA2#154 Nov F2F meeting.
NOTE 2: The Orange box shows Rel-18 study items that are not 100% complete and were on the agenda for SA2#154 Nov F2F meeting.

## Slide 6: Work overload and SA2#155 F2F planning
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 |  |  | 
SID/WID | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Study TU (Used) | Normative TU (Used) | Total TU (Remaining)
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 3.5 | 1 | 0.5
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0.5 | 0.5 | 4 | 0 | 1
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 1 | 1 | 3.5 | 0 | 2
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25 | 3.25 | 0 | 2.25
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0 | 1.5 | 1 | 3 | 0 | 2.5
FS_eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 2 | 1.5 | 0.5 | 7.25 | 1 | 2
FS_5G_ProSe_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 0.25 | 7 | 1 | 1.25
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.75 | 0.5 | 4 | 0.5 | 1.25
FS_AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 2 | 2 | 1 | 8.5 | 0.5 | 3
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 8.5 | 0.5 | 3
FS_eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 0.25 | 7.75 | 0.25 | 1.25
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 11 | 0 | 3
FS_REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0.5 | 2 | 0.5 | 0.5
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 0.5 | 4.5 | 0 | 1.5
FS_ATSSS_ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0 | 1.25 | 1.25 | 6 | 0 | 2.5
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0.5 | 3.5 | 0.5 | 1.5
FS_EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 2 | 1.5 | 1 | 8 | 1 | 2.5
FS_5TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 2 | 1 | 0 | 7 | 1 | 1
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 0 | 3.5 | 1 | 0.5
FS_5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0.25 | 0.25 | 1.5 | 0.5 | 0.5
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0.5 | 0 | 1 | 1
FS_AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0.25 | 0 | 0.25 | 0 | 1.5 | 0.25 | 0.25
FS_eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 9 | 1 | 4
FS_eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 2 | 1 | 0.75 | 7 | 1 | 1.75
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0 | 0.75 | 0.75 | 4.25 | 0 | 1.5
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0.5 | 3 | 0 | 1
FS_DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 0.5 | 1 | 0 | 1
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0 | 1.5 | 0.25 | 0
Total | 119.5 | 71.75 | 191.25 | 19.25 | 21.5 | 27.5 | 29.75 | 26.25 | 23 | 26.75 | 17.25 | 134.5 | 12.75 | 44
At SA2#154, following Rel-18 study/work were allocated 1 additional TU than originally planned in order to handle large number of input documents - FS_eNS_ph3, FS_5TRS_URLLC, FS_VMR, FS_AIML_sys, FS_eNPN_Ph2, FS_MBS_Ph2, FS_eLCS_Ph3, FS_XRM, FS_ProSe_Ph2, FS_EDGE_ph2.
This is reflected in the table and 1 TU is reduced from Feb 23 meeting for these Rel-18 topics.
In additional, drafting sessions were planned on these topics but they are not counted towards TU Budget.

## Slide 7: Rel-18 Study Items with outstanding work
Name | Acronym | % Completion (study/work) | Outstanding Issues for study phase | Additional TU required
Study on Personal IoT Networks | FS_PIN | 95% / 0% | 5 editor’s notes remained in the TR conclusions, including: 1. Whether more parameters are needed in non-3GPP QoS assistance information or not. 2. Whether one PDU session can serve more than one PIN or not. 3. Whether PEMC UE needs a specific 5G subscription for providing PIN service or not. 4. Whether 5GC knows PINE ID or not. 5. How to support validity duration and time validity for a PIN. | 0.125
Study on Phase 2 of UAS, UAV and UAM | FS_UAS_Ph2 | 98% / 0% | Some editor’s notes, some of which depending on RAN work, remain in the TR conclusions. | 0.125
Study on Ranging based services and sidelink positioning | FS_Ranging_SL | 85% / 0% | RAN dependent issues including terminology alignment and Ranging/Sidelink Positioning Protocol definition. SA3 dependent issues including privacy and security concerns. | 0 (0.5 remaining for study phase)
Study on generic group management, exposure and communication enhancements | FS_GMEC | 95% / 15% | Evaluations and conclusion for KI#4: Multiple SMFs for VN group communication - static control of the connectivity between UPFs controlled by different SMF Sets - dynamic control of the connectivity between UPFs controlled by different SMF Sets | 0.25
Study on system architecture for next generation real time communication services | FS_NG_RTC | 85% / 0% | For KI#1: The converged solution to services for DCSF and IMS AS needs be agreed. For KI#3: Which Third Party specific user identities are stored in HSS needs to be concluded. The interaction between IMS and Third Party network needs to be defined. | 0.5
Study on UPF enhancement for Exposure And SBA | FS_UPEAS | 98% / 20% | Resolve the following Editor’s Note in TR conclusion for KI#2 Editor's note: how to support following case is FFS: the case where the consumer of NWDAF service doesn't provide the target DNN, S-NSSAI, but provides the application server IP address/FQDN. | 0.1
Study on 5G Timing Resiliency and TSC&URLLC enhancements | FS_5TRS_URLLC | 98% / 50% | 1) Resolution of open editor’s notes in the conclusion for KI#1 based on RAN2, RAN3, SA3 feedback. 2) Resolution of open editor’s notes in the conclusion for KI#6 based on SA1 feedback | 0.2
Study on enhancement of support for 5WWC | FS_5WWC_Ph2 | 90% / 20% | • KI1: conclude based on BBF/cable Labs input LS • KI2(TNGF): support of configuration with N:1 or 1:N relationship between SSID and TNGF | 0.25
Study on enhanced support of Non-Public Networks phase 2 | FS_eNPN_Ph2 | 98% / 50% | There are outstanding issues that are dependent on feedback from other WGs (SA1, SA3 and CT1), which are agreed to be considered during normative phase. Whether to standardize any Localized Service related information that may be sent to the UE to aid manual selection of hosting network. | 0.5
Study on enhancement of 5G UE Policy | FS_eUEPO | 95% / 0% | There are four Editor’s notes in the conclusion: Editor's note: How to provide VPLMN ID to UE along URSP is FFS. Editor's note: Coordination with UPEAS is required to define how NWDAF interacts with UPF. Editor's note: It is FFS how to handle the EPS mobility for a UE that is dual registered (i.e. with a registration in 5GS via N3IWF and attached to EPC/E-UTRAN) and thus whether UE policy association can be maintained in both EPS and 5GS or only in 5GS or EPS. Editor's note: It is FFS whether URSP mapping in EPS requires any dynamic configuration mechanism (e.g. as proposed in Sol #17) to address the aspects identified in the 2nd bullet of the KI#3 description. In addition, KI #2 conclusion on solution based on UE reporting assistance information during PDU Session Establishment/Modification to 5GC needs to be discussed. | 0.2
Study on Extensions to the TSC Framework to support DetNet | FS_DetNet | 90% / 0% | Conclude open issue in the TR: The TR leaves it open whether to optionally allow to insert a NEF in the signalling path, and on whether to define mechanisms to expose the N6 uplink routing table to the DetNet controller. | 0.25

## Slide 8: Way Forward
Rel-18 study items shown on slide#7 have outstanding work that doesn’t require significant additional TU. Please note some of these study items could not be on agenda for SA2#154 due to constraint in scheduling the parallel F2F session.
It is proposed to endorse the following way forward -
  SA2 can schedule the Rel-18 study items (on slide#7) at SA2#154AH-e (Jan 2023) to conclude the remaining outstanding issues. Additional TU budget required to conclude the outstanding issues will be taken from their respective overall TU budget.
  No Rel-18 study items will be scheduled after SA2#154AH-e. If the outstanding issues for Rel-18 study items (on slide#7) are not concluded by SA2#154AH-e (Jan 2023) then they should be dropped from the Rel-18.