## Slide 1: Way Forward on Rel-18 Planning
3GPP TSG SA#98e SP-221310
Electronic, 13-19 December 2022 Agenda Item 7.3

## Slide 2: Rel-18 Proposed Alternative Timeline
Proposal for freeze date shift by one quarter
  Extend both Stage 2 and Stage 3 (SA/CT) shift
    Impact on Open API freeze date will be discussed during RAN, SA, and CT common Rel-18 planning.
    RAN Rel-18 timeline is NOT part of this discussion
Ground rules (Guidance from SA to SA2) shall be enforced
  1) Finish all Rel-18 study items by Jan-2023.
  2) Normative work will be limited to existing approved WIDs, with possible updates due to remaining study conclusions in Jan- 2023.
  3) Any SA2 work required to allow RAN progress shall be completed by SA#99. This is normal alignment work and TU allocation should be taken from SA2 overall buffer.
  4) Finalize normative work by SA#100. SA expects none or very few of exceptions for SA#100 e.g. due to inter TSG dependence.
Rel-18 | Current | Proposal
Stage 2 | TSG#99 (Mar 2023) | TSG#100 (Jun 2023) with ground rules
Stage 3 PHY | TSG#101 (Sep 2023) | TSG#101 (Sep 2023)
Stage 3 RAN | TSG#102 (Dec 2023) | TSG#102 (Dec 2023)
Stage 3 SA/CT | TSG#102 (Dec 2023) | TSG#103 (Mar 2024)
RAN ASN.1 | TSG#103 (Mar 2024) | TSG#103 (Mar 2024)
CT Prot., Open APIs | TSG#103 (Mar 2024) | TBD

## Slide 3: Thank You!