## Slide 1: Rel-18 & Rel-19 Planning
Huawei, Hisilicon
SP-221282_rev2

## Slide 2: Rel-19 planning
In Release 17 and Release 18 SA content discussion, prioritization and approval (mostly for SA2) took 6 months from the start of the release causing the actual technical discussion time budget is very limited. 3GPP SA needs to take serious efforts to improve in order to free more time for technical discussions.
  It is reasonable to follow the SA timeline with approving and starting the work earlier on if there is consensus while not necessarily waiting for the RAN final package.
SA2 and possibly other SA WGs should, based on the timeline and the resulting number of available TUs, come up with a maximum number of S/WIs which would be realistic to be worked on during Rel-19.
Conclusion on Release timeline and contents in the same plenary would lead to re-planning and additional efforts, e.g. for the determination of how much content fits into a release. It is worthwhile to consider approving the timeline at the beginning of the content discussions.
All issues which impact RAN / CT need to be decided together with the other TSGs.

## Slide 3: Overview of R19 planning
Release 19
Release 18
SA#98-e
12/22
SA#99
EU 3/23
SA#100-e
6/23
SA#101
9/23
SA#102-e
12/23
SA#103
3/24
Agree R19
Planning
Process
Stage 2 Functional
Freeze
SA/CT
Stage 3 Freeze
3GPP R19
Timeline Approval
R19 SA
workshop
SA final R19 Content Approval with RAN/CT
SA 1st R19
Content Approval
RAN 1/2/3 package
approval
RAN2/3
function Freeze
RAN 1
function Freeze

## Slide 4: Proposals on Rel-19 planning
It is agreed to the planning schedule as slide 3 shows.
  March 2023 SA#99: Discussion and approval of Rel-19 timeline
  June 2023 SA#100e: SA R19 workshop binding with SA plenary(i.e. before SA plenary or in the same week of SA plenary)
  Sept 2023 SA#101: Approve first package of Rel-19 SA content
  Dec 2023 SA#102e: Approve final SA package with RAN and CT.
  Note: How the work package can be split between Sep and Dec (e.g. how many SIDs can start already in September) is TBD.
SA give guidance:
  SA2 and optionally other SA WGs should give based on the timeline and the resulting number of available TUs, come up with a maximum number of S/WIs which would be realistic to be worked on during Rel-19.
  SA2 should start to arrange some slot(s) since Q2 2023 for Rel-19 SID presentation and discussion.

## Slide 5
Thank you!