## Slide 1: 3GPP TSG-SA meeting #99 SP-230344 Rotterdam, Nederlands, March 21th – 24th, 2023 Agenda Item: 7.4 Source: Ericsson Title: Time schedule for Release 19 Document for: Discussion, Decision

## Slide 2: Considerations
TSG-SA #98e made a coordinated decision with TSG-RAN and TSG-CT to shift the time schedule of Release 18 with 3 months.
Furthermore, the Rel-19 planning to set the Rel-19 content was agreed, with a joint RAN and SA content setting in TSG#102, December 2023.
It was also agreed to target a first subset of Rel-19 content to be approved in TSG-SA #101, September 2023, to allow SA stage 2 WGs, such as SA2, to start work on Rel-19 on approved study items in their October and November meetings, Q4 2023.
The next slide is illustrating the release schedule where Rel-19 release length is 18 months.
It is seen as essential that this SA#99 meeting agrees on the timeline for Rel-19 to allow the SA WGs to discuss work planning to define the capacity, taking into account reasonable work schedule, for the WG in terms of:
    upper limit on number of number of Study Items/Work Items,
    budget for TEI19 work,
    budget for maintenance work and
    a reasonable buffer for unexpected work.
  It will be beneficial for the SA workshop in June to take the input on work capacity from each SA WG into consideration, and to potentially endorse the work capacity of the WGs to guide further work planning leading up to the approval of a work package in December TSG meetings, as well as the first package in TSG-SA meeting in September.

## Slide 3: Proposed 3GPP Release plan for Rel-19

## Slide 4: Proposals
The release schedule for Rel-19 is 18 months.
The completion date for stage 1 (100%) is December 2023, with 80% completion by September 2023.
The completion date for the stage 2 (in SA2 and SA6) is December 2024.
    As a general principle, the stage 2 study items have a general target to complete 6 months earlier than the target date for normative stage 2 completion.
    The SA3 completion date for stage 2 specifications is March 2025.
The completion date for stage 3 specifications is September 2025.
    This is a coordinated stage 3 target date with RAN stage 3 functional freeze.
    OpenAPI files and ASN.1 coding is targeted to freeze December 2025.