## Slide 1: FS_PALS Status Update Study on 5G Networks Providing Access to Localized Services
Jack Nasielski
Qualcomm
FS_PALS Rapporteur
3GPP TSG-SA WG1 Meeting #92e
Electronic Meeting, 10-19 November 2020
Notes: 1

## Slide 2: FS_PALS Progress
Progress made at this meeting
  Agree TR skeleton, scope and overview
  Agree initial use cases
Work/Study Item Completion: 35%
Controversial issues
  None
Notes: 1

## Slide 3: FS_PALS Planning
Planning for subsequent meetings
  SA1#92e_adhoc (Jan 2021): 50%
    New/Updated use cases and potential requirements
  SA1#93 (Feb-Mar 2021): 75%
    New/Updated use cases and potential requirements
    Start consolidation
  SA1#94e (May 2021): 100%
    Updated use cases and potential requirements
    Complete consolidation and conclusions
Notes: 1

## Slide 4: Work plan between meetings
Email coordination
  Coordination among interested/contributing companies, about planned inputs, use cases, etc.
  Before each SA1 meeting
  To be moderated by the rapporteur
Notes: 1

## Slide 5: FS_PALS Completion Date
Current expected completion dates:
  For information: SA#91 (03/2021)
  For approval: SA#92 (06/2021)
Have these dates been changed at this meeting? no
  If yes, previous target completion dates:
    For information: <mm/yyyy> SA#xx
    For approval: <mm/yyyy> SA#xx
Notes: 1

## Slide 6: FS_PALS History
This WI has been approved at SA#89e
  Approved WID is in tdoc SP-200798
History of completion rates
  SA1#92e (Nov 2020): 35%
Notes: 1