## Slide 1: FS_VMR Status Update Study on vehicle-mounted relays
Francesco Pica
Qualcomm
FS_VMR Rapporteur
3GPP TSG-SA WG1 Meeting #92e
Electronic Meeting, 10-19 November 2020
Notes: 1

## Slide 2: FS_VMR Progress
Progress made at this meeting
  Agreed TR skeleton, and scope
  Agreed draft overview section
  Agreed 16 use cases
  Agreed draft on other considerations
Work/Study Item Completion: 35%
Controversial issues
  None
Notes: 1

## Slide 3: FS_VMR Planning
Planning for subsequent meetings
  SA1#92e_adhoc (Jan 2021): 60%
    New/Updated use cases and potential requirements
  SA1#93 (Feb-Mar 2021): 80%
    New/Updated use cases and potential requirements
    Start consolidation
  SA1#94e (May 2021): 100%
    Updated use cases and potential requirements
    Complete consolidation and conclusions
Notes: 1

## Slide 4: Work plan between meetings
Email coordination
  Coordination among interested/contributing companies, about planned inputs, use cases, etc.
  Before each SA1 meeting
  To be moderated by the rapporteur
Notes: 1

## Slide 5: FS_VMR Completion Date
Current expected completion dates:
  For information: SA#91 (03/2021)
  For approval: SA#92 (06/2021)
Have these dates been changed at this meeting? n
  If yes, previous target completion dates:
    For information: <mm/yyyy> SA#xx
    For approval: <mm/yyyy> SA#xx
Notes: 1

## Slide 6: FS_VMR History
This WI has been approved at SA#89e
  Approved WID is in tdoc SP-200798
History of completion rates
  N.A.
Notes: 1