## Slide 1: FS_Resident Status Update Study of Enhancements for Residential 5G
Toon Norp
KPN
FS_Resident Rapporteur
3GPP TSG-SA WG1 Meeting #94e
Electronic Meeting, 10 – 20 May 2021
Notes: 1

## Slide 2: FS_Resident Progress
Progress made at this meeting
  General clean up of existing text
  Architecture description
  Requirement on regulatory aspects
  10 updates of existing use cases
  4 new use cases
  Framework for consolidation and one consolidated req.
  Conclusion section
Work/Study Item Completion: 85%
  Even though completion is >80%, we do not send TR for approval to avoid CR process next meeting
Controversial issues
  None
Notes: 1

## Slide 3: FS_Resident Planning
Planning for subsequent meetings
  SA1#91e (Aug 2020): 30%
    Outline, Scope, Use cases with potential requirements
  SA1#92e (Nov 2020): 50%
    (Updates of) use cases with potential requirements
  SA1#93e (Mar 2021): 75%
    Clean up of terminology, new and updates of use cases, clean up of editor notes, discuss normative WID
  SA1#94e (Jun 2021): 85%
    Identification / credentials of PRAS, Starting consolidation process, Conclusions, Adding figures
  SA1#94ah (Jul 2021) or ad-hoc: 100%
    Consolidation of requirements and clean-up of use cases
Notes: 1

## Slide 4: Work plan between meetings
Phone conference
  At least conference call on the consolidation will be organised
  Probably followed by a conference call on how to structure the normative text (addressing also the relation with PIN)
Notes: 1

## Slide 5: FS_Resident Completion Date
Current expected completion dates:
  For information: SA#91 (03/2021)
  For approval: SA#92 (06/2021)
Have these dates been changed at this meeting? N
  If yes, previous target completion dates:
  Guide: Remove “If yes…” and all subsequent bullets if current completion date is unchanged
Notes: 1

## Slide 6: FS_Resident History
This WI has been approved at SA1#88e
  Approved WID is in tdoc SP-200576
History of completion rates
  SA1#90 (05/2020): 0%
  SA1#91e (08/2020): 30%
  SA1#92e (11/2020): 50%
  SA1#93e (03/2021): 75%
  SA1#94e (05/2021): 85%
Notes: 1