## Slide 1: FS_ 5GSAT_Ph3 Status Update Study on satellite access - Phase 3
Rapporteur: Thierry Bérisot, Novamint
Co-Rapporteur: Xu Xia, China Telecom
3GPP TSG-SA WG1 Meeting #98e
Electronic Meeting, May 9-19, 2022
Notes: 1

## Slide 2: FS_ 5GSAT_Ph3 Progress
Progress made at this meeting
  Agreed SID
Study Item Completion: 0%
Controversial issues
  None
Notes: 1

## Slide 3: FS_ 5GSAT_Ph3 Planning
Planning for subsequent meetings
  SA1#99e (Aug 2022): 35%
    Agree TR skeleton & scope
    Agree initial Use cases and potential requirements
  SA1#100e (Nov 2022): 80%
    Updated/Additional Use cases and potential requirements
    Consolidation
    Send TR to SA for information
  SA1#101e (Feb 2023): 100%
    Conclusions, TR corrections/clean-up
    Send TR to SA for Approval
Notes: 1

## Slide 4: Work plan between meetings
Email coordination
  Coordination among interested/contributing companies, about planned inputs, use cases, etc.
  Before each SA1 meeting
  To be moderated by the rapporteur
Conference calls
  TBD (upon need)
Notes: 1

## Slide 5: FS_ 5GSAT_Ph3 Completion Date
Current expected completion dates:
  For information: SA#98 (12/2022)
  For approval: SA#99 (03/2023)
Have these dates been changed at this meeting? n
  If yes, previous target completion dates:
    N/A
Notes: 1

## Slide 6: FS_ 5GSAT_Ph3 History
This SI has been agreed at SA1#98e
  Agreed SID is in Tdoc S1-221229
History of completion rates
  N.A.
Notes: 1